## Slide 1: Texas Nodal Market Implementation Program Scenarios / Trade-Offs September 5, 2006

## Slide 2: Agenda - Tuesday
Introduction | Ron Hinsley
Background Discussion of ERCOT Nodal Transition Plan | Floyd Trefny
EDS Walk-Through | Floyd Trefny
Overall Program Review | Kathy Hager
Market Participant Engagement & Readiness | Trip Doggett & Pat Harris
ERCOT Readiness & Transition | Steve Grendel
Integration & Design Authority | Jeyant Tamby
Network Model Management System | Raj Chudgar

## Slide 3: Agenda - Wednesday
Energy Management System | Carlos Gonzalez-Perez
Market Management System | Al Hirsch
Congestion Revenue Rights | Shawna R. Jirasek
Commercial Systems | Raj Chudgar
Enterprise Data Warehouse | Kathy Hager
Infrastructure | David Forfia
Integration | Kathy Hager
Integration Testing | Glen Wingerd
Program Office | Michael Collins
Next Steps | Kathy Hager

## Slide 4: Texas Nodal Implementation Scenarios Briefing for PUCT Commissioners August 28 - 30, 2006

## Slide 5: Executive Summary
The principal binding document (the Protocols signed into Order) established 3 major requirements for the Nodal Program:
  The scope of Nodal
  The implementation date (1/1/09)
  The requirement for a “big bang” implementation
Market Participants established the ERCOT Nodal Transition Plan, which sets requirements for approach:
  The trials sequence and requirements for Early Delivery Systems (EDS) to enable Market Participants to test and gain confidence in the new systems and processes – over two years
  It also envisaged the potential for phased implementation
The key risk mitigation the Program recommends is phasing of implementation:
  The acceptance of phased implementation will have a fundamental impact on timeline and cost
  Capabilities can certainly be implemented earlier that 1/1/09 (some will be later)
  An early decision will enable the re-direction of detailed planning to ensure the robustness of estimates
We seek concurrence for this recommendation through this briefing

## Slide 6: Phasing scenario logic
Scope, schedule and cost are the three primary variables of the program – quality is implied.
Scenario construction is focused on scope and schedule options with consideration of consequential impact on cost, benefit and delivery risk
Primary variable
“Time to market” is a primary driver for the program.
The ERCOT Nodal Transition Plan – developed with the Market Participants – envisages the following implementation options, based on business need and benefit:
  start-up of Real-Time operations, or
  start-up of Real-Time operations and RUC or
  start-up of Real-Time operations including DAM and RUC and settlement of all systems
Appendix 2 describes how the major capabilities to be delivered through Nodal drive the anticipated types of benefits
Secondary variable
The Nodal baseline envisages delivering the complete scope of the Protocols signed into Order 4/5/06.
The Market Participants developed the Protocols to address the unique needs and characteristics of the Texas market.
De-scoping of the protocols is not considered in the scenario analysis; this are confined to phasing of scope
Appendix 1 describes the unique characteristics of ERCOT (compared to other ISOs) and Texas Nodal (compared to other Nodal Markets)

## Slide 7: Implementation scenario definition – the two phasing scenarios
Scenario #2 – Three Incremental Releases (recommended)
Scenario #1 – “Big Bang” (current baseline)
  Release 1: Single Entry Model (with stable and capable SE):
    Basic Network Model & SE Criteria
    NMMS (UI)
    ICCP (RTU migration)
    Nodal EMS (non-live)
    SCADA P2P Check-Out
  Release 2: Real Time Operations (LMPs with Real Time CRR to hedge local congestion):
    NMMS (Operations UI)
    Nodal EMS (live)
    Outage Scheduler
    SCED
    RUC
    SASM
    COP
    Emergency Operations
    Trades, Schedules
    Offers (3 part)
    CRR (settled in RT)
    CMM (part)
  Release 3: Forward Markets (DAM & CRR):
    NMMS (Planning UI)
    DAM
    CRR (full)
    CMM (full)
    Full back-end (x4)
Versus

## Slide 8: Timeline impact
Scenario #1 – “Big Bang” (current baseline)
Release 1: Single Entry Model (with stable and capable SE)
Release 2: Real Time Operations (LMPs with Real Time CRR to hedge local congestion)
Release 3: Forward Markets (DAM & CRR)
  Accurate model, SCADA P2Ps, drives all calculations
  Increased dispatch efficiency (unit-level)
  More granular, locational price signals
  Direct assignment of congestion costs
  Additional participation in and increased liquidity for Texas energy sales
Depends on EMS and staffing
Later than baseline
Much earlier than baseline
Early Delivery Systems (EDS) and Trials Sequence
Core Power and Market Operations Product development
Go Live
(1 year)
(2 years)
Scenario #2 – Three Incremental Releases (recommended)

## Slide 9: Phased implementation – a timeline to achieve 1/1/09 and shutdown Zonal early
EMS
Trials & Implementation
MMS
CRR
MIS
NMMS
Commercial Systems
ERCOT & MP Readiness
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q1 2008
Q3 2006
Q1 2009
Integration
EDW
Q2 2009
Qualification Freeze
EDS 3
EDS 4
MMS FAT
ITEST
CRR Design, Build, Pre-FAT
CRR FAT
ITEST
Final MP Interface Specs 3/31
MP Registration complete
168 hour market trial
Real Time Operations GO/NO GO
Zonal Shutdown GO/NO GO
MIS (EMS/MMS/CRR) Design, Build, Pre-FAT
EDW FAT
ITEST
Statements Layout
Script test
End of Trials
MP Nodal Registration
MP Financial & Operational Qualification
ITEST
EMS
EMS FAT
EMS Requirements, Conceptual Design
ITEST
MIS (SCED) Design, Build, Pre-FAT
MIS FAT
MMS Design, Build, Pre-FAT
MMS Requirements, Conceptual Design
ITEST
OS Build
FAT
OS Requirements, Conceptual Design
CRR Requirements, Conceptual Design
Commercial Systems Design, Build, Pre-FAT
CS FAT
ITEST
EDW Requirements, Conceptual Design
ITEST
SCED Build
SCED FAT
SCED Requirements, Conceptual Design
Registration ready
MPSCED Offers
Business Requirements complete 10/30
Preliminary MP Interface Specs 12/31
CS Requirements, Conceptual Design
EDW Design, Build, Pre-FAT
MIS FAT
ITEST
Begin MP trial participation
EDS 4 MP SAT
OTS ITEST
OTS FAT
EDS 3 Data Validation
Planning UI
FAT
ITEST
Naming Convention DB
Common model update process
NMMS Conceptual Design
Naming Convention information collection
Model Data Certification
Model Data Remediation Reconciliation
NMMS Build
Outage Scheduler
EDS 1/2
Build
FAT
ITEST
Requirements, Conceptual Design
ITEST
OS FAT
Forward Markets GO/NO GO
Single Entry Model GO LIVE
Q3 2007
Operations UI

## Slide 10: Phased implementation requires adjustments to Early Delivery System strategy
EDS 1/2 – Single Entry Model
Basic Network Model & SE Criteria NMMS (UI internal only) ICCP (RTU migration) Nodal EMS (non-live)
EDS 3 – Real Time Operations
NMMS (Operations UI) Nodal EMS (live) Outage Scheduler SCED RUC SASM COP Emergency Operations Trades, Schedules Offers (3 part) CRR (settled in RT) Financial Transfer CMM (part) EDW & MIS (part) Integration (part) LMPs published 8*5 support
EDS – Forward Markets
NMMS (Planning UI) DAM CRR (full) CMM (full) MIS (full) EDW & MIS (full – x4) 8*5 support (24*7 for MP SAT) ERCOT & Market Readiness Criteria approved
EDS 4 Trial outcomes
All MP Registration complete for Go Live OTS complete All market facing interfaces complete Testing of all markets complete 168 Hour test complete All interfaces validated Training complete MP financial & operational qualification complete Market Readiness Declarations met
Forward Markets – GO/NO GO
EDS 3 Trial outcomes
6 month SCED test completed EMS enhancements complete MP offers LFC, OS, RPP complete All MP Registration complete for Go Live OTS complete All market facing interfaces complete Testing of all markets complete 168 Hour test complete All interfaces validated Training complete MP financial & operational qualification complete Market Readiness Declarations met “Home Team” transitioned
Real Time Operations – GO/NO GO Zonal Shutdown – GO/NO GO
Q2 2008
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2007
Q1 2008
Q1 2009
Q3 2007
EDS 3
EDS 4
EDS 4 MP SAT
EDS 3 Data Validation
EDS 1/2
EDS 1/2 Trial outcomes
SE Criteria achieved Telemetry criteria achieved
Single Entry Model (with stable and capable SE) GO LIVE

## Slide 11: Texas Nodal Appendix 1 – How Texas Nodal Is Unique

## Slide 12: There are essential, “environmental” differences between ERCOT and other ISOs
Characteristic | Implication
Intra-state electric interconnection 1 of 3 North American interconnections “Island” - Connected to other ISOs by DC ties only One of 10 NERC Regional Reliability Councils | FERC pro-forma open access transmission tariff does not apply to ERCOT, except across DC tie lines, allowing for uniqueness in scheduling and power delivery protocols. At ERCOT, annual capacity supply is driven by Market Participant investments rather than ISO coordinated capacity synergy as in US Northeast. There is no Installed capacity market (ICAP) at ERCOT, reducing the complexity of the real time market 99% of power generation provided within Texas. At ERCOT, Ancillary Service products are limited and different than other ISOs. Other ISOs, due to tight interconnections, can share reserves and procure from adjacent areas for shortages, while ERCOT must provide all AS capacity to satisfy its needs. Sensitivity of the ERCOT grid to disturbances is generally higher
Single regulatory jurisdiction – Public Utility Commission of Texas (PUCT) | Single authority for Texas power governance for wholesale, retail, planning and any other power related topic. Together with its isolation as an electric grid, this allows unique ERCOT market protocols compared to all other ISOs
Registration is unique in Texas | All MPs must register all generation units, markets, legal entities etc with ERCOT ERCOT has multiple QSE level registration (level 1 – 4) Level 4 QSEs must perform fidelity tests for generation units under unique protocols
Unique provisions for Non Opt-In Entities (Munis and Coops) in Texas | Customization required for NOIE provisions in ERCOT such as ability to carry CRRs to Real-Time, Dynamically Scheduled Resources, Pre-Assigned CRRs, Self Schedules
Requirement to model equipment at lower voltages (down to 60kV) | Increased complexity with respect to system observability and measurements Enforcement of constraints to a more granular level adds complexity to network modeling process at ERCOT when compared to other ISOs in the high frequency of model changes (ERCOT has thousands compared to other ISOs having hundreds)
High pace of economic growth in Texas | Increased complexity in maintaining load models. Many model/field changes require significant modification within the power grid model in order predict power flow and power consumption.
Wholesale and Retail scope impact | Size of retail choice responsibilities is significantly larger than any other ISO in North America. ERCOT is the central hub of the Retail transaction system. There is a big difference in metering, load profiling and data aggregation (ERCOT deals with 7M ESI Id’s while other ISOs may deal with aggregated data from TDSPs)

## Slide 13: Texas Nodal Protocols differ from other nodal markets (1 of 2)
Component | Implication | Impact on complexity
Common, time-based network model for all major ERCOT applications | Multiple consuming applications including EMS, MMS, CRR and Outage Scheduler Multiple file formats and layouts creates unique interfaces for each application Significant impact on culture, business processes, software for planning and operations | 
Congestion Revenue Rights: CRRs are available between any two Settlement Points, in the form of Options or Obligations Non Opt-In (NOIE) Entities (Munis and Coops) are allowed to carry their pre-Assigned CRRs to be settled in the Real Time energy market | Ability to create millions of market product permutations increases complexity of solution CRR Bilateral trading forces multiple source systems to settlements (MMS and CRR application) Additional feature for NOIE CRR secondary market increases complexity for CRR settlements | 
Day Ahead Market: Requirement to co-optimize markets in the Day Ahead for Ancillary Services capacity, point-to-point obligation CRRs and forward financial energy markets is unique to ERCOT Protocols specify a unique, automated methodology for establishing price caps. Further, protocols require the prices be published before the service is provided | DAM methodology for price caps creates uniqueness and forces MPs to understand the distinctions in the ERCOT market DAM is not necessary for reliability of the electric grid - participation in DAM is voluntary, except for RMR units | 
Reliability Unit Commitment: RUC rules are unique to ERCOT, and have significant implications to unit commitment | Direct assignments of DRUC and HRUC costs are unique in each nodal market | 
Real Time Market: Protocols specify the use of average losses in the calculation of LMPs | Other markets specifically include the calculation of marginal losses in their LMPs | 

## Slide 14: Texas Nodal Protocols differ from other nodal markets (2 of 2)
Component | Implication | Impact on complexity
Settlement is unique to ERCOT | Market rules for settlements are unique across ISOs – all settlements must be built from scratch | 
Credit Monitoring creating limited exposure to ERCOT markets | ERCOT will evaluate credit exposure and collateral for every market participant on a daily basis, updating the MPs credit limits for any ERCOT market Additional credit checks will be performed as part of the CRR Auction optimization. This unique aspect of ERCOT’s transmission rights market is intended to maximize revenues from CRR auctions, and therefore value to Loads Increases the complexity of the solution system and the volume of data transactions to the systems | 

## Slide 15: Texas Nodal Appendix 2 – Benefits Logic of Texas Nodal

## Slide 16: Benefits Logic – How Nodal Capabilities Drive Value (1 of 2)
Increased dispatch efficiency
(unit-level)
Nodal RT operations
New Day-Ahead Energy Market
New CRR Market
Additional participation in and increased liquidity for Texas energy sales
More granular, locational price signals
Increased transparency of energy prices
Reduction in congestion costs
Benefits passed on to consumers
Efficient location of new generation
Efficient location of new transmission
Direct assignment of congestion costs
Reduction in Energy/AS prices
Reduction in undesirable market behavior
True commodity-based pricing
Opportunity hedge real-time energy and day ahead congestion costs
Enforcement of open access and real customer choice
Reduction in incentive for aberrant market behavior
Increased potential for locational demand-side participation
Key Nodal capabilities…
…have direct impacts …
…that drive efficient market behaviors…
…and deliver improved economic outcomes for market participants and benefits to consumers

## Slide 17: Benefits Logic – How Nodal Capabilities Drive Value (2 of 2)
Increased dispatch efficiency
(unit-level)
Nodal RT operations
New Day-Ahead Energy Market
New CRR Market
Additional participation in and increased liquidity for Texas energy sales
More granular, locational price signals
Increased transparency of energy prices
Reduction in congestion costs
Benefits passed on to consumers
Efficient location of new generation
Efficient location of new transmission
Direct assignment of congestion costs
Reduction in Energy/AS prices
Reduction in undesirable market behavior
True commodity-based pricing
Opportunity hedge real-time energy and day ahead congestion costs
Enforcement of open access and real customer choice
Reduction in incentive for aberrant market behavior
Increased potential for locational demand-side participation
Key Nodal capabilities…
…have direct impacts …
…that drive efficient market behaviors…
…and deliver improved economic outcomes for market participants and benefits to consumers
Accurate, time-based models are a key enabler

## Slide 18: Going-in critical path analysis – 1/1/09 is unlikely – the basis for the initial project estimates to deliver
EMS
Early Delivery Systems
MMS
CRR
MIS
NMMS
Commercial Systems
ERCOT & MP Readiness
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Outage Scheduler
EDW
“UI in production”
Q2 2009
Qualification Freeze
EDS 3 (TXMACS 0.3)
SCED; MP SCED Offers
EDS 4 TXMACS 0.4) with selected MPs
EDS 5 (TXMACS 0.5)
MMS FAT
MMS SAT
CRR Design, Build, Pre-FAT
CRR FAT
CRR SAT
Final MP Interface Specs 3/31
MP Registration complete
MIS FAT
MIS SAT
168 hour market trial
FAT
SAT
Naming Convention DB
NMMS Build
Common model update process
NODAL GO LIVE
MIS (EMS/MMS/CRR) Design, Build, Pre-FAT
EDW FAT
EDW SAT
Statements Layout
Script test
Credit Monitoring
End of Trials
MP Nodal Registration
MP Financial & Operational Qualification
EMS SAT
EMS
EMS FAT
EMS Requirements, Conceptual Design
MIS SAT
MIS (SCED) Design, Build, Pre-FAT
MIS FAT
MMS Design, Build, Pre-FAT
MMS Requirements, Conceptual Design
OS SAT
OS Build
OS FAT
OS Requirements, Conceptual Design
CRR Requirements, Conceptual Design
Commercial Systems Design, Build, Pre-FAT
CS FAT
CS SAT
EDW Requirements, Conceptual Design
SCED SAT
SCED Build
SCED FAT
SCED Requirements, Conceptual Design
Registration ready
MPSCED Offers
Business Requirements complete 10/30
Preliminary MP Interface Specs 12/31
CS FAT
CS SAT
EDW FAT
EDW SAT
EDW FAT
EDW SAT
CS Requirements, Conceptual Design
EDW Design, Build, Pre-FAT
MIS FAT
MIS SAT
Begin MP trial participation
“Non-binding settlements”
Financial Transfer
CS FAT
CS SAT
EDS 4 MP SAT
TXMACS 1.0
Live operations
MIS FAT
MIS SAT
“CRR Auction for Go Live”
OTS SAT
OTS FAT
EDS 3 Data Validation
NMMS Conceptual Design
Naming Convention information collection
Model Data Certification
Model Data Remediation Reconciliation
Assumptions affecting the critical path
The current State Estimator will meet the necessary criteria
Current NMMS product will be capable of providing Real Time Models for any Nodal System
Vendors selection will be done by Mid-June
Vendors will share detailed design documents with other vendors for interface definitions
TDSPs will be trained on new NMMS and there will dual entry of models – into the new NMMS and into GENESYS. ERCOT will have enough staff to handle this work
To allow for interface definitions, detailed design documents of individual projects can be completed 80 hours after one another. The order of completion will be NMMS – MMS/EMS/SE – CRR/Outage Schedule – Commercial Systems – MIS/EDW
To satisfy section 17.3 of the Nodal protocols, ERCOT will deploy COGNOS and SAS to provide PUCT with the ability to generate reports
ERCOT would need 6 months of integration testing on applications such as MMS, CRR and NMMS
Areva’s EMS will handle CIM models
All systems have to conform with the integrated Data Dictionary
TPTF will hold review meetings as required for approval of requirements and conceptual design documents

## Slide 19: Phased implementation – a timeline to achieve 1/1/09 and shutdown Zonal early
EMS
Trials & Implementation
MMS
CRR
MIS
NMMS
Commercial Systems
ERCOT & MP Readiness
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q1 2008
Q3 2006
Q1 2009
Integration
EDW
Q2 2009
Qualification Freeze
EDS 3
EDS 4
MMS FAT
ITEST
CRR Design, Build, Pre-FAT
CRR FAT
ITEST
Final MP Interface Specs 3/31
MP Registration complete
168 hour market trial
Real Time Operations GO/NO GO
Zonal Shutdown GO/NO GO
MIS (EMS/MMS/CRR) Design, Build, Pre-FAT
EDW FAT
ITEST
Statements Layout
Script test
End of Trials
MP Nodal Registration
MP Financial & Operational Qualification
ITEST
EMS
EMS FAT
EMS Requirements, Conceptual Design
ITEST
MIS (SCED) Design, Build, Pre-FAT
MIS FAT
MMS Design, Build, Pre-FAT
MMS Requirements, Conceptual Design
ITEST
OS Build
FAT
OS Requirements, Conceptual Design
CRR Requirements, Conceptual Design
Commercial Systems Design, Build, Pre-FAT
CS FAT
ITEST
EDW Requirements, Conceptual Design
ITEST
SCED Build
SCED FAT
SCED Requirements, Conceptual Design
Registration ready
MPSCED Offers
Business Requirements complete 10/30
Preliminary MP Interface Specs 12/31
CS Requirements, Conceptual Design
EDW Design, Build, Pre-FAT
MIS FAT
ITEST
Begin MP trial participation
EDS 4 MP SAT
OTS ITEST
OTS FAT
EDS 3 Data Validation
Planning UI
FAT
ITEST
Naming Convention DB
Common model update process
NMMS Conceptual Design
Naming Convention information collection
Model Data Certification
Model Data Remediation Reconciliation
NMMS Build
Outage Scheduler
EDS 1/2
Build
FAT
ITEST
Requirements, Conceptual Design
ITEST
OS FAT
Forward Markets GO/NO GO
Single Entry Model GO LIVE
Q3 2007
Operations UI

## Slide 20: Phased implementation requires adjustments to Early Delivery System strategy
EDS 1/2 – Single Entry Model
Basic Network Model & SE Criteria NMMS (UI internal only) ICCP (RTU migration) Nodal EMS (non-live)
EDS 3 – Real Time Operations
NMMS (Operations UI) Nodal EMS (live) Outage Scheduler SCED RUC SASM COP Emergency Operations Trades, Schedules Offers (3 part) CRR (settled in RT) Financial Transfer CMM (part) EDW & MIS (part) Integration (part) LMPs published 8*5 support
EDS – Forward Markets
NMMS (Planning UI) DAM CRR (full) CMM (full) MIS (full) EDW & MIS (full – x4) 8*5 support (24*7 for MP SAT) ERCOT & Market Readiness Criteria approved
EDS 4 Trial outcomes
All MP Registration complete for Go Live OTS complete All market facing interfaces complete Testing of all markets complete 168 Hour test complete All interfaces validated Training complete MP financial & operational qualification complete Market Readiness Declarations met
Forward Markets – GO/NO GO
EDS 3 Trial outcomes
6 month SCED test completed EMS enhancements complete MP offers LFC, OS, RPP complete All MP Registration complete for Go Live OTS complete All market facing interfaces complete Testing of all markets complete 168 Hour test complete All interfaces validated Training complete MP financial & operational qualification complete Market Readiness Declarations met “Home Team” transitioned
Real Time Operations – GO/NO GO Zonal Shutdown – GO/NO GO
Q2 2008
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2007
Q1 2008
Q1 2009
Q3 2007
EDS 3
EDS 4
EDS 4 MP SAT
EDS 3 Data Validation
EDS 1/2
EDS 1/2 Trial outcomes
SE Criteria achieved Telemetry criteria achieved
Single Entry Model (with stable and capable SE) GO LIVE

## Slide 21: Texas Nodal Market Implementation Program Effort Analysis Storyboards September 5, 2006

## Slide 22: Market Engagement and Readiness (MER) Project Effort Analysis

## Slide 23: MER: Package Summary
Description: Market Participant approval of Nodal designs, preparation for and participation in testing and trials, training and readiness live nodal operations.
Vendor(s): N/A
Project Manager: Trip Doggett
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Training design (to accommodate several learning styles) development & delivery, and web-based training Communications TML replacement with new MIS web portal Market Participant Readiness Criteria, status reporting & Declarations Customer Care
Key Assumptions: TPTF is the primary Market Participant representative body for Nodal Engagement with Market Participants will comply with the requirements of the ERCOT Nodal Transition Plan
Challenges/Risks: Market Participant mobilization and active engagement in support of overall nodal project Number and heterogeneity of Market Participants Competing demands – including training development – for SME resource bottlenecks
Comments: Market Participant Accountable Executive concept being implemented TPTF workgroups being established (for MIS portal and Training consultation) where needed

## Slide 24: MER (excluding MIS): Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
Not included
4,098,600
11/04 CBA (KEMA)
Dimensions
10 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA assumptions:
  Training included planning, curriculum design & development.
  Training resource estimated at 6 FTE for 6 Months (split evenly between EMS, MMS and Commercial Operations topics. Excluded basic ERCOT training as ERCOT already performs these
  Change Management includes MP interactions requiring NPPR approval (TPTF activities)
Cost drivers for training:
  Scope: volume/diversity of audience; breadth of training types
  Very large curriculum (38 courses)
  Approval process
+163%
Total
3,184,460
7,430,407
81,025
84,025
See overall summary
10,780,818
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Includes training and LMS
  Excludes approval process
9/06 Program Estimate
TBD%

## Slide 25: MER (MIS): Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
Not included
891,000
11/04 CBA (KEMA)
Dimensions
10 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA assumptions:
  ERCOT.com and MIS changes low assuming DAM and (Zonal) Portal Replacement Project would absorb some of these costs
Cost drivers:
  Scope: over 130 Protocol refs
  Vendor unknown; cost est.
  Need to replace TML to ensure quality user experience
  Large number of integration points/dependencies
-39%
Total
90,675
211,575
-
241,800
See overall summary
544,050
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Assumed MIS enhancement, not re-design
  Assumed using current ERCOT portal licenses and technology
  Assumed no re-write of existing Portal, only enhancements due to Nodal protocols
9/06 Program Estimate
TBD%

## Slide 26: MER: Schedule and Resource Effort

## Slide 27: MER: Budget Assumptions (1)
Key Assumptions for MIS: Budget begins July 06 Testing and release management staff resource costs not included No vendor expenses (travel, hardware/software, lease) included No payment/expenses for Market Participant involvement (including Market Participant site integration expense) included Vendor will provide system-level training, documentation, operation manuals in costs listed under VENDOR No integration at Market Participant site expense is covered Current WAN or other network structure will support the new MIS portal Scope of expense does not extend past MIS web portal (does not include changes to ERCOT.com or other sites) No changes or additions to Protocols that affect MIS portal functionality will be accommodated past Feb 1, 2006 (prototype 1 delivery) No new reporting or re-work of existing reporting is included in MIS portal scope or budget Transition from MIS portal project to ERCOT maintenance staff will occur thru staff participation on project during 2008/2009 Key Assumptions for Training: No inclusion of WebEx sessions costs. ERCOT departments are allowed to use WebEx sessions without specifying the actual charge in budgets Use current LMS with no purchased extension Level of effort is based on training courses identified by the Market Participants in the "Curriculum" document Market Participant support & travel is not included Internal ERCOT required training or training for supporting system deployment is not yet identified or included LMS contract is good for two years - can not guarantee same price in 3rd year Scaling is done on a factor of five for development time only; the economies of scale will be in the other course processes The Nodal project team is not responsible for the operator seminar until 2009, however the team will provide whatever support is needed for the current seminars

## Slide 28: MER: Budget Assumptions (2)
Key Assumptions for TPTF: Only Leader, Meeting Manager and Secretary will charge to the TPTF Project. Anyone else attending TPTF meetings will charge to other projects. Any support from ERCOT Market Rules, other than the secretary, will be budgeted by ERCOT, not MER. 5 meeting days per month; at the MET center (no travel or outside facility costs). Updates to TAC once per month; no updates to other groups. Key Assumptions for Communications: 4 big “events” per year. Current publications and web work, including postings, will continue at current pace. Key Assumptions for MP Readiness Criteria: ERCOT will hire a firm to serve as Market Readiness Advisor (MRA) who will provide services similar to the MRA at MISO, including creating proposed readiness criteria, gain TPTF’s approval of the criteria, build a data collection tool and prepare a dashboard to share progress. 4 auditors will make 45 site visits each, with a travel budget, to Market Participants to gather data from Market Participants on their progress toward meeting the criteria, and will report that progress to the MRA. All data to measure Market Participant personnel readiness will be based on training test results. Key Assumptions for Customer Care: Provide critical support to Market Participants. Includes an Online Help Center (web-based) and “extension 3900” support. Includes sending required market notices. A ratio of 1 Account Manager per 10-14 QSEs. Maintenance of FAQ to cross-train other reps and as a resource for the Online Help Center. Does not include travel expenses.

## Slide 29: MER: Overview of current threats to success
 | TPTF, MP Readiness Criteria, Communications and Customer Care | MIS | Training
Scope/Plans |  | In development, high-level only now, but making progress | Need to determine internal/project requirements
Resourcing | New internal resources must be hired |  | Future resources are dependent on course delivery dates
Costs |  | Costs for vendor are unknown, but staff costs are firm | Resource driven
Timescales |  | Dependent upon securing vendor and finalizing plan | 
Critical dependencies |  | Need vendor finalized, otherwise dependent on integrations, IDA | Need ERCOT course information
Business Modeling & Requirements | N/A | Underway but behind | 
Analysis & Design | N/A | In process | N/A
Vendors | N/A | RFP complete and vendor evaluation underway | N/A
External Stakeholders |  |  | Continue to work to establish a repeatable process for approval from TPTF sub-group
Internal Stakeholders | N/A |  | 
Communications | N/A | N/A | 
Overall |  | Plan in place, staff in place, vendor almost selected | Need better definition of scope, that will drive everything else
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 30: Integrated ERCOT Readiness and Transition (IRT) Project Effort Analysis

## Slide 31: IRT: Project Summary
Project area: Integrated ERCOT Readiness and Transition Project
Description: Preparation of the ERCOT organization and final verification of all parties’ readiness to operate under the Nodal Protocols in live operations.
Vendor(s): N/A
Project Manager: Steve Grendel
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Early Delivery System (EDS) strategy and plans ERCOT Readiness Criteria ERCOT Readiness & Transition Plans (by function) ERCOT readiness preparations EDS Market Trials ERCOT Readiness Declarations
Key Assumptions: Management of the EDS trials will be the responsibility of the IRT Project Team Planning and preparations for each ERCOT function will be the responsibility of the respective ERCOT Director
Challenges/Risks: Balance of staffing (including contractors and employees) between Zonal, Nodal program and Nodal transition activities
Comments: Contract discussion occurring with 3rd Party readiness advisor RFP process in progress for Transition experts

## Slide 32: IRT: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
Not included
9,801,000
11/04 CBA (KEMA)
Dimensions
6-10 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA assumptions:
  Includes documentation and 6 months of Trials
  Assumed 2 major trial activities (not the complexity envisaged in the EDS sequence)
  Excluded SAS70 audits
Cost drivers:
  Market Trial Duration
    ERCOT Readiness
    MP Readiness
    Complexity of Systems
  Ability to leverage ERCOT FTEs for Trial Operations
  Readiness Activities (393 significantly impacted FTEs)
    Average of 67 class-room training hours
    Average of 6 months of hands-on Nodal simulation (via EDSs)
  Multiple overlapping application environments to operate
  Market Participant Registration, Financial & Operational Qualification
  Operating Guides, and internal procedures documents to update / maintain
+36%
Total
3,463,032
8,080,407
891,275
902,975
See overall summary
13,337,689
Dimensions
26 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Assumed 6 months of market trials
  Assumed significant effort by internal FTEs
  Assumed 6 months of pilot
9/06 Program Estimate
TBD%

## Slide 33: IRT: Schedule and Resource Effort

## Slide 34: IRT: Budget Assumptions
Assumptions: Key project resources will transition from FAT to SAT to EDS trial operations. Impacts on Corporate divisions are not included in the IRT EAC. Resources are available for the IRT Project as listed in the EAC. EDS 3, 4 & 5 will be treated as separate releases with different PM’s. EDS 3 is required to run 6 full months, EDS 4 & 5 will last 6 months each. The full testing period will be required to achieve the exit criteria for each EDS. After completing EDS 3, LMPs will be calculated and posted only when necessary to support subsequent EDS Trial needs EDS 5 resources will transition to TXMACS 1.0 Live Operations. The test harnesses/simulators used during SAT will be sufficient to support EDS trials. Applications entering EDS trials will not have level 1, 2 or 3 defects. Each EDS is the incremental build of the ultimate TXMACS 1.0 environment and will include all redundancies and DR capabilities required for production. A 3rd party (Readiness Advisor) will be used to provide readiness assessments and dashboards. The MER project will gather Market Participant readiness status and provide this information to the IRT’s Readiness Advisor Trial and production hardware is included in the Infrastructure Project EAC. All software licenses are included in other Nodal projects’ EACs through September 1st, 2009. Vendor software maintenance, warranty and technical support is covered by other projects’ EACs through September 1st, 2009. Software maintenance, warranty and technical support contracts are a derivative of business SLA’s and negotiated by business and IT. This scope is not within the IRT charter. Infrastructure will be ready as outlined by the IRT build schedule (next slide). All extracts/market information will be available during the appropriate EDS Trails phase. The functionality included in the Q2 2009 CS,MIS and EDW release will not require any market trial exposure and will be released into production with only a production verification performed. EDS 1 and 2 execution will occur in the NMMS and/or EMS project. Each EDS will be built in a separate environment to allow subsequent EDS preparations to occur in a parallel fashion. ERCOT Staff Training Assumptions. Class Room Training – avg. per employee 45 (using 582 employees) Hands on – FAT, SAT, UAT, EDS Execution – 4 months (using 582 employees) IRT does not own the Nodal Program staffing strategies or execution. IRT does own ERCOT Nodal Organization Design.

## Slide 35: IRT: Build Schedule
UAT/EDS Build Schedule
UAT leading into EDS 3 (3 month build cycle)
  Server build process, 7/1/ 2007 - 8/1/2007
  Application build process, 8/1/ 2007 - 10/1/2007
  UAT begins 10/1/2007
  EDS 3 begins 11/1/2007
  EDS 3 ends 6/1/2008
UAT leading into EDS 4 (3 month build cycle)
  Server build process, will not leverage EDS 3 infrastructure, 2/1/ 2008 - 3/1/2008
  Application build process, 3/1/2008 - 5/1/2008.
  UAT begins 6/1/2008
  EDS 4 begins 7/1/2008
  EDS 4 ends 12/31/2008
  EMS, MMS, CRR & Outage Scheduler remain in service ready for production as "TXMACS 1.0"
UAT leading into EDS 5 (3 month build cycle)
  Server build process will not leverage EDS 4 infrastructure, 8/1/2008-9/1/2008
  Application build process, 9/1/2008 - 11/1-2008
  UAT begins 11/1/2008
  EDS 5 begins 1/1/2009
  EDS 5 ends 6/31/2009
  EMS, MMS, Outage Scheduler & CRR remain in service ready for production as "TXMACS 1.0"
UAT March 1,2009 leading into TXMACS 1.0 (Go Live Systems) (2 month build cycle)
  Server build process will not leverage EDS 5 infrastructure, 1/1/2009 - 2/1/2009
  Application build process, 2/1/2009 - 3/1/2009
  UAT begins 3/1/2009
  Cut TXMACS 1.0
MOTE Build Schedule
MOTE 3 Readiness (3 month build cycle)
  Server build process, 5/1/2007 - 6/1/2007
  Application build process, 6/1/2007 - 8/1/2007
  MOTE begins 8/1/2007
MOTE 4 Readiness (3 month build cycle)
  Server build process, 2/1/2008 - 3/1/2008
  Application build process, 3/1/2008 - 5/1/2008
  MOTE begins 5/1/2008
MOTE 5 Readiness (3 month build cycle)
  Server build process, 8/1/2007 - 9/1/2007
  Application build process, 9/1/2007 - 11/1/2007
  MOTE begins 11/1/2008
Early Go Live Production Systems
MP Nodal Registration
  Server build process, 7/1/2007 - 8/1/2007
  Application build process, 8/1/2007 - 10/1/2007
  Registration begins 10/1/2007
  Registration ends 6/31/2008
MP Financial & Operational Qualification
  Server build process, 4/1/2008 - 5/1/2008
  Application build process, 5/1/2008 - 7/1/2007
  F & O Qualification begins 7/1/2008
  F & O Qualification ends 5/31/2009

## Slide 36: IRT: Milestones Schedule

## Slide 37: IRT: Overview of Current Threats to Success
 | Current Status
Scope/Plans | Plans Under Developed
Resourcing | Contention for ERCOT SME’s
Costs | 
Timescales | 
Critical dependencies | Key Resource Availability, Application Delivery
Business Modeling & Requirements | 
Analysis & Design | 
Vendors | N/A
External Stakeholders | Market Participant Readiness for EDS phases
Internal Stakeholders | 
Communications | 
Overall | Key Resource Availability, Application Delivery
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 38: Integration and Design Authority (IDA) Project Effort Analysis

## Slide 39: IDA: Project Summary
Description: Business and technical architecture, design standards and design assurance for the Program
Vendor(s): IBM
Project Manager: Jeyant Tamby
Key deliverables/short term deliverables: Guidance on contracts and Vendor selection Overall business and technical architecture Strategies & Roadmaps – Integration, EDW, MIS, hardware, security, database hosting, UI design, XML standards RUP artifacts and training Technical architecture assistance Quality assurance Requirements traceability (e.g. RequisitePro) User interface standards
Key Assumptions: Current top-level business architecture is solid All systems will conform to the integrated Data Dictionary based on CIM standards Program will follow concepts of Rational Unified Process Methodology of iterative development All critical documentation will go through QA process
Challenges/Risks: Integration – across multiple projects, vendors and applications Quality and rework due to complexity and changes Testing Strategy for complex overall Nodal “system”
Comments:
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD

## Slide 40: IDA: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
-
1,425,600
11/04 CBA (KEMA)
Dimensions
3 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA Assumptions:
  The numbers above only include Requirements Definition activities.
  It assumed that independent quality assurance will be provided by development groups and production support groups under different managers and teams (2004 ERCOT organization).
  These development groups work with vendors up till FAT; SAT, UAT and Regression stages are performed by Production Support and Business Teams.
  Design fidelity and assurance was the responsibility of Release Management, Production Support and Business Owners.
  This organizational structure was abandoned in 2005.
Cost drivers:
  Consultants for additional capability in Business Architecture, Enterprise Architecture and Project Management
  IBM RUP training & adoption
  KEMA Study
  Software licenses (ReqPro, Business Process Modeler)
+77%
Total
595,061
1,388,476
243,075
301,575
See overall summary
2,528,187
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Includes enhancement of technical delivery capability: RUP artefacts and training, solution architects, and delivery environment and tools (e.g. ReqPro)
  Excluded RUP/SDLC development
  Excluded RUP training
  Excluded Rational Tool suite
  Excluded external solution Architects
  Excluded Rational Support
9/06 Program Estimate
TBD%

## Slide 41: IDA: Schedule and Resource Effort
2006
2008
2007
2009
Budget under IRT
Vendor Sourcing
Strategic
Vendor
Sourcing
Assurance
Requirements
Traceability
Enterprise
Architecture
Project Management
Architecture, Strategy, Standards & Approach, EA Organization Forum
RUP Training and Adoption
RUP
Quality Assurance & Certification, Design Issue Resolution
Project Start-up, Monitoring & Tracking
  Requirements Management, Configuration & Analysis

## Slide 42: IDA: Budget Assumptions
Assumptions: 13 IDA FTEs move to Home Team in December 2007 Technical Architects will be centrally coordinated but funded 100% by relevant projects starting on September 1, 2006. They will ramp down with their respective projects. Their contingency will also be managed by their respective projects.

## Slide 43: IDA: Overview of current threats to success
 | Current Status
Scope/Plans | On target
Resourcing | Non-nodal demands on internal IDA resources; Lack of external energy industry SMEs
Costs | On target
Timescales | Potential slippage due to dependencies on projects
Strategic Vendor Sourcing | On target
Enterprise Architecture | Delayed due to late start of resources
RUP Adoption | Late artifact definition
Requirements Traceability | On target
Assurance | On target
Overall | Yellow due to resources and timescales
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 44: Network Model Management System (NMMS) Project Effort Analysis

## Slide 45: NMMS: Project Summary
Description: Capability to generate Planning and Network Models for Real-Time, Day-Ahead and Future applications and studies
Vendor(s): Siemens Power T&D, Inc. (NMMS); Nexant, Inc. (Network Modeling & Telemetry)
Project Manager: Raj Chudgar
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Naming Conventions State Estimator Criteria Network Modeling & Telemetry (proof of required fidelity) Requirements for TPTF approval Conceptual System Design for TPTF approval Time based Network Operations and Planning Model Management System
Key Assumptions: Factory Acceptance Testing – Pre-FAT on vendor premises; FAT on ERCOT premises Zero severity 1 or 2 bugs coming out of FAT or SAT
Challenges/Risks: Integration - multiple interface, one-liner and data dependencies (MMS, EMS, CRR, outage scheduler, registration) There are no vendors with prior experience with development of time-based models
Comments: ERCOT will be the first ISO to utilize time-based model functionality for down-stream applications

## Slide 46: NMMS: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
-
3,564,000
11/04 CBA (KEMA)
Dimensions
12 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA Assumptions:
  Use of automated Regression Testing tools limited to Commercial Systems
  Release Management Department already owned those tools
  EMMS regression testing limited to the utilization of project developed Test Scripts
Cost drivers:
  Project Mgt, SME Consultants to supplement internal capability, support requirements & architecture are from many consulting firms
  Siemens licenses and Maintenance: $4.3MM
-80%
Total
218,048
508,778
See overall summary
726,825
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Excluded 80-90% of NMMS is funded by Zonal (~$7MM)
  Excluded majority of model fidelity cost, assumed as part of ERCOT O&M budget
  Excluded naming convention cost
  Narrower scope of model fidelity work (cf Nexant)
9/06 Program Estimate
TBD%

## Slide 47: NMMS: Schedule and Resource Effort
Current high-level schedule
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
Original master schedule
SE/Telemetry Corrections
Development and FAT
“UI in production”
FAT
SAT
Naming Convention DB
NMMS Build
Common model update process
NMMS Conceptual Design
Naming Convention information collection
Model Data Certification
Model Data Remediation Reconciliation
Integration Design 3/31
Project Ramp-down

## Slide 48: NMMS: Budget Assumptions
Assumptions: Zonal work will gradually taper off in 2007 and 2008 and the remainder of Network Model operations staff will move to ERCOT Readiness project No Major change controls that affect Network Modeling project overall budget or schedule will be accepted All performance and integration issues can be solved with KNOWN technology All data outputs to other systems will be point to point All data from upstream systems will be provided under Network Modeling format specifications No significant diversion of current Network Modeling Staff to alternative Nodal or Zonal work TSPs can provide updates or changes to model within a quick turnaround or provide a detailed plan for model data issues

## Slide 49: NMMS: Overview of current threats to success
 | Current Status
Scope/Plans | Extent of Model updates being defined
Resourcing | Core team complete; known threat to staff instability
Costs | 
Timescales | Model correction timelines at risk
Critical dependencies | TSP involvement; Vendor timeline; Integration
Business Modeling & Requirements | 
Analysis & Design | 
Vendors | 
External Stakeholders | Road show to educate solution
Internal Stakeholders | 
Communications | Network Modeling Forum
Overall | Resourcing, timeline, and critical dependencies
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 50: Energy Management System (EMS) Project Effort Analysis

## Slide 51: EMS: Project Summary
Description: Implement the necessary changes to ERCOT’s current Energy Management System (EMS), Outage Scheduler (OS), and implement the new Renewal Production Potential (RPP) function to satisfy the requirements set forth in the Texas Nodal Protocols approved by Order signed by the PUCT on April 5th, 2006. At the same time, upgrade the ERCOT EMS and the Operator Training Simulator (OTS) from the existing vendor platform to the newest version.
Vendor(s): Requirements KEMA, AREVA T&D, Inc. (EMS, LF); ABB (OS), AWS True Wind (RPP)
Project Manager: Carlos Gonzalez-Perez
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Requirements for TPTF approval Conceptual System Design for TPTF review EMS platform upgrade & ERCOT customizations Network Security upgrade and Load Frequency Control Migration of enhanced Zonal Load Forecast to Nodal Replacement OS & new RPP Operator Training Simulator (OTS)
Key Assumptions: Factory Acceptance Testing – Pre-FAT on vendor premises; FAT on ERCOT premises Zero severity 1 or 2 bugs coming out of FAT or SAT
Challenges/Risks: Resource bottlenecks are delaying completion of business requirements for this critical path project Integration - multiple interfaces and data dependencies between the EMS and other systems (MMS, NMMS, Settlements, OS, etc.) Vendor Capability to deliver new software and application according to the Nodal Program timeline
Comments: Short-term efforts to alleviate EMS requirements resource shortfall impacts other projects. Mid-term solution involves sourcing from all industry EMS vendors and contracting firms Existing EMS vendor retained (AREVA); OS vendor selection governed by selection of MMS (ABB)

## Slide 52: EMS: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
Not included
7,789,500
11/04 CBA (KEMA)
Dimensions
9 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA assumptions:
  Assumed single vendor for EMMS (EMS, MMS & CRR)
  Included modifications to Operator Actions, Real Time Sequence and Dispatch (LFC and SCED), NSA Study Network Apps, procurement of LMP calculator and AS Monitoring
  Excluded Load Forecast, Outage Scheduling and Operator Training Simulator
Cost drivers:
  ERCOT EMS upgrade included in the Nodal implementation.
  New Outage Scheduler
  New development in the EMS systems, specially LFC, to fulfil the Nodal requirements
  Renewable Production Potential system will be also part of the nodal implementation
  Major EMS/NMMS interface will be implemented along with the Texas Nodal Market
  Different vendor in the MMS system increased complexity of EMS/MMS interfaces
-32%
Total
623,651
1,455,185
1,618,650
1,618,650
See overall summary
5,316,135
Dimensions
18 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Assumed 50% Network Security upgrade funded by Zonal
  Assumed EMS upgrade was Zonal
  Assumed OTS scope narrower (expanded as a result of ABB MMS selection)
9/06 Program Estimate
TBD%

## Slide 53: EMS: Schedule and Resource Effort
EMS (Energy Management System)
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Outage Scheduler
Q2 2009
EMS1-2
EMS1/2 FAT/SAT
EMS Requirements, Conceptual Design
OS SAT
OS Build
OS FAT
OS Requirements, Conceptual Design
Begin Ramp-down
Business Requirements complete 10/30
OS Complete 7/1
Business Requirements complete 10/30
EDS
EDS 3
EDS 4
EDS 1-2
EMS 3
EMS 3
SAT/FAT
EMS 4
EMS 4 FAT/SAT
OTS DEV
OTS FAT/SAT
Operator Training Simulator (OTS)
RPP DEV AWS
RPP FAT/SAT
Renewable Potential Production (RPP)
RPP DEV ERCOT

## Slide 54: EMS: Budget Assumptions
Assumptions: Maintain Zonal relevant EMS functionality in the Nodal EMS system OTS initialization phase will start after definition of EMS and MMS OTS component of the MMS is out of scope Assuming no delays due to Network Model or State Estimator Validation NMMS/EMS interface will be defined and operational on time to generate EMS models and databases. If not, assuming manual modeling using current AREVA’s GENESYS System Load Forecast requirements will be gathered for the Nodal implementation. However, at this time no development is expected, migrating from current Zonal system into the Nodal systems. Outage Scheduler will be rewritten for the Texas Nodal Market Implementation Assume a code freeze of the current production system by the end of 2006 – before AREVA coding EMS Upgrade will have a phased approach, starting with AREVA EMP 2.3 / Habitat 5.6 platform ERCOT current specials in the Zonal system will be merged in the AREVA platform. Development of new Nodal functionality will occur on application basis, to meet EDS development Resources in the EMS package will transition into subsequent packages Two (2) Site Acceptance Testing cycles before EDS 3 and EDS 4 RPP contracted as a subscription forecasting service. Monthly RPP subscription fee in EAC until Q3-2008 No SW license maintenance is included in the EMS EAC Vendor SAT maintenance is not included in the EMS EAC

## Slide 55: EMS: Overview of current threats to success
 | Current Status
Scope/Plans | Approval process caused delays; Lack of SMEs for delivery review
Resourcing | Long term resources identified but need to be filled
Costs | Outage Scheduler increases overall costs
Timescales | Behind schedule in the requirements definition
Critical dependencies | Business SME resource staffing constraints
Business Modeling & Requirements | Requirements/Use Cases in progress. Lack of definition of interfaces
Analysis & Design | Delay in requirement definition is holding the conceptual design and development of the EMS
Vendors | ABB (green), AWS True Wind (Green), AREVA with potential resource constraints to meet the timeline.
External Stakeholders | 
Internal Stakeholders | Key resources performing production support task in the Zonal System
Communications | Improve EMS ability to communicate with TPTF and Market Participants
Overall | Resources/Timeline
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 56: Market Management System (MMS) Project Effort Analysis

## Slide 57: MMS: Project Summary
Description: Business processes and systems for the Nodal Real-Time and Day-Ahead Energy and AS Markets
Vendor(s): ABB, Inc.
Project Manager: Al Hirsch
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Requirements for TPTF approval Conceptual System Design for TPTF approval Day Ahead Market capability Supplemental AS Market capability Reliability Unit Commitment capability Security Constrained Economic Dispatch (Real Time Market) capability DC Tie Data for Wholesale Market Monitoring
Key Assumptions: Factory Acceptance Testing – Pre-FAT on vendor premises; FAT on ERCOT premises Zero severity 1 or 2 bugs coming out of FAT or SAT
Challenges/Risks: Inadequate or Flawed Nodal System Design – Critical impact to performance, robustness, dependability, reliability Integration, Architecture & System Construction - multiple interface and data dependencies causing major impacts to schedule, cost, operation Substantial rework over the extended life of the project impacting schedule, cost & performance due to directed changes
Comments: ABB is fully committed and has stepped up as a member of the joint project team

## Slide 58: MMS: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
-
5,078,700
11/04 CBA (KEMA)
Dimensions
15 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA Assumptions:
  Auction-based DAM will be implemented prior to Nodal; related ADAM costs considered sunk.
Cost drivers:
  Prime cost driver is splitting SCED from balance of MMS and delivering first
  Prime cost driver is developing requirements from inadequate protocol documents
  Prime cost driver is lack of system design/specification prior to start of MMS design
  Secondary cost driver is excessive amount of “market trials” following development
  Secondary cost driver is lack of team environment and SMEs from existing ERCOT staff
+169%
Total
1,857,240
4,333,560
3,729,000
3,729,000
See overall summary
13,648,801
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  One (1) build cycle
  Excluded multiple market trials
  Included significant ERCOT staff available for development
9/06 Program Estimate
TBD%

## Slide 59: MMS: Schedule and Resource Effort
Current high-level schedule
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
MMS Design, Build, Pre-FAT
MMS FAT
MMS SAT
SCED Requirements, Conceptual Design
Original master schedule
Begin Ramp-down
Business Requirements complete 10/30
Base Software 4/13
SCED/MMS Requirements
MMS FAT
MMS Build
SCED FAT complete 7/1
MMS Requirements, Conceptual Design
SCED Build
SCED FAT
SCED SAT
MMS SAT
SCED Build
SCED FAT
SCED SAT

## Slide 60: MMS: Milestone Schedule

## Slide 61: MMS: Budget Assumptions
Assumptions: MMS installed as Black Box with COTS Standard Transfer Function (No Customs) FAT on site at ERCOT (No FAT at vendor site) Minimal level of MMS Project Technical Staff support for SAT and EDS (8/15 - Changed to add required Bus/Proj Staff) Limited support funding for Market Trials (8/15 - Some funding added for Analysts) Budget includes technology/operational knowledge transfer to ERCOT staff sufficient to operate and support All custom work is limited to User Interface Screen Layout All standard product security and access authorizations included Total releases limited to original plus two (2) Input data will be direct from Market Participant/Operator Interface and other sub-systems (Portals) without edit/manipulation Key Resource staffing will be provided timely with Texas Nodal orientation provided prior to joining MMS project (No budget in MMS) All ERCOT approvals will be provided timely and expeditiously within time period budgeted in schedule TPTF Approval Cycle will not exceed three (3) weeks

## Slide 62: MMS: Overview of current threats to success
 | Current Status
Scope/Plans | 
Resourcing | Core team; contention for ERCOT SME’s
Costs | 
Timescales | RT/RUC/SCED
Critical dependencies | Internal Key Resource Availability
Business Modeling & Requirements | 
Analysis & Design | 
Vendors | 
External Stakeholders | 
Internal Stakeholders | Lack of Bilateral Collaboration
Communications | See Internal Stakeholders
Overall | Internal Collaboration & Impact Mitigation
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 63: Congestion Revenue Rights (CRR) Project Effort Analysis

## Slide 64: CRR: Project Summary
Project area: Congestion Revenue Rights
Description: Business processes and systems to allow the CRR Owner to be charged or receive compensation for congestion rents that arise when the ERCOT Transmission Grid is congested in the Day-Ahead Market (DAM) or in Real-Time
Vendor(s): Nexant, Inc.
Project Manager: Shawna R. Jirasek
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Short term deliverables: Requirements for TPTF approval, Conceptual System Design for TPTF approval Key deliverables: PCRR and MCFRI allocation capability CRR auction capability CRR ownership tracking capability and Bilateral trading capability
Key Assumptions: Factory Acceptance Testing – Pre-FAT on vendor premises; FAT on ERCOT premises Zero severity 1 or 2 bugs coming out of FAT or SAT
Challenges/Risks: New CRR process to ERCOT, new technology to ERCOT, and implementation different than that in other ISOs Integration - multiple interface and data dependencies (NMMS, MMS, Registration, Settlement, Credit Monitoring) Early CRR delivery – may result in rework to fit into integrated Nodal program
Comments: Solution vendor accepting fast delivery timeline Market Participant specialist on board and integrated in the project team

## Slide 65: CRR: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
-
7,533,000
11/04 CBA (KEMA)
Dimensions
14 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA Assumptions:
  Tighter and more complex interactions with Planning and Operations Engineering models and staff.
  Assumed new products, new 3rd party software; considered new SW license costs.
Cost drivers:
  Untested nodal protocols; protocol design decisions increase costs
  Complicated solution requiring highly specialized SME and vendor knowledge
  Fixed price software development contract with perpetual license
  Early delivery of completed CRR product
  Entirely new CRR business processes and ongoing business team
  No CRR ‘Home-Team’ in the ERCOT business until 2008
-26%
Total
1,683,000
3,927,000
See overall summary
5,610,000
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Excluded CRR statements and bills (COMS)
  Excluded credit limit generation (COMS)
  Excluded Registration (COMS)
  Excluded CRR interface with MMS (MMS)
9/06 Program Estimate
TBD%

## Slide 66: CRR: Schedule and Resource Effort
Current high-level schedule
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
CRR Design, Build, Pre-FAT
CRR FAT
EDS 4 SAT
CRR Requirements, Conceptual Design
Original master schedule
Ramp-down complete
Business Requirements complete 10/30
Base software installed 12/15
CRR Requirements Design, Build, Pre-FAT
CRR FAT
CRR “Pre-SAT”
FAT complete 7/1

## Slide 67: CRR: Key Milestones

## Slide 68: CRR: Budget Assumptions
Assumptions: ERCOT will hire fulltime CRR Market Operators (~6) as additional Home Team staff to be carried in the project budget until 2008 ‘Stub data’ from CRR interfacing systems will be available in February 2007 CRR will finish development, documentation, and FAT by July 11, 2007. However, if multi-period annual auctions are eliminated, FAT could be completed by May 9 2007 Vendor cost for development of multi-period annual auctions is $390,000 (NPRRs in-flight) CRR will complete SAT with the other applications in EDS 4 but will also conduct a 3 month Pre-SAT During SAT there will be two FTEs assigned half-time to serve as SAT liaisons CRR team will test and validate the newly created business processes following Pre-SAT and prior to handing over to the business at the end of 2007 Vendor consulting time will be for practice allocation and auction (outside software customization costs) Some CRR team travel to vendor site will be necessary

## Slide 69: CRR: Overview of current threats to success
 | Current Status
Scope/Plans | September 2005 to August 2006 Protocols Impact being assessed
Resourcing | Core team; contention for ERCOT SME’s
Costs | 
Timescales | 
Critical dependencies | Internal Key Resource Availability; Vendor SOW
Business Modeling & Requirements | Feasibility of Protocols Undetermined
Analysis & Design | Unproven Capability/Solution
Vendors | 
External Stakeholders | 
Internal Stakeholders | 
Communications | 
Overall | Unproven Capability/Solution
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 70: Commercial Systems (COMS) Project Effort Analysis

## Slide 71: COMS: Project Summary
Project area: Commercial Systems
Description: Business processes and systems for Settlements and Billing, Data Aggregation, Metering, Load Profiling, Credit Monitoring, Registration, Disputes, Financial Transfer
Vendor(s): LODESTAR®, Siebel®, ROME®
Project Manager: Raj Chudgar
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Requirements for TPTF approval Settlement payments and charges for Day Ahead, RUC, Real Time, Ancillary Services, and CRRs Credit monitoring and management capabilities Invoicing capabilities Registration capabilities Disputes capabilities Financial Transfer capabilities
Key Assumptions: Zero severity 1 or 2 bugs coming out of FAT or SAT
Challenges/Risks: Integration - multiple interface and data dependencies Probability of substantial re-work due to scope changes/clarifications introduced in Real-Time and Day-Ahead requirements
Comments: Nodal necessitates a complete re-write of Settlement due to volume of data and new methods of calculation ERCOT is leading the Settlement development internally

## Slide 72: COMS: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
Not included
11,939,400
11/04 CBA (KEMA)
Dimensions
18 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA assumptions:
  Included Registration, MMS to COS interface, Data Aggregation, Credit and Risk Management, Settlements, Post LMP Mitigation and Dispute Resolution
Cost drivers:
  Sheer effort to re-write settlements ( 150,000 effort hours)
  Project Management, SME Consultants to supplement internal capability, support requirements & architecture are from many consulting firms
  ROME Licenses and Maintenance: $2.3MM
  Additional Lodestar Licenses: $300k
-5%
Total
3,405,614
7,946,434
-
-
See overall summary
11,352,048
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Excluded training for settlements (MER)
  Excluded any changes to zonal settlements
  Excluded extracts (EDW)
  Excluded CRR settlements (CRR)
9/06 Program Estimate
TBD%

## Slide 73: COMS: Schedule and Resource Effort
Current high-level schedule
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
Original master schedule
Staff Ramp-down
Business Requirements complete 10/30
Integration Design 3/31
CS Development and FAT
CS Requirements
CS SAT
Statements Layout
Script test
Credit Monitoring
Financial Transfer
Disputes
Commercial Systems Design, Build, Pre-FAT
CS FAT
CS SAT
Registration ready
CS FAT
CS SAT
CS Requirements, Conceptual Design
“Non-binding settlements”
CS FAT
CS SAT

## Slide 74: COMS: Budget Assumptions
Assumptions: ERCOT, with vendors, will complete all Business requirements by 10/31 ERCOT, with vendors, will create CSDs by end of 2006 All performance issues can be solved with existing application technology All data inputs from other systems will be as defined by Commercial Systems team ERCOT has sufficient staff for all Commercial System projects, and currently dedicated staff is not redirected to other projects ERCOT Commercial System Zonal projects will ramp down in 2007 and 2008 Vendor price quotes will not significantly change going forward Commercial Systems will have multiple releases to satisfy the TPTF Transition Plan Mini-Settlements and Billing development team (business and IT) will stay in project team until the end of project to support late changes and defects Go Live implementation strategy does not require additional manual or automated workarounds to settle the market

## Slide 75: COMS: Overview of current threats to success
 | Current Status
Scope/Plans | 
Resourcing | 
Costs | 
Timescales | Prototype slightly behind schedule
Critical dependencies | All upstream systems data
Business Modeling & Requirements | 
Analysis & Design | Settlement performance capability
Vendors | 
External Stakeholders | 
Internal Stakeholders | 
Communications | 
Overall | Upstream applications and performance
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 76: Enterprise Data Warehouse (EDW) Project Effort Analysis

## Slide 77: EDW: Project Summary
Description: Capability to collect historic data and provide information services to MPs, PUCT, WEMM and FERC, perform data analysis.
Vendor(s): N/A
Project Manager: Sylvia Shiroyama
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: EDW strategy and roadmap Requirements for TPTF approval Business Intelligence – dynamic reporting (CDW framework) Business Intelligence – standard reporting (including internal, MOMS, Market, Compliance, Credit reporting) Operational Data Stores (including Lodestar, EMMS ODS) Market data extracts Information replication (ODS, RSS replication)
Key Assumptions: EDW is a shared asset across ERCOT Zero severity 1 or 2 bugs coming out of FAT or SAT
Challenges/Risks: Impact of extensive schema changes will require all output types to change EDW governance
Comments: EDW Project Manager starts 9/5/06 ERCOT is leading the EDW development internally

## Slide 78: EDW: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
Not included
1,960,200
11/04 CBA (KEMA)
Dimensions
12 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA assumptions:
  Included Performance Monitoring changes and Nodal driven enhancements to general data extracts and reporting capabilities. A substantial EDW replacement project was under way at the time of the study therefore major EDW system changes were not included
Cost drivers:
  Number of new databases / systems
  Schema changes to existing systems
  External resource needs
  Increased information services for ERCOT, PUCT and Market
+59%
Total
937,275
2,186,974
-
-
See overall summary
3,124,249
Dimensions
23 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Assumed substantial leveraging of Zonal
  Assumed leveraged zonal technology
  Excluded Compliance (ERO) reports
  Excluded rebuilding zonal extracts/reports
9/06 Program Estimate
TBD%

## Slide 79
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Original Master
Schedule
Q2 2009
EDW FAT
EDW SAT
EDW Requirements, Conceptual Design
EDW FAT
EDW SAT
EDW FAT
EDW SAT
EDW Design, Build, Pre
-
FAT
EDW: Schedule and Resource Effort
EDW Schedule
NMMS, CM
EDW Requirements, Conceptual Design
S&B
FT
EDW SAT
MMS, CS, CRR
EMS, SCED, OS

## Slide 80: EDW: Budget Assumptions
Assumptions: ERCOT business & Nodal projects will determine the tables to be replicated into the ODS At least 6 EIS FTEs will be involved in the Nodal EDW development All replication objects will be delivered at the same time as the project Extracts and standard reports identified in source system design will be delivered within 3 months of project FAT Resources are fungible and can be easily trained; will require additional staff to execute the nodal EDW project The cost estimate is based on currently known requirements All EDW hardware and software estimates are included in the Infrastructure project 20-25% level of EDW Project Technical Staff support for SAT

## Slide 81: EDW: Overview of threats to success
 | Current Status
Scope/Plans | Charter not signed off
Resourcing | 5 dedicated resources, PM joining 9/5
Costs | Not identified yet
Timescales | High level timeline established
Critical dependencies | Not identified
Business Modeling & Requirements | Not started
Analysis & Design | Solution has been established
Vendors | Not known
External Stakeholders | Good relationship with PUCT, others are unknown
Internal Stakeholders | Governance model to be established
Communications | Communication plan to be established
Overall | Scope not established
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 82: Infrastructure (INF) Project Effort Analysis

## Slide 83: INF: Project Summary
Project area: Infrastructure
Description: Provision of development, testing, EDS and production environments across the Program
Vendor(s): IBM, EMC, Oracle
Project Manager: David Forfia
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Hardware specifications Hardware procurement IT Services Catalogue Service Level Agreements for all Nodal projects Project development & test (FAT) environments Integration testing (SAT) environments EDS environments Production environments
Key Assumptions: Infrastructure capacity can be incrementally added as the project progresses using IBM’s capacity upgrade on-demand model Data center capacity issues will be resolved in the next 90 days (resolved via current plan of record – 9/1)
Challenges/Risks: Existing Data Center capacity (power) (resolved via current plan of record – 9/1)
Comments: IT Operations will be the first ERCOT function to transition to Nodal operations, starting with setting up development environments

## Slide 84: INF: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
Not included
14,310,000
11/04 CBA (KEMA)
Dimensions
10 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA assumptions:
  Included facilities labor and activities (modifications to existing datacenters and work area and incremental hardware
  At the time ERCOT had just renovated their EMMS hardware and TCC 2 was under construction
Cost drivers:
  ERCOT staff operating new infrastructure in production by Q1 2007 – 9 months ahead of original plan
  Nodal Enterprise Infrastructure necessary for data center power recovery in zonal
  Key consulting through IBM Global Services Establish best practices for infrastructure configuration and operation prior to Q1 2007 Operate hardware environment while ERCOT operations staff completes training Define database operation and recovery techniques for high availability systems Acceleration of the data center consolidation with Migration Factory practice
+187%
Total
906,000
2,114,000
-
38,109,318
See overall summary
41,129,318
Dimensions
27 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Included all standard OS costs
  Included all Oracle licenses
  Included all hardware licensing and maintenance costs
  Included internal labor to build hardware
  Excluded Data Center
9/06 Program Estimate
TBD%

## Slide 85: INF: Schedule and Resource Effort

## Slide 86: INF: CPU Capacity
Current Production
(172 CPUS)
Total CPUs all environments (400 CPUs)
Notes: <number>
<footer>
<header>
<date/time>

## Slide 87: INF: Storage
Notes: <number>
<footer>
<header>
<date/time>

## Slide 88: INF: Budget Assumptions
Assumptions: Sufficient data center capacity can be reclaimed at both data centers to house the Nodal infrastructure. Sufficient effort exists in the deployment plan and contingency to meet the needs of both the Nodal and any Zonal equipment retirements necessary to reclaim the data center capacity. ERCOT IT staff will be capable of operating the new infrastructure and database infrastructure in a production environment in Q1 2007. Multiple logical release environments can be deployed on the same server without violating security policy. Only enhancements are necessary to the networking infrastructure to meet the Nodal requirements. Operations testing and load profiling can be completed at the IBM test lab. ERCOT Deployment of IBM’s P6 based architecture will occur in Q3 2007.

## Slide 89: INF: Overview of current threats to success
 | Current Status
Scope/Plans | 
Resourcing | SME balance between zonal operations and nodal installation
Costs | 
Timescales | Delivery Timeframe for environments significantly accelerated
Critical dependencies | Data center capacity recovery
Business Modeling & Requirements | Project level capacity plans not complete
Analysis & Design | 
Vendors | 
External Stakeholders | 
Internal Stakeholders | 
Communications | Resource level issue
Overall | Delivery of shared infrastructure no longer on program critical path
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 90: Integration and Product Testing (INT) Project Effort Analysis

## Slide 91: Program Review – INT
Project area: Integration Testing
Description: Site Acceptance Testing (SAT) of integrated applications from multiple projects and vendors
Vendor(s): N/A
Project Manager: Glen Wingerd
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Sustainable testing tools, procedures and methodologies Smoke, Performance, Integration, and Regression Test scripts SAT entrance criteria SAT exit criteria Test Results and sign-off
Key Assumptions: Zero severity 1 or 2 errors are accepted into Integration Testing
Challenges/Risks: Multiple dependencies on upstream projects and applications Demonstration of Nodal TXMACS overall system performance
Comments: ERCOT is leading the integration Testing internally This project will establish an ongoing testing capability for Nodal

## Slide 92: INT: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
Not included
3,564,000
11/04 CBA (KEMA)
Dimensions
6 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA assumptions:
  ERCOT integration Testing and User Acceptance Testing
  6 months and 17 FTEs
  Use of automated Regression Testing tools limited to Commercial Systems
  Release Management Department already owned those tools
  EMMS regression testing limited to the utilization of project developed Test Scripts
Cost drivers:
  Sequence and proportion of testing:
    Smoke (5%)
    Functional (35%)
    Integration (35%)
    Severity (7%)
    Regression (10%)
    Performance (8%)
  Number of integration points (~200)
  SO/SO internal/external
  IT support
+158%
Total
2,010,922
4,692,151
1,215,375
1,273,875
See overall summary
9,192,323
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Assumed 1 SAT phase
  Assumed composition included significant ERCOT FTE staff
9/06 Program Estimate
TBD%

## Slide 93: INT: Schedule and Resource Effort

## Slide 94: INT: Overview of current threats to success
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)
 | INT
Scope/Plans | 
Resources | 
Costs | 
Timescales | 
Critical dependencies | SAT Entry Criteria
Business Modeling & Requirements | N/A
Analysis & Design | Developing SAT Testing Guidelines
Vendors | 
External Stakeholders | N/A
Internal Stakeholders | N/A
Communications | 
Overall | 

## Slide 95: Enterprise Integration (EIP) Project Effort Analysis

## Slide 96: EIP: Project Summary
Description: Messaging capability to loosely couple ERCOT applications through web services, transforming interfaces into messages
Vendor(s): UISOL
Project Manager: TBD
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Integration strategy and roadmap Integration Vendor procurement Project mobilization ERCOT extended CIM (ECIM) Implemented ECIM on database and XSD Tested and operating interfaces Tested and operating Common services (Audit, Monitoring, Exception Handling, Authentication, Data Transfer)
Key Assumptions: Vendor will deliver interfaces compliant with ERCOT integration standards Scope of integration would not include over 100 interfaces
Challenges/Risks: Transformation layer requires ERCOT extended CIM (ECIM) Balance of point-to-point solutions (for bulk data) with web services (messaging) Integration design work is starting late
Comments: UISOL will be performing integration design and quality assurance. A separate vendor may be chosen for implementation.

## Slide 97: EIP: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
Not included
3,029,400
11/04 CBA (KEMA)
Dimensions
6 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
11/04 CBA assumptions:
  Assumed 6 months & 17FTE
  Assumed single vendor for EMMS (EMS, MMS & CRR) – hence majority of effort was needed on MMS to Lodestar, EMMS to EDW, EMMS to MP User Interface.
  All interfaces point to point using Oracle gateways
Cost drivers:
  Number of interfaces
  Number of critical applications where backup solution (P2P) is needed
  ECIM definitions
  Common integration infrastructure that can be leveraged
-81%
Total
169,985
396,633
-
-
See overall summary
566,618
Dimensions
15 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Integration assumed to be within projects thus SOA would leverage Zonal resources and cost when needed
  Included integration effort within base projects
9/06 Program Estimate
TBD%

## Slide 98: EIP: Schedule and Resource Effort
Current high-level schedule
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
Requirements
Design
Build – Iteration 1
Build – Iteration 2
Build – Iteration 3
Test

## Slide 99: EIP: Budget Assumptions
Assumptions: Nodal requires 100 interfaces to be developed UISOL will do the following tasks for Nodal Requirements Design Quality Assurance (including FAT) An Integration Implementation vendor will be hired for developing the integration solution ERCOT Integration team will be transitioned and trained on the new integration platform Enterprise Integration project will deliver components in line with the EDS strategy Travel expenses are assumed to be 15% of labor cost A contingency cost of 15% is added to the labor cost Assumes integration work will be completed by the end of Q3 2008

## Slide 100: EIP: Overview of current threats to success
 | Current Status
Scope/Plans | Charter not signed off
Resourcing | 
Costs | Nominal, P2P mitigation built in
Timescales | Not defined
Critical dependencies | Not identified as yet
Business Modeling & Requirements | 
Analysis & Design | 
Vendors | 
External Stakeholders | Establish meetings with vendors
Internal Stakeholders | Project communication to be started
Communications | See Internal Stakeholders
Overall | Late start
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 101: Program Management Office (PMO) Project Effort Analysis

## Slide 102: PMO/PC: Project summary
Description: Program leadership, organization, mobilization, strategic planning and delivery assurance.
Vendor(s): N/A
Project Manager: Michael Collins
Budget: $TBD
Actuals YTD: $TBD
Actuals Total: $TBD
Key deliverables/short term deliverables: Program organization & governance Program Charter Program Management Corporate Standard & Operating Procedures Integrated plans, controls and reporting Program risk management Executive stakeholder management
Key Assumptions: The resource model envisages a lean core team (including “super” Project Managers and assurance functions) – ‘contracting’ with internal and external providers for deliverables (rather than resources) The Program Charter establishes the Program scope, schedule and budget baseline – any changes will be subject to formal change control
Challenges/Risks: Balance of staffing (including contractors and employees) between Zonal, Nodal program and Nodal transition activities
Comments: External consultants (PA) have been retained to provide PMO/Program Management support External consultants (IBM) have been retained to provide independent review of Program Controls

## Slide 103: Nodal Program: Overall Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
19,690,395
45,944,255
8,102,501
46,601,819
5,313,468
125,652,437
Total
-
-
-
-
-
78,429,600
11/04 CBA (KEMA)
Dimensions
30 months
$100/hour
25%
Dimensions
18 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
9/06 Program Estimate
12/05 High-Level Estimate
12/05Assumptions:
  Funding from Zonal includes: 50% Network Security Upgrade, EMS upgrade, 80-90% of NMMS
  OTS scope narrower (expanded as a result of ABB MMS selection)
  Model fidelity scope narrower (cf Nexant)
  Integration within projects, thus SOA would leverage Zonal resources and cost when needed
  MIS enhancement, not re-design
  Excluded SAS 70 and a greater proportion of ERCOT Readiness and Transition is O&M
11/04 CBA Assumptions:
  Use of automated Regression Testing tools limited to Commercial Systems
  Included facilities labor and activities (modifications to existing data centers and work area and incremental hardware)
  Minor incremental hardware
  Single vendor for EMMS (EMS, MMR and CRR); only modifications to Operator Actions, LFC/SCED, NSA, LMP calc and AS Monitoring. Excluded Load forecasting, Outage Scheduling and OTS.
  Few ERCOT.com and MIS changes, DAM and (Zonal) Portal Replacement Project will absorb some of these costs
  Training resource estimated at 6 FTE for 6 months (EMS, MMS and CS)
  Auction-based DAM will be implemented prior to Nodal; related ADAM costs considered sunk.
+65%
TBD%

## Slide 104: PMO/PC: Cost Summary
 | Base estimate | Contingency | Total
Internal Resource Costs |  |  | 
External Resource Costs |  |  | 
Vendor Labor |  |  | 
Hardware, Software, misc. |  |  | 
Finance Charges |  |  | 
Total |  |  | 
Total
-
-
-
-
-
3,445,200
11/04 CBA (KEMA)
Dimensions
21 months
$137.5/hour
35%
 | Dimensions
Project duration | TBD
Composite fee rate | TBD
Contingency (vs base) | TBD
9/06 Program Estimate
11/04 CBA Assumptions:
  PMO of 10 FTEs spread over two phases
Cost drivers:
  Duration
  Consultants to supplement Program Management capability
  Program Control independent audit (IBM), SAS70, Security Audit
-28%
Total
545,433
1,272,677
324,100
339,700
See overall summary
2,481,910
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Significantly lower estimate of program management consulting support for PMO
  10 PMO 50% FTE, 50% contractors
  Excluded Program Control Independent Audits
TBD%

## Slide 105: PMO/PC: Schedule and Resource Effort
Current high
level schedule
Q2 2008
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Program Budgeting
Program Control Tools
EDS 3
Scheduling Tools
Regular & Ad Hoc Reporting
Program Delivery Assurance & Analysis
Program Change Control
PC Project Management
EDS 4
EDS 5

## Slide 106: PMO/PC: Budget Assumptions and High-Level Milestones
Q2 2008
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
EDS 3
EDS 4
EDS 5
Security Audit
IBM Independent Reviews
Program Risk Reviews
SAS 70 Reviews
  Number of changes by the TPTF will be minimal.
  Number of change requests will not exceed capacity of the Change Control Board.
  Annual rate of attrition will not exceed 10%.

## Slide 107: PMO/PC: Overview of current threats to success
 | Current Status
Scope/Plans | Program Control Tool creation is incomplete
Resourcing | Several vacancies remain
Costs | Number of resources and deliverables increasing
Timescales | 1/1/09 date is not feasible given delivery schedules
Critical dependencies | 
Business Modeling & Requirements | 
Analysis & Design | 
Vendors | 
External Stakeholders | Budget is not approved
Internal Stakeholders | Some confusion around transition to Home Team
Communications | Plan in place, making progress
Overall | Program pulling together manageable deployment timeline
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 108: Next Steps…