Background:

In its final order in Docket 31540, the PUC asked stakeholders for Timely Response on the feasibility of adding real-time co-optimization.

Final Order 5 April, 2006 Ordering Paragraph 3

ERCOT and the electric-market stakeholders shall determine whether co-optimization is feasible and beneficial to implement in the wholesale market as approved by this Order.  Any modifications to the protocols required to implement co-optimization shall be brought to the Commission for final approval.

TAC assigned this issue to WMS.  WMS formed a Task Force on Feasibility of Co-optimization in the Nodal Market.

- Two meetings: May 1, May 10

- Broad Participation in meetings

  - Municipal Utilities

  - Independent Generators

  - Retail Electric Providers

  - PUCT

  - ERCOT

  - Power Marketers

- Developed framework & whitepaper describing process

- Developed recommendation for WMS

The task force examined two forms of co-optimization which became known as Sequential Co-Optimization (hour ahead) and Real Time Co-Optimization.  The task force concluded that Real Time Co-Optimization should not be pursued for the initial implementation of the Texas Nodal Market as it would have too great an impact on the nodal implementation schedule, due in part to the number of decisions that would have to be made by stakeholders and that there would be a large number of interactions with the real time control systems that may potentially impact reliability of the system.  The task force concluded that Sequential Co-Optimization could be accomplished with less risk and schedule impact and a NPRR was drafted to provide definition.

The WMS endorsed the findings of the Co-Optimization Task Force but asked ERCOT to request information from vendors regarding the cost and schedule impact of either Sequential or Real Time Co-Optimization.

ERCOT interaction with WMS on this subject was as follows:

- May WMS

  - ERCOT was asked to question potential vendors about costs and schedule impacts for

    - Real-time Co-Optimization

    - Hour-ahead Co-Optimization

- June WMS

  - ERCOT response

    - No specific cost or schedule impacts available

    - Both Real-time and Hour-ahead are possible

    - Impacts to protocols and systems are expected

- July WMS

  - Vendor selected, estimates will follow

ERCOT asked MMS vendor to determine cost and schedule impacts of implementing each of the two co-optimization options, neither of which have defined requirements.

- Sequential Co-Optimization (Hour Ahead)

  - MMS System Cost & Schedule Impact

    - Minimum $950,000 + $250,000 risk**

    - Minimum 2 months MMS project delay

    - Potential 2 month impact on Texas Nodal, cost not quantified

  - Must also consider:

    - Settlement Impact Certain (cost not quantified, analysis in progress)

    - Operational Staffing Impact

    - Market Rules Changes – Proposed NPRR XXX

**Risk uncertainty due to new software development and the addition of a sequence

- RT Co-Optimization (Every SCED run)

  - MMS System Cost & Schedule Impact

    - Minimum $950,000

    - Minimum 2 months MMS project delay

    - Potential 2 month impact on Texas Nodal, cost not quantified

  - Must also consider:

    - Settlement Impact Certain (cost not quantified, must have additional information such as NPRR)

    - EMS Impact Certain (cost not quantified, must have additional information such as NPRR)

    - Operational mechanics between QSE and ERCOT

    - Overlap of AS Deployment and Re-Allocation

    - Market Rules Changes

At its August meeting, the WMS heard and discussed the findings of the ERCOT staff regarding the inclusion of either Real Time or Sequential Co-Optimization in the initial implementation of the nodal market.  In addition, the PUCT staff strongly encouraged the stakeholders not to proceed with the hour-ahead Sequential Co-Optimization proposal that may be in effect for only a few years and instead to consider an eventual implementation of the RT Co-Optimization in the future.  The potential benefit to consumers or the market associated with Co-Optimization was not discussed again and the decision of WMS is based primarily on the cost, schedule and risk impact on initial nodal implementation.

WMS notes that other ISOs in the United States have either implemented or are in the process of implementing real-time Co-Optimization for their markets.  Given that a number of markets see the benefits of implementing real-time Co-Optimization, and given the importance of scarcity pricing in meeting ERCOT’s resource adequacy needs in the long run as noted by a number of stakeholder comments in the Commission’s Resource Adequacy rulemaking, it is the intent of WMS that the subject of real-time co-optimization be reconsidered in the future.

Finaly, WMS viewed the cost and the delay of the nodal market as not being worth the benefit at this time and noted that the architecture planned would have the fundamental systems for performing the Co-Optimization should it be implemented at a later time.  So there are little savings to be achieved by developing the Co-Optimization engine now versus waiting until later.

This paper and the following resolution of WMS were drafted after the August WMS meeting based on discussions in the meeting and were passed by e-mail vote of the WMS.

Resolution of the WMS:

The WMS has found that while it would be feasible to implement either of the forms of Co-Optimization, the impact on the cost, schedule and risk associated with implementing the option outweighs the potential benefit of doing so in the initial implementation.  For this reason, the WMS recommends that the initial implementation of the Texas Nodal Market not include either Sequential or Real Time Co-Optimization.