## Slide 1: Texas SET Version 3.0 Project PR40038_01
Retail Market Subcommittee Meeting
September 13, 2006

## Slide 2: Accomplishments
POLR Rule – Project 31416
  TX SET recommended language in RMGRR 42 – Mass Transition Process Necessary for PUCT Rule for RMS approval to comply with the Rule and provide the Market with the long-term Mass Transition processes, procedures, roles and responsibilities.
  TX SET recommended language in PRR684 Mass Transition for RMS and PRS approval to comply with the Rule. Changes submitted affect section 15.1.2.9, which includes new subsection 15.1.2.9.1 Customer Billing Contact Information

## Slide 3: Accomplishments
POLR Rule – Project 31416
  Retail Market Guide Revision 042 - Section 7.11.6 Submission of Customer Billing Contact Information TX SET’s recommendation states that all information must be sent in CSV. file format via Secure FTP.
    Some Market Participants questioned if Secure FTP was the Market approved methodology or should some other form of communication be utilized. With the assistance of ERCOT, TX SET requested the expertise of TDTWG for their technical recommendation on this subject.
  TDTWG members held a conference call on Friday, 9/1/2006, at 1:30 PM to address the question of Secure FTP, if not, then what???
    TDTWG’s recommendation – Secure FTP

## Slide 4: Approved as Emergency Change Controls
  2006_700 – 650_01 Transaction
    Adds new segment ‘YNQ Yes/No Friday Overdue Authorization for Disconnects for Non-Payment’. This was a recommendation from the Terms and Conditions Taskforce (Issue 2006-033)
  2006_701 – 810_02 Transaction
    Adds (2) new MSC Codes to the 810_02 SAC 04 SET Transaction to meet a Regulatory requirement identified by TXU ED (Issue 2006-032)
  2006_702 – 650_04 Transaction
    Provides the TDSP with the mechanism to correctly communicate the Action (BGN08) taken when services have been Reconnected due to Denial of Access (RC004) by the TDSP when the TDSP Disconnected Service for Denial of Access (Issue-034)

## Slide 5: Approved as Emergency Change Controls
  2006_703 v3.0 Transaction Clean-up (Issue 2006-035)
    814_04 SET Transaction:
      Clarification required that ‘SNP’ shall only be used by the TDSP when 814_03 from ERCOT is for Mass Transition and a Safety Net Move-In Request is pending for a different CR for the ESI ID.
    814_08 SET Transaction:
      Correct ‘MTC’ Mass Transition Cancel gray box to restrict use to ‘ERCOT Use Only’ in the REF 1P (Status Reason)
    814_09 SET Transaction:
      Correct ‘EFR’ Evaluate for Resubmission to remove “For ERCOT Use Only” since this is response code from CR and TDSP in the REF~1P.
    814_14 SET Transaction:
      Correct DTM 376 Header gray box to be clear that segment is only required when Mass Transition and Move-Out date is communicated to the gaining CR from ERCOT
    814_15 SET Transaction:
      Correct ASI segment to remove the ‘RL’ data element, which is not necessary because ‘Accept’ response will accomplish the same thing.

## Slide 6: PR40038_01 Timelines
RBP PR50121_ 07
PR40038_01Tx SET 3.0 including Mass Transition and Ts & Cs (7/1/2007)
Jun 06
Jul 06
Aug 06
Sep 06
Oct 06
Nov 06
Dec 06
Jan 07
Feb 07
Mar 07
Apr 07
May 07
Moved from 10/22
7/15
5/1
Build
Prod. Dec 2006
UAT
Stabilization
9/11
7/17
Business Req’mts
9/25
Dec 2, 06 v3.0 Development
2/27/07
5/29
Conceptual Design
Detail Design
Build
UAT
7/1 Prod
Market Flight 0407
Market Requirements
7/3
Flight Testing
4/16 – connectivity
4/27 – Day 1
5/29 – Flight ends
Draft 3.0 TX SET Guides
9/1 – Due Date
8/10
Stabilization January 2007

## Slide 7: Completed Action Items
August 10 –
  Turned over TX SET v3.0 Requirements documentation to Susan Munson, Market Coordination Team Lead, to manage document updates/revisions where and if needed for the remainder of the project through version implementation
August 23-24 –
  TX SET Meeting reviewed/signed-off on final changes to redline Implementation Guides. READY for PUBLICATION!!
  Initial review of Protocols Section 15, 19, and 24 to comply with changes approved via PUCT Rule and/or TX SET Change Controls. TX SET approval scheduled for 9/12/2006
September 1 –
  Published TX SET Version 3.0 Redlined Implementation Guides to website
    http://www.ercot.com/mktrules/guides/txset/3.0/index.html

## Slide 8: Open Action Items Timeline
September 21 – PRS Open Meeting
  PRR 684 Mass Transition Section 15.1.2.9 has been submitted for approval
October 11 – RMS Open Meeting
  Protocol Revisions (PRR) for Sections 15, 19, and 24 will be submitted for approval
October 19 – PRS Open Meeting
  Protocol Revisions (PRR) for Sections 15, 19, and 24 will be submitted for approval
Market Issue Processing Large Volume of 814_20 Transactions
  TX SET’s initial brainstorming session was held on August 24 and some discussion also overlapped with the PRR 672 meetings concerning transaction processing timing. TX SET has plans to continue this discussion to discover possible solution/recommendations to RMS for the 814_20 volume issue at the TX SET September and October meetings.
  Because of overlapping efforts between the next phase of PRR 672 and the discussion around the volume issue, TX SET leadership has invited Karen Farley (ERCOT) to facilitate the SET meetings when this issue is being discussed to better utilize all resources available.

## Slide 9: Questions/Discussion