## Slide 1: Retail Business Processes PR 50121_07 Project Update Retail Market Subcommittee September 13, 2006 Adam Martinez Mgr, Market Operations DPO

## Slide 2: Project Status
Project Status
  On target for Schedule, Scope, and Budget
Project Phases
  Initiation & Planning Phases completed
  Execution Phase underway, scheduled Go-Live in early December
  Closing Phase not started, scheduled for February ’07
Recent Activities
  Completed build of Core Components (MVI, SWI, etc.)
  Completed migration of Core Components to iTEST
  Completed UAT Smoke Test in iTest & started formal UAT cycles
Next Steps
  Continue UAT of Core Components
  Migrate Reprocessing Build & ETS Build to iTEST on 09/13/06
    Phased build approach used for similar projects (i.e., TX SET releases)

## Slide 3: Milestones
Requirements (pens down) – Completed 04/12/06
Design (internal document) – Completed 07/14/06
Build (Core Components) – Completed 07/28/06
Internal Testing – Target Complete 11/18/06
  Transaction Processing – Approx. 600 Scripts, started 08/28/06
  Retail TML – Approx. 50 Scripts, starts 09/25/06
  ETS – Approx. 60 scripts, starts 09/25/06
  Exception Handling – 70 Scripts, starts 10/2/06
  Load/Performance – Starts 10/30/06
  MIMO Regression – Approx 450 Scripts, starts 10/16/06
Internal Training – Target Complete 11/18/06
Production Go Live – Target weekend 12/02/06
  Code Migration, Data Conversion, and Production Verification

## Slide 4: Risks / Issues Log
Risk / Issue | Mitigation | Status
Risk to RBP schedule due to delays incurred on MarkeTrack project testing schedule. iTEST TIBCO component needed for both MarkeTrak and RBP, but iTest configuration can only support single project pipeline thread | RBP team Deployed a 2nd TIBCO component to allow both projects to test in parallel without impact to each other | Closed

## Slide 5: User Acceptance Testing
ERCOT will communicate UAT results to the Market on a rotation cycle beginning this Friday, 9/15
  Similar approach used for other projects not requiring Market changes Market testing
  ERCOT testing team running functional tests to cover transaction processing of all transactions and related Retail transaction support applications
  ERCOT also running load test using Production volume

## Slide 6: Migration Weekend and SLA Exception
ERCOT will seek RMS approval for SLA exception once production migration schedule is finalized
  Approval needed to support expected migration activities that need to start prior to weekend
  ERCOT is currently looking at 80 hours of work effort to allow for migration, production verification, and backout plan contingency
  Migration Plan is currently under review to ensure minimal outage impact to the Market
  Final details presented and RMS approval requested at October RMS meeting

## Slide 7: Questions?