## Slide 1: Market Coordination Team Update Retail Market Subcommittee September13, 2006 Susan Munson Retail Market Liaison

## Slide 2
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO
Background
Objectives:
  TX SET Version 3.0 is the next iteration of retail market transaction enhancements and modifications to enable more efficient transaction processing and business process solidification to be supported by the Texas Electric Retail Market. In addition to the TX SET Change Controls, it was deemed necessary to implement solutions for the PUCT Project 31416, PRR660, and PRR672 in support of Terms and Conditions.
Drivers:
  PRR 660 – Provide a transactional solution for Mass Transition vs. current manual efforts involved for this process. The transactional solution approved with PRR660 will significantly reduce the time that is required to execute a Mass Transition by removing manual processing efforts and allowing for a consistent transactional solution
  PRR 672 - Retail Market Timing Necessary for compliance with PUCT Project 29637 Terms and Conditions
  PUC Project 31416 - relating to Provider of Last Resort. Requirements of PUCT Rulemaking must be developed and implemented for compliance with the PUCT Rules and Regulations
  PRR 684 – Customer Information File submitted periodically and stored for support of Mass Transition
  RMGRR 040 - Estimated Meter Readings Necessary for PUCT Project 29637
  RMGRR 042 - Mass Transition Process Necessary for PUCT Rule 31416
Dependencies:
  PR50121_07 RBP infrastructure and resources

## Slide 3
Project Status
Status:
  On target for schedule, budget, and scope
Project Phases:
  Initiation – Completed
  Planning – Target completion date December 9, 2006
  Execution – Mandated completion date July 1, 2007
  Closing – Target completion is post go-live
Recent Activity:
  Finalized and approved Market Requirements document August 10, 2006
  Posted Version 3.0 Implementation Guides on ERCOT.com
  Posted Version 3.0 SEF Files on Retail Testing website
  Reviewing ERCOT Internal Requirements Document
Next Steps:
  Obtain Sign-off on ERCOT Internal Requirements Document
  Begin Internal Conceptual Designs
  Develop Recommendations for TTPT Script Sub-team Market Testing requirements
  Start creation of Production Implementation and Contingency Plans
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 4
Milestones
Market Requirements (pens down) – Completed August 10, 2006
Design (internal document) – December 9, 2006
Planning Phase Exit – December 9, 2006
Build – Target completion of February 27, 2007*
Internal Testing – Target completion of June 16, 2007*
Market Testing – Target completion of May 29, 2007*
Internal Training – TBD
Production (Go live) – July 1, 2007
* Dates to be confirmed upon Planning Phase exit
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 5: Risks / Issues
Issue | Mitigation | Owner
PR50121_07 RBP – Stabilization necessary for successful implementation | Schedule management Milestone completion | ERCOT
PUCT Mandate of 07/01/2007 poses tight timeline | Schedule and resource management Milestone completion | All
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 6
Meeting Dates and Locations through 2006
  October - ERCOT in Austin (10/3)
  October – ERCOT in Austin (10/24)
  November - ERCOT in Austin (11/6)
  December – CenterPoint in Houston (12/??)
(Note: all meetings are held in conjunction with TX SET meetings)
Future Meetings/Market Communications
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 7: ERCOT Contacts
ERCOT Project Manager ERCOT SR. Business Analyst
Hope Satterfield Jennifer Frederick
hsatterfield@ercot.com jfrederick@ercot.com
512-248-6522 (w) 512-248-6733 (w)
512-771-9582 (c) 512-413-0815 (c)
ERCOT Market Liaison
Susan Munson
smunson@ercot.com
512-248-3881 (w)
512-826-0564 (c)
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 8: Questions?
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO