## Slide 1: Enhancements to FasTrak PR 50007 Project Update Retail Market Subcommittee September 13, 2006 Adam Martinez Mgr, Market Operations DPO

## Slide 2: Recent Activities – API Issues
ERCOT reported to the Market on August 15th that the product launch, scheduled for August 26, would be delayed
SOAP Header Interoperability Issue - Delay was result of API interoperability issue discovered between ERCOT and Market Participants
  ERCOT specified SOAP standard; did not specify “required” software tools for Market to use when generating API messages
  Difference in tools used by Market Participants and ERCOT delivered slight differences in message Header information
  Header information generated by “sender” did not match Header information expected by “receiver”
  Each of 5 MPs coding for API had to work with ERCOT individually to resolve issue because resolution depended on software tools used and changes specific for resolution

## Slide 3: Recent Activities – API Issues
In addition to the SOAP Header issue, two additional API-related issues were identified during the interoperability resolution period
XML Issue
  Specific to each MP; discovered during dev tests of SOAP Header fix
  Case-by-case simple (incorrect or missing data, incorrect format), but time-consuming activity due to differences specific to each MP
API Market Certification Requirements Issue
  Differences expectations between ERCOT and Market
  ERCOT expecting full functionality certification based on TTPT scripts delivered for Market test
  TTPT communicated to MPs that full functionality testing not required, MPs only certify for functions to be used

## Slide 4: Recent Activities – API Issues
ERCOT and Market have resolved all known API issues
  4 of 5 MPs report readiness; 5th MP not using API at initial launch
API Issues Resolutions
  SOAP Header Interoperability Issue
    Resolved via fixes specific to each MP, but contained bulk of recode efforts to ERCOT code
    ERCOT will update API documentation to clarify standard and toolset options for future use
  XML Issue
    Resolved through 1-on-1 technical reviews and development testing cycles with each MP
  API Market Certification Requirements Issue
    Addressed via input and clarity from TTPT
    ERCOT making changes to API permissions and Market test requirements to align with TTPT direction

## Slide 5: Current Events – GUI Issues
ERCOT currently addressing 2 GUI-related issues
Excel Scientific Notation Issue – when downloading long numbers from data to Excel (e.g. ESI IDs), number converts to scientific notation because field not recognized as text
  Vendor ruled out root cause within product code; inherent in MS Excel
  ERCOT proceeding with investigation of internal options for solution
  Dev testing of fix options underway; fix expected for initial launch
Mass Update Issue – when a mass update request submitted by several users at same time, updates for some fail while others are successful
  Feature functionally works, but may require resubmission to complete
  No data integrity concerns related to multiple failed attempts
  Product vendor, Serena, engaged onsite at ERCOT to resolve issue
  No ETA for delivery of fix

## Slide 6: ERCOT Recommendation
At this time, ERCOT cannot provide revised budget & schedule revisions that reflect all known impacts
  Mass Update fix remains unknown; revisions to current estimates exclude impact of that issue
Seeking RMS input and feedback today in support of ERCOT recommendation and budget request to be presented to ERCOT Board next week
ERCOT Recommendation: proceed with remaining project activities in support of launch; do not wait on Mass Update fix
  Remove Mass Update fix from critical path
  Deliver product to Market sooner, albeit with Mass Update feature that requires possible resubmissions to complete updates
  Keep Mass Update fix a high priority item with intent to deliver ASAP

## Slide 7: Known Budget and Schedule Impacts
Budget Impact
  Budget increase, EXCLUDING fix for Mass Update issue, is estimated at $188K
  Total project budget cap increasing from $2.5MM to $2.7MM
  Project costs to date have maxed the approved budget cap
    Includes completion of planned activities through GUI Market Testing
    Includes completion of unplanned work and/or re-work related to analysis and coding efforts for API & GUI issues (excluding Mass Update issue)
Schedule Impact
  If proceed with project immediately and avoid continued delay from Mass Update issue, remaining activities will consume up to a 10-week period
  New Market go-live date is November 11
  This schedule minimizes impacts from ERCOT planned blackout periods and conflicts from other projects in pipeline (RBP & TX SET 3.0)
Details on next 2 slides

## Slide 8: Budget Increase Detail
Labor Category | Planned Work – Not Yet Completed | Unplanned Work – New/Repeat
Internal Labor | $78,640 | $75,215
External Labor | $0 | $16,671
Contingency | $0 | $17,053
Totals | $78,640 | $108,939
Project Activity | Planned Work – Not Yet Completed | Unplanned Work - New/Repeat
API and GUI issues resolution (to date) |  | X – New
Product Testing (pTest) / iTest Prep |  | X – Repeat
iTest Environment Migration |  | X – Repeat
ERCOT UAT – GUI & API Regression Test |  | X – Repeat
Market CERT Test – API | X | 
Production Migration | X | 
Production Stabilization Prior to Market Release |  | X - New
Market Release | X | 
Project Closure | X | 
Estimated budget increase is $187,579 and all Labor-related plus 10% contingency

## Slide 9: Proposed Schedule Detail
New Schedule Accounts for separate ERCOT and Market Release Dates
* Dates tentative; final dates locked by end of week
Project Activity | Duration | Dates*
API and GUI issues resolution (to date) | Ongoing since 8/15 4 wks | 8/15 – 9/15
Product Testing (pTest) / iTest Prep | 1 wk | 9/11 – 9/15
iTest Environment Migration | 1 wk | 9/18 – 9/22
ERCOT UAT – GUI & API Regression Test | 4 wks | 9/25 – 10/20
Market CERT Test – API | 2 wks | 10/23 – 11/03
Market Training Window | 1 wk | 11/03 – 11/10
Production Migration & Stabilization Prior to Market Release | 2 wks | 10/30 – 11/10
Market Release | 1 day | 11/13
Project Closure | 4 wks | 11/13 – 12/8

## Slide 10: Other Topics - Deferred Business Requirements
Deferred Business Requirements |  | 
Defect / Issue | Reason to Defer | Status
Bulk Insert Performance – The requirement states that each issue submitted via Bulk Insert must be submitted in three seconds or less | In the testing environment, issues submitted via Bulk Insert consistently are submitted in 4.5 seconds | Target fix post-launch when production stats are confirmed. ERCOT will monitor results to ensure optimal performance and minimal impact to user experience.
TML to MarkeTrak Link prompts for Digital Cert twice | The business requirement states that users will only have to enter their digital certificate once. This defect only occurs when users access MarkeTrak via TML | Target fix post-launch. Current work-around is for users to create “Favorites” link directly to MarkeTrak to avoid additional prompt for certificate.
While there are 3 concurrent users (same dig cert) the MarkeTrak system does not properly display the error messages for invalid data | ERCOT has repeatedly educated the Market during this effort that all users need to have their own digital certificate | This is not an issue impacting requirements as ERCOT has required that all users be assigned individual digital certificates.
Inadvertent Switch Issues – The Siebel call is not populating all of the necessary data | The business requirement states that MarkeTrak will interface with Siebel to auto-populate information associated with Inadvertent Switch issues after it is submitted to ERCOT | Targeting fix post-launch. ERCOT has already agreed to continue to support Siebel data population via manual steps as done today. ERCOT will monitor volumes of Inadvertant Switch Issues and will escalate issue resolution if volumes become unmanageable.

## Slide 11: Other Topics – Digital Certificates
RMS asking for information related to ERCOT’s Digital Certificate Audit and plans for incorporation of MarkeTrak certificates to be included in audit scope
Digital Certificate Audit responsibility is with Larry Grimm,
  Request for information delivered too late to respond by today
  Will plan to deliver information to RMS at October meeting
  If desired, can also address topic during a weekly Monday call with the Market

## Slide 12: Questions?