## Slide 1: ERCOT Outage Evaluation & Resolution Phases I & II PR 60006_01 Project Update Retail Market Subcommittee September 13, 2006 Adam Martinez Mgr, Market Operations DPO

## Slide 2: Project Status
Project Status
  On target for Schedule, Scope, and Budget
  Slight risk to schedule currently under review
Project Phases
  Initiation & Planning Phases completed
  Execution Phase underway, scheduled completion in October ’07
  Closing Phase not started, scheduled for December ’07
Recent Activities
  Systems installed and configured in Development environment
  End to end testing initiated
  Migrations plans to CERT and ITEST started
Next Steps
  ITEST environment build out
  Development testing completion

## Slide 3: Risks / Issues Log
Risk / Issue | Mitigation | Status
Schedule risk – NAESB Production Release date change possibly needed to address storage capacity constraint Availability of storage capacity to support project need is a concern Delivery & implementation timelines associated with purchase of additional storage capacity may result in need to change production date | Project team working closely with Storage Team to mitigate impact Team considering moving release to November 17th from October 7th to mitigate storage constraint by allowing additional window of time to secure needed storage. A change to date also provides for A release during ERCOT’s planned production migration window for November; no SLA exception needed A release prior to RBP production migration to ensure minimal resource contentions between the two projects | Active

## Slide 4: Testing Considerations
QA Build Out project delivered test environment more like production environment
Testing period currently planned for 4 weeks
  Functional Testing
    Leveraging manual and automated scripts
    Similar to other UAT – do results match expected outcomes?
  ERCOT testing performance / stability
    Using copy of production data
    Performance – is there any degradation to current processing times?
    Load – are production volumes in danger?
    Stability – do processes run for extended period without interruption?

## Slide 5: Questions?