## Slide 1: PMO Update to PRS
Troy Anderson
Program Management Office
September 21, 2006

## Slide 2
Project Status Updates
Project Implementation Date Change
  RO – SCR738 – MarkeTrak (FasTrak replacement)
    Revised implementation date = 11/11/2006
Recent Project Added to PPL
  RO – Majordomo Replacement (1.1/8.5, $100k)
Projects Now in Planning Phase
  MO – PRR666 – Mod. of RPRS Undersched. Capacity Charge Calc
  MO – PRR565 – Calc. of Losses for Settlement
  MO – PRR668 – Distribution Loss Factor Calculations
Project Cancelled
  SO – Outage Scheduler Enhancements Phase II

## Slide 3
2007 Project Budget Update
Program Area | Initial Budget Request | Revised Budget Request
CO | $ 5,750,000 | $ 4,250,000
IO | $ 16,000,000 | $ 12,750,000
MO | $ 2,058,000 | $ 1,500,000
RO | $ 7,659,000 | $ 7,000,000
SO | $ 4,908,000 | $ 4,500,000
Totals | $ 36,375,000 | $ 30,000,000
Program Area | Carryover | Baseline Maintenance | Enhancements | PUCT/NERC/Market
CO | $ 900,000 | $ 850,000 | $ 2,500,000 | $ 0
IO | $ 3,100,000 | $ 4,350,000 | $ 5,300,000 | $ 0
MO | $ 400,000 | $ 100,000 | $ 800,000 | $ 200,000
RO | $ 4,700,000 | $ 0 | $ 975,000 | $ 1,325,000
SO | $ 2,350,000 | $ 0 | $ 600,000 | $ 1,550,000
Totals | $ 11,450,000 | $ 5,300,000 | $ 10,175,000 | $ 3,075,000
Modified budget request to meet target
Breakout of project budget by project type

## Slide 4
2007 Project Budget Update
Why did the budget change take place?
  Allowed ERCOT to maintain its current admin fee
What is the impact?
  Primarily IT infrastructure changes
  Changes impacted ERCOT-requested projects
  No changes to priorities or rankings in CO, MO, RO and SO
Additional review is taking place now that Nodal budget is coming into focus
  Impacts relate to IO and SO program areas