|  |  | System Planning Division |
| --- | --- | --- |
|  |  | Monthly Status Report to Technical Advisory Committee Reliability and Operations Subcommittee for August 2006 |
|  | Report Highlights |  |
| Item |  | Section |
| 1. | Interconnection Requests Increase by 2,258 MW in August. 2,258 MW of new generation interconnection requests were received by ERCOT resulting in a total of 40,753 MW of potential new generation under study. | 1.0 |
| 2. | Atkins RMR Exit Work Underway. Construction of the transmission improvements necessary to exit the Atkins RMR contract to be completed by October 31, 2006. | 2.0 |
| 3. | Long-Term System Study Progressing. ERCOT staff continues modeling and evaluation of possible transmission upgrades related to potential Competitive Renewable Energy Zones (CREZs) and development of a Long-Term System Assessment (LTSA) pursuant to new requirements under Senate Bill 20. | 3.0 |
| 4. | Developing Methodologies to Comply with PASA. ERCOT staff is developing a plan to implement new requirements of the new resource adequacy rules, particularly for monthly projection of transmission constraints as required in the Projected Assessment of System Adequacy (PASA) rule. | 3.0 |
| 5. | Load Forecast Methodology Reviewed. ERCOT staff completed a simulation to determine what the forecast would have been if the actual 2006 temperatures had been used in preparing the 2006 forecast. Results validated the model utilized. | 4.0 |

1.0	Status of Active Generation Interconnection Requests

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” data folder posted in the “Operations and System Planning” data area on the ERCOT website.

  - New Generation Beginning Commercial Operations.

No new units have begun commercial operations since the July report.

1.2	Active Generation Interconnection Requests.

The table below summarizes the active generation interconnection requests currently being processed by ERCOT System Planning.  The current 99 projects reflect 40,753 MW of capacity, an increase of 2,258 MW of potential capacity over the July total of 38,495 MW.

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |
| --- |
| Currently tracking 81 active generation interconnection or change requests |
|  | North | South | West | Total |
| Security Screening Study |  | 0 | 1 | 9 | 10 |
| SSS Completed |  | 7 | 9 | 14 | 30 |
| Full Interconnect Study |  | 14 | 7 | 33 | 54 |
| FIS Completed |  | 1 | 1 | 3 | 5 |
| Interconnect Agreement Completed |  | 2 | 3 | 12 | 17 |
| Capacity for Grid, MW |  | 15,093 | 11,487 | 14,173 | 40,753 |
| Wind MW (under development) |  | 480 | 4,126 | 11,917 | 16,523 |

| INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED BY FUEL TYPE |
| --- |
| Fuel -Type | Public Projects | Confidential (Non-Public) | Total Capacity Under Review (MW) | % |
| Natural gas | 2,300 | 4,445 | 6,745 | 17% |
| Coal | 11,709 | 4,652 | 16,361 | 40% |
| Wind | 2,944 | 13,578 | 16,523 | 41% |
| Other | 12 | 1,112 | 1,124 | 2% |
| Totals | 16,965 | 23,788 | 40,753 | 100% |

1.3	Potential Future Generation Interconnections.

The table below summarizes the publicly known potential future generation projects for the ERCOT region.

| FUTURE GENERATION INTERCONNECTIONS (PUBLIC PROJECTS) |
| --- |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 06INR0008 | Big Spring Electricity Gen Fac 1 | Interconnect Agreement | Howard | West | Waste heat | Aug-06 | 12 |  |
| 06INR0016 | Dow 9 | Interconnect Agreement | Brazoria | South | Gas | Oct-06 | 0 |  |
| 05INR0018 | Horse Hollow 2 | Interconnect Agreement | Nolan | West | Wind | Oct-06 | 186 |  |
| 04INR0020 | WKN Wind 1 Snyder | Interconnect Agreement | Scurry | West | Wind | Dec-06 | 60 |  |
| 05INR0011 | Forest Creek | Interconnect Agreement | Sterling | West | Wind | Dec-06 | 215 |  |
| 04INR0011 | Mesquite Wind 1 | Interconnect Agreement | Shackelford | West | Wind | Dec-06 | 200 |  |
| 03INR0034 | Silver Star | Interconnect Agreement | Erath | West | Wund | Mar-07 | 60 |  |
| 04INR0015 | Cirello 1 | Interconnect Agreement | Taylor | West | Wind | Mar-07 | 233 |  |
| 06INR0035 | Colorado Bend Energy Center 1 | Interconnect Agreement | Wharton | South | Gas | Apr-07 | 275 |  |
| 06INR0036 | Quail Run Energy Center 1 | Interconnect Agreement | Ector | West | Gas | Apr-07 | 275 |  |
| 06INR0038 | Scurry County Wind 1 | Interconnect Agreement | Scurry | West | Wind | May-07 | 130 |  |
| 03INR0030 | Wild Horse Wind 1 | Interconnect Agreement | Cottle | West | Wind | Jun-07 | 126 | New |
| 05INR0015 | Gulf Wind 1 | Public Letter | Kenedy | South | Wind | Sep-07 | 300 |  |
| 06INR0021 | Barton Chapel Wind 1 | Interconnect Agreement | Jack | North | Wind | Oct-07 | 120 |  |
| 04INR0011 | Mesquite Wind 2 | Interconnect Agreement | Shackelford | West | Wind | Dec-07 | 200 |  |
| 03INR0030 | Wild Horse Wind 2 | Interconnect Agreement | Cottle | West | Wind | Aug-08 | 39 | New |
| 05INR0015 | Gulf Wind 2 | Public Letter | Kenedy | South | Wind | Sep-08 | 300 |  |
| 09INR0006 | Oak Grove 1 | Public Letter | Robertson | North | Coal | Mar-09 | 790 |  |
| 09INR0008 | Big Brown 3 | Public Letter | Freestone | North | Coal | Apr-09 | 858 |  |
| 09INR0010 | Martin Lake 4 | Public Letter | Rusk | North | Coal | Apr-09 | 858 |  |
| 09INR0011 | Monticello 4 | Public Letter | Titus | North | Coal | Apr-09 | 858 |  |
| 09INR0013 | Tradinghouse 3 | Public Letter | McLennan | North | Coal | Apr-09 | 858 |  |
| 09INR0014 | Valley 4 | Public Letter | Fannin | North | Coal | Apr-09 | 858 |  |
| 06INR0006 | Greenville | Public Letter | Hunt | North | Gas | May-09 | 1750 |  |
| 01INR0028 | Orion Delaware Mt. Wind Farm | Interconnect Agreement | Culberson | West | Wind | Jul-09 | 175 |  |
| 08INR0003 | Sandow 5 | Public Letter | Milam | North | Coal | Jul-09 | 585 |  |
| 05INR0015 | Gulf Wind 3 | Public Letter | Kenedy | South | Wind | Sep-09 | 300 |  |
| 09INR0009 | Lake Creek 3 | Public Letter | McLennan | North | Coal | Oct-09 | 858 |  |
| 09INR0012 | Morgan Creek 7 | Public Letter | Mitchell | West | Coal | Oct-09 | 858 |  |
| 09INR0006 | Oak Grove 2 | Public Letter | Robertson | North | Coal | Mar-10 | 790 |  |
| 09INR0013 | Tradinghouse 4 | Public Letter | McLennan | North | Coal | Apr-10 | 858 |  |
| 09INR0001 | Sandy Creek 1 | Public Letter | McLennan | North | Coal | Jun-10 | 800 |  |
| 09INR0002 | J K Spruce 2 | Public Letter | Bexar | South | Coal | Jun-10 | 750 |  |
| 05INR0015 | Gulf Wind 4 | Public Letter | Kenedy | South | Wind | Sep-10 | 300 |  |
| 10INR0002 | Hugo Plant | Public Letter | Choctaw, OK | North | Coal | Dec-10 | 500 |  |
| 11INR0001 | Twin Oaks 3 | Public Letter | Robertson | North | Coal | Jun-11 | 630 |  |
|  |  |  |  |  |  | Totals: | 16,965 |  |

2.0	Status of RMR Contracts

The table below summaries generating units currently under RMR Contract as of August 31, 2006.

| Unit | Generation Capacity (MW, Net) | RMR Contract Status | Contract Date | Current Anticipated Exit Date | Change Since Last Report |
| --- | --- | --- | --- | --- | --- |
| Laredo 1, 2, & 3 | 172 | Under Contract | 1/1/06-12/31/06 | 3Q 2010 under review | CCN filed on 9/13 for Exit Strategy Transmission Project |
| Atkins 4, 5, 6 | 97 | Under Contract | 6/1/06-10/31/06 | 10/31/06 | ERCOT Board notified of RMR/Exit Strategy Status on 9/12. |
| Total MW Under RMR Contract as of March 31, 2006 | 269 |  |  |  |  |

Atkins RMR:  ERCOT staff has completed its review of the need for Atkins unit 4, 5, and 6 beyond summer 2006 and has confirmed that once the Gibbons Creek-College Station Switch 138kV project is complete, ERCOT can release all the Atkins units from RMR status.  Texas Municipal Power Agency (TMPA), Brazos Electric Power Cooperative (BEC), and College Station Utilities (CSU) are performing the work on this project.

3.0	Regional Planning Activities

The following summarizes numerous significant activities associated with regional planning issues.

3.1	Long-term System Study (SB20).

  - Initiated modeling and evaluating transmission upgrades related to potential Competitive Renewable Energy Zones (CREZs).

  - Worked with Southwest Power Pool (SPP) Planning staff on approach to joint consideration of connection for potential CREZ in Texas Panhandle.

  - Identified end-to-end line loading and other local problems in each scenario.  Since the focus of the Long-Term System Assessment (LTSA) is on bulk transmission needs, these problems will be shared with the TSPs but overlooked in the remainder of the analysis.

  - Begun modeling and evaluating transmission upgrades necessary for bulk transfers of power into high load areas to meet reliability criteria.

  - Five-year Transmission Plan development.

  - Completed analysis of 2007 and 2008 reliability and economic upgrades; working on economic upgrades for 2009.

  - Identified solutions that can be implemented in 2007 and 2008 for 5,000 MW wind scenario which indicate that a significant portion of the curtailments that would otherwise exist can be eliminated by these near-term upgrades from a thermal perspective; however, the study of potential dynamic constraints has not been completed and these constraints may require significantly more curtailment than the thermal constraints.

  - Work on 2010 and 2011 scenarios will begin once the 2009 economic study is completed.

  - Entergy Study (PUCT Project 32217:  Entergy Gulf Coast Inc.’s Plan for Identifying Applicable Power Region Pursuant to PURA 39.452(F)).

  - Studies of potential lower-cost alternatives to the projects presented at the March PUCT workshop, as suggested by stakeholders and others, have begun.

  - Powertech Labs has begun work on the dynamic studies of the potential interconnection.

  - Regulatory and Policy

    - Preparing comments on PUCT Project 31972 Renewable Rules.

    - Preparing implementation approach on new resource adequacy rules as they relate to Regional Planning, particularly the requirement for monthly projection of 36 weeks of projected transmission constraints in Projected Assessments of System Adequacy (PASA).

  - Regional Planning Group Project Reviews.

  - STEC Clemville project has completed ERCOT Independent Review and a letter supporting the project is in preparation.

  - TXUED Venus-Sherry project has completed ERCOT Independent Review and will be presented to TAC and BOD for approval.

  - TXUED Odessa 345/138kV Autotransformer project has completed ERCOT Independent Review and a letter supporting the project is in preparation.

  - TNP/CNP 345kV Tie Project is currently in ERCOT Independent Review.  This is a $22.1 million set of projects to provide support for TNP’s system south of Houston.

  - Independent study of the Sandow #2 auto project was completed and a letter supporting the project was sent to TXUED.

3.6	Other.

- Completed exit strategy development for Atkins RMR.

- Provided support for Transmission Operations in the Bryan and College Station area and ERCOT Operations for construction related issues.

4.0	Transmission Services Activities

4.1 	Dynamic Analysis and Modeling.

- ERCOT staff is continuing to prepare and review a draft study of dynamic limits for power transfer out of West Texas.  A new run engine, developed by Staff, to automate multiple PSSe dynamics runs and plotting of results was utilized in the study.

- Supporting dynamic studies associated with the proposed integration of Entergy into ERCOT.  Participating in conference calls and meetings to define study scope and data requirements for Powertech.

- Supporting ongoing Regional Planning efforts to develop a wind ancillary service when related to dynamics studies.

- Supporting various outside efforts (WECC, UWIG, NREL, CIGRE) to improve wind farm modeling.

- Supporting ongoing DWG efforts to develop a transient voltage recovery criteria, update the DWG procedure manual and draft requirements for field testing of NERC generator performance standards (PRC-019, PRC-024, MOD-026, & MOD-027).

- Preparing for upcoming activities for the final third of the year including a transient event screening study for the entire ERCOT system.

4.2	Case Building.

- Quarterly updates of the SSWG base cases for the August TPIT have been completed and the cases have been posted.

- Started the SPWG future year short circuit database building.

4.3	Network Model Management System (NMMS) Support.

- Attend meeting with the NMMS team at TXU ED to discuss development of Network Model Management System (NMMS) and TXU ED’s TMIS functionality.

4.4	Load Forecasting.

- Completed a first-pass on the development of the Interval Data Recorders (IDRs) and Non-Opt In Entities (NOIEs) profile type forecast.

- Finalized the creation of a more efficient process to retrieve final cuts for settlement load data, including additional capabilities for retrieving generation data.

- Conducted a simulation to determine what the forecast would have been if the actual 2006 temperatures had been used in preparing the 2006 long-term demand forecast, which was finalized at the beginning of this year.  The results of this simulation resulted in a “forecast” which varied only 0.3% from the actual peak demand.

- Attended a software training class on MetrixND.

4.5  	Studies underway or planned within System Planning Division

- Verifying TIPIT updates for 3rd quarter.

- Began update of the planning contingency file.

4.6	Other.

- Started the 2007 transmission losses calculation with SSWG.

- Provide support to ERCOT settlements for new station CM Zone identification.

- Completed October TCR calculations.

- Continuing efforts to complete the 2007 transmission losses calculation with SSWG.

- Provide support to ERCOT settlements for new station CM Zone identification.

- TARA training.

- Black Start Testing Training.

- Meeting with Stakeholders on New Generation Interconnection Procedures.

- Upcoming Events/Deadlines

September

- August TPIT to be completed by end of month and posted September 1st

- October I Report materials ordered

- System Planning Map Orders completed

- Draft and management approval of October 1 report

- NERC Winter Assessment

- Regional Planning Group Meeting; September 25th.

- Finalize new generation interconnection procedures and post manual on website

- Steady State WG 2007 Data Set B case creation to begin Sept 15 RAW data due to ERCOT for SSWG 2007 data set B

October

- TAC ROS Dynamics Working Group (DWG) meeting; October 3-4

- Publish October 1 Report

- Regional Planning Group Meeting; October 23rd.

- Oct 30- Nov 1 SSWG DSB meeting at TCC 1

November

- NERC MMWG meeting Nov 13-14