## Slide 1: Role of Account Management at ERCOT
Project Update
Data Extract Projects
Adam D. Martinez
Mgr., Market Operations Divisional Project Organization
Commercial Operations Subcommittee Meeting
September 26, 2006

## Slide 2: Status Summary PR 30026 EPS Data Extract (aka Resource ID Extract)
Current Status
  Production Stabilization & Verification in progress
Extract Project Information Postings
  New market extract
  Find User Guide at http://www.ercot.com/services/comm/projects/current/30026/index.html
  Find DDL at TML Report Explorer/Extract Data Definitions - being verified for immediate posting
Market Testing Strategy
  Continuing with the philosophy of past implementations of new reports/extracts, ERCOT will not be providing market test files for the new extracts

## Slide 3: Target Timeline PR 30026 EPS Data Extract (aka Resource ID Extract)
September
October
November
Mid to Late 10/2006
Complete Production Stabilization
Market Go Live
PR 30026
December
9/19
EIS Production Migration
PR 30026
January
February
MPs request stabilization files for review
PR 30026 Production Stabilization begins

## Slide 4: Status Summary PR 40042_06 Lodestar Batch Extracts
Current Status
  Production Stabilization & Verification in progress
Extract Project Information Postings
  ERCOT project to move current extracts for Shadow Pricing, Load, Generation and Settlements & Billing from Data Archive to Lodestar ODS – AND – to create new Settlement Input Data (SID) Extract
  Find User Guides at http://www.ercot.com/services/comm/projects/current/40042_06/index.html
  Find DDLs at TML Report Explorer/Extract Data Definitions – using existing DDLs; SID is using the current S&B DDL since it is an excerpt of the current S&B
Market Testing Strategy
  SID is using the current S&B DDL since it is an excerpt of the current S&B
  Continuing with the philosophy of past implementations of new reports/extracts, ERCOT will not be providing market test files for the new extract
    During production stabilization 9/21/06–10/06, ERCOT will provide MPs that are currently opted in per extract the opportunity to request ERCOT’s verified stabilization files to be FTP’d, emailed or mailed. Will allow MPs to see the addtime/timestamp lags
    ERCOT will be sending a market notice 9/25 to offer this to market participants with information on how they need to request files

## Slide 5: Timeline Target PR 40042_06 Lodestar Batch Extracts
September
October
November
9/21
EIS Production Migration
PR 40042_06
Mid to Late 10/2006
Complete Production Stabilization
Market Go Live
PR 40042_06
December
9/22
PR 40042_06
Production Stabilization begins
January
February
MPs request stabilization files for review

## Slide 6: Summary Status PR 40007 SCR 727 Phase II
Current Status
  Product Testing (PTEST) in progress
Extract Project Information Postings
  ERCOT’s project to move current extract for SCR 727 from Data Archive to Lodestar ODS
  Post updated User Guide and cutover plan to project on ERCOT.com (http://www.ercot.com/services/comm/projects/current/40007/index.html) by 10/15/06
  DDL will remain the same and is currently posted to TML/report explorer/public/extract data definitions – using existing DDLs
Market Testing Strategy
  During production stabilization 12/2/06 – 01/07, ERCOT will provide MPs the opportunity to request ERCOT’s verified stabilization files to be FTP’d, emailed or mailed
  This will allow MPs to see the addtime/timestamp lags, as well as the new naming convention on the count.csv file
  ERCOT will send a market notice after production migration with the details for market participants to request the files

## Slide 7: Timeline Target PR 40007 SCR 727 Phase II
September
October
November
10/9
ITEST Begins for 12/2/06 release
PR 40007
December
10/15
PR 40007
Post User Guide with Cutover Plan
12/2
EIS Production Migration
PR 40007
12/4
PR 40007
Production Stabilization Begins
January
February
1/2007
Complete Production Stabilization
Market Go Live
PR 40007
MPs request stabilization files for review

## Slide 8: Summary Status PR 50024 SCR 740 Enhancements to SCR 727 Phase II
Current Status
  Product Testing (PTEST) in progress
Extract Project Information Postings
  Find draft versions of the following documents: User Guide, WSDL, Technical Specification, and Web Services 101 documentation at http://www.ercot.com/services/comm/projects/current/50024/index.html
  Market notice will be sent when ERCOT posts any updates to the draft documentation
Market Testing Strategy
  Planning for a point-to-point market test still a work in progress. ERCOT working through the details to ensure that the testing process is well-defined and environment hardware available/in place to support this type of testing
  ERCOT is working to provide MPs opportunity to perform Web Services connectivity testing by scheduling to test in CERT environment starting Q1 2007
    This test will only test for a success/fail acknowledgement response on service request. This will ensure that MPs are able to connect to ERCOT point-to-point and ERCOT is able to read the automated Web Service request
    This test will not provide payload data to the request

## Slide 9: Summary Status PR 50024 SCR 740 Enhancements to SCR 727 Phase II
September
October
November
10/9
ITEST Begins for 12/2/06 release
PR 50024
December
12/2
EIS Production Migration
PR 50024
January
February
11/3, 11/7 OR 11/10
PR 50024
Technical & Business Training Session by ERCOT
11/17
PR 50024
Post updated User Documentation

## Slide 10: Timeline Targets Consolidated Summary
September
October
November
9/21
EIS Production Migration
PR 40042_06
Mid to Late 10/2006
Complete Production Stabilization
Market Go Live
PR 30026
PR 40042_06
10/9
ITEST Begins for 12/2/06 release
PR 40007
PR 50024
December
10/15
PR 40007
Post User Guide with Cutover Plan
12/11
ITEST Begins for 1/18/07 release
PR 50059 extracts
9/19
EIS Production Migration
PR 30026
9/22
PR 40042_06
Production Stabilization begins
12/2
EIS Production Migration
PR 40007
PR 50024
12/4
PR 40007
Production Stabilization Begins
10/2
Go Live
PR 50025
TDSP ESIID Extract
January
February
11/3, 11/7 OR 11/10
PR 50024
Technical & Business Training Session by ERCOT
1/2007
Complete Production Stabilization
Market Go Live
PR 40007
1/18
EIS Production Migration
PR 50059 extracts
2/2007
Complete Production Stabilization
Market Go Live
PR 50059 extracts
11/17
PR 50024
Post updated User Documentation
MPs request stabilization files for review
MPs request stabilization files for review
MPs request stabilization files for review
PR 30026 Production Stabilization begins

## Slide 11: Project Activity - Other EDW-related Projects
PR 50005 EMMS Extracts
  Production Stabilization on HOLD
  Hold due to impact of PUCT Docket mandated changes for 10/06
PR 50025 ESIID Lookup/TDSP ESIID Extract (PRR312)
  Production Stabilization & Verification complete for TDSP ESIID Extract
    Market Go Live 10/2/2006; notice sent 9/20/2006
  GUI/PiApp in Integration Test UAT (ITEST)
    Scheduled Market Go Live 12/9/06
PR 50030 EDW Lodestar Transition
  Development in progress
PR 50059 EDW Siebel Transition
  Development in progress
  TDSP ESIID Extract DDL will add field for POLR Customer Class that will be provided with PR 40038 TX Set 3.0

## Slide 12
QUESTIONS?