## Slide 1: Role of Account Management at ERCOT
Project Update
PR 40103 TML Phase 3
Adam D. Martinez
Mgr., Market Operations DPO
Commercial Operations Subcommittee Meeting
September 26, 2006

## Slide 2: Project Recent Activity
ERCOT met with COPS on 07/26/06 and presented 30 requirements that COPS may want to implement
COPS categorized the 30 enhancement requests as follows:
  Parking Lot – 12
  Replaced by Nodal NOMCR process – 1
  Required for Nodal – 3
  Covered by SCR 743 – 1
  Nice to have for Zonal / Must have for Nodal – 8
  In scope for this effort and Nodal – 2
  Nice to have for Zonal – 3
COPS requested ERCOT provide estimates on 5 of the requirements
COPS wanted to discuss benefit of the 8 enhancements flagged as “Nice to have for Zonal / Must have for Nodal ” with respective companies prior to making the decision to implement

## Slide 3: ERCOT Requirements Analysis “In scope for this effort and Nodal / Nice to have for Zonal”

## Slide 4: ERCOT Requirements Analysis “Nice to have for Zonal / Must have for Nodal”

## Slide 5: Timeline Analysis
Possible Delivery Targets
  Under SIR process, delivery target no sooner than March 2007
  Under project process, delivery target no sooner than 3rd Quarter 2007
Constraints Impacting Delivery Timelines
  Targets based on current project pipeline and resource allocations
  SIRs can be implemented during scheduled monthly releases based on priority

## Slide 6: ERCOT Market Ops DPO Recommendation
Cancel current Zonal project, PR-40103
  Current constraints pushing out delivery window
  Most requirements currently on list would be addressed by Nodal rewrite of “MIS”
  Cancellation frees up 2006/2007 funding for other initiatives
  COPS to formally cancel with vote
Address remaining Zonal enhancements under SIR process
  Work with Client Relations to submit SIRs for Zonal TML needs
  No SCR required from Market
  MO DPO and MORO CART to schedule SIRs implementation in monthly release for TML changes
  MO DPO can provide SIR status to COPS on request

## Slide 7
QUESTIONS?