## NMMS
Number | Issuing Entity | Name | Page Number | Description | Accept/Reject/Response | Reviewer | Comments/Reasons | Project Related | Document Incorporated | Original Requirements

## EMS
Number | Issuing Entity | Name | Page Number | Description | Accept/Reject/Response | Reviewer | Comments/Reasons | Document Incorporated | Original Requirements

## MMS
Number | Issuing Entity | Name | Page Number | Description | Accept/Reject/Response | Reviewer | Comments/Reasons | Document Incorporated | Original Requirements
| TXU | Mr. Spangler | p. 8 § 1.3.4 | ERCOT will notify the market of any decisions regarding the impact upon | Rejected | jsha | The intent of the original language is to articulate a Document Assumption regarding the systemic implications of the DAM. The replaced language appears to be a requirement that Operations would notify the Market upon the inability to execute the DAM Ancillary Service, not a Business Requirement applicable to Settlements and Billing. | ??? | DAM AS
| Reliant | Wagner | p 47 | Additional Comments: The AABP calculation process needs to adhere to §6.4.2.2, §6.6.5.1(2), and §6.6.5.1(3). For example (but not limited to), the AABP should equal zero for a 15-minute settlement interval where the Resource’s BP deviation is in a direction that contributes to frequency correction that resolves an ERCOT System frequency deviation and the ERCOT System frequency deviation is greater than ±0.05 Hz at any point during the 15-minute settlement interval. [Reliant: is this charge cross checked with the operating system? How will the validation of this work?] | Response | jsha | Settlements is anticipating that this check will take place on the Operation's Side, given that the relavent information is available on that side of the business. | ??? | RT ENERGY
| LCRA | Bascom | p 42 | Added a requirement for calculation of AABP | Rejected | jsha | Settlements intentionally left that calculation out of the Settlements Business Requirements. The purpose of the Assumptions is to delineate that this calculation process should occur on the EMS / LFC side of the Business given they have the data and the system structure to perform the calculation. The Settlement System does not have the capability to handle this type of data or calculation process, and in an effort to minimize the build of new system structures when an existing system had the capability seemed redundant. Concomitantly, Settlements wants to keep the Interface Structure streamlined to enhance transparency and validation processes. | ??? | RT ENERGY
| LCRA | Bascom | p 46 | Added BP, TLMP, TWAR, ARI, ATG, and HSL to the Input Bill Determinants table. | Rejected | jsha | Settlements intentionally left that calculation out of the Settlements Business Requirements. The purpose of the Assumptions is to delineate that this calculation process should occur on the EMS / LFC side of the Business given they have the data and the system structure to perform the calculation. The Settlement System does not have the capability to handle this type of data or calculation process, and in an effort to minimize the build of new system structures when an existing system had the capability seemed redundant. Concomitantly, Settlements wants to keep the Interface Structure streamlined to enhance transparency and validation processes. | ??? | RT ENERGY
| LCRA | Bascom | p 48 FR 97 | Added BP, TLMP, TWAR, ARI, ATG, and HSL to the requirement. | Rejected | jsha | Settlements intentionally left that calculation out of the Settlements Business Requirements. The purpose of the Assumptions is to delineate that this calculation process should occur on the EMS / LFC side of the Business given they have the data and the system structure to perform the calculation. The Settlement System does not have the capability to handle this type of data or calculation process, and in an effort to minimize the build of new system structures when an existing system had the capability seemed redundant. Concomitantly, Settlements wants to keep the Interface Structure streamlined to enhance transparency and validation processes. | ??? | RT ENERGY
| LCRA | Bascom | p 49 FR 99 | Added BP, TLMP, TWAR, ARI, ATG, and HSL to the requirement. | Rejected | jsha | Settlements intentionally left that calculation out of the Settlements Business Requirements. The purpose of the Assumptions is to delineate that this calculation process should occur on the EMS / LFC side of the Business given they have the data and the system structure to perform the calculation. The Settlement System does not have the capability to handle this type of data or calculation process, and in an effort to minimize the build of new system structures when an existing system had the capability seemed redundant. Concomitantly, Settlements wants to keep the Interface Structure streamlined to enhance transparency and validation processes. | ??? | RT ENERGY
| TXU | Durrwachter | p 45 | (BPD) Comment:: Does this section need to include the variable TWAR cited in Nodal Protocol Section 6.6.5?) | Rejected | jsha | Settlements intentionally left that calculation out of the Settlements Business Requirements. The purpose of the Assumptions is to delineate that this calculation process should occur on the EMS / LFC side of the Business given they have the data and the system structure to perform the calculation. The Settlement System does not have the capability to handle this type of data or calculation process, and in an effort to minimize the build of new system structures when an existing system had the capability seemed redundant. Concomitantly, Settlements wants to keep the Interface Structure streamlined to enhance transparency and validation processes. | ??? | RT ENERGY

## CRR
Number | Issuing Entity | Name | Page Number | Description | Accept/Reject/Response | Reviewer | Comments/Reasons | Document Incorporated | Original Requirements

## CS
Number | Issuing Entity | Name | Page Number | Description | Accept/Reject/Response | Reviewer | Comments/Reasons | Document Incorporated | Original Requirements
1 | TXU | Mr. Spangler | p. 40 § 3.8 | DESCRIBE THE IMPACT OF RESETTLEMENT TO TRUE-UP ANCILLARY SERVICE OBLIGATIONS/RESPONSIBILITITES BASED ON REAL-TIME LOAD (REFER TO Section 4.2.1.2). | Rejected | rc / jsha | Resettlement of the Ancillary Service Obligations/Responsibilities occurs in the Real-Time Supplemental Ancillary Services Market and will be addressed accordingly in the document that covers that calculation process. | Real time AS requirements | DAM AS
2 | Reliant | Ms. Wagner | p. 8 § 1.2.4 | … we may be able to build off of these documents for AP settlement. | Rejected | jsha | Issues surrounding other Charge Types will be handled within the Business Requierements for that Charge Type. | Real time AS requirements | DAM AS
3 | Reliant | Ms. Wagner | p. 9 | Will the Market Identifier be the Date of the DAM or the Date of the Operating Day for which the DAM was run? | Rejected | jsha | Undecided, ultimately ERCOT has decided that this is a design issue, and will be reflected in the Conceptual System Design document when further information will allow ERCOT to make a more informed decision. | DAM AS Design | DAM AS
4 | Reliant | Ms. Wagner | p. 11 A1 and Through Out the Document | … wouldn’t the substitution occur in the Settlement System, rather than through the MMS? | Rejected | jsha | ERCOT is anticipating strengthening its abilitity to determine Settlements' Related Issues sooner in the process rather than later. As a part of that effort ERCOT is evaluating many validation tools for the Interface between the Operations and the Settlement systems. In order to have consistent validation of existance of prices coming through the Interface, Operations will need to have provided all available data prior to a Lodestar Decision Making process is available. As such, ERCOT believes Operations will be able to provide the data as outlined in the Assumption. ERCOT currently is concerned that there may be more risk associated with Settlements determining the appropriate price versus Operations. If through the course of discovery, Operations is unable to comply, this assumption will be modified and appropriate changes will be made at that time. | Interfaces or statements | DAM AS
5 | Reliant | Ms. Wagner | p. 11 A2 and Through Out the Document | … and that settlement of all other processes could proceed if this value were missing. Is this the case? | Response | jsha | Yes, that intent of the statement is to allow the continuation of the non-interelated Charge Types to continue. The requested overall architecture is forth coming. | Kenneth's CS Schedule | DAM AS
6 | Reliant | Ms. Wagner | p. 22 B and Throug Out the Document | This doesn’t seem possible. ERCOT assigns the obligation in the DA at 0600. | Response | jsha | This document is intended to only address the settlement calculations associated with the Day Ahead Market for Ancillary Services. Accordingly, the Day-Ahead Net Obligation Quantity necessary for Day-Ahead Settlement Calculations is determined by Operations at 0600 and is calculated using Historical Load Ratio Share data. The Supplemental Ancillary Services Document will address the settlement of Ancillary Services in the Real-Time Market. As such, ERCOT will calculate a Net Obligation for the Real-Time settlement statement using actual load data from the Operating Day. Ultimately, the Net Obligation settled in the Real-Time Market will sometimes be greater or lesser than the Net Obligation settled in the Day-Ahead Market. | Real time AS requirements | DAM AS
7 | TXU | Spangler | p. 5, p.6, p.20 | Commenter Note: This document is extremely confusing with regard to the treatment of PTP obligations purchased in the DAM. I believe that the following is true with regard to PTP Obligations purchased in the DAM: 1. PTP Obligations clear in the DAM at the shadow price as determined by the DAM optimization engine. Consequently, the CRR Account Holder that has bid for a CRR and who is awarded the instrument pays ERCOT an amount as determined by the shadow price (which for these obligations is the difference between the source and sink DASPP) for the PTP Obligation as bid times the MW amount of PTP Obligations awarded in the DAM. 2. PTP Obligations bought in the DAM are settled in Real Time at the RTSPP difference between the source and sink nodes. This may result in a charge or payment to the CRR Account Holder that owns the instrument. (7.9.2.1) 3. At the moment we are thinking that the amounts paid to ERCOT for PTP Obligations purchased in the DAM should contribute to the DAM Congestion Rent Calculation described in Section 7.9.3.1. 4. In addition, CRRs previously purchased in the Annual and Monthly CRR Auctions (Options, Obligations and Flowgate Rights) may be offered for sale by the CRR Account Holder. The purchase price payable to the CRR Account Holder is the clearing price as determined by the DAM optimization engine times the MW amount of the CRR offers struck. These amounts result in a payment to the CRR Account Holder and these payments contribute to the DAM congestion rent calculation described in Section 7.9.3.1. These transactions and separate and distinct from the PTP Obligations purchased in the DAM and discussed in 1 and 2 above | Response | KR / RC / MB | -This requirements document will be renamed to reflect that it covers more than Day-Ahead Energy settlements. - ERCOT will publish a master list identifying the requirements documents that support Nodal settlements and the specific charge types and other calculations covered by each document. - The "Settlement for PTP Obligations Bought in DAM" charge type was not included in the CRR Settlements documentation because those calculations are performed by CRR Owner, rather than QSE. - All CRR Settlements that are calculated by CRR Owner and included on the DAM Statement are documented in a different requirements document. - All CRR Settlements that are calculated by CRR Owner and included on the RTM Statement are documented in a different requriements document. - Shadow Price is not used by the Charge Types documented in this requirements document. The requirements document that addresses the Charge Types that use the Shadow Price will provide details around the calculation of the Shadow Price. | -Kenneths CS Schedule -DA and RT CRR Settlements Requirements | DAM Energy
8 |  |  |  | Finally, the document’s name should be revised to reflect that it addresses both energy settled in the DAM and congestion related settlement amounts. Please consider organizing all billing calculations related to CRR purchase, settlement payoff and congestion rent banking in a unique Business Requirements Document
9 |  |  |  | Commenter Note: Please consider the addition of a protocol reference to all calculation input level data values (boxes) and an indication of the units of the value (i.e. MWH or $/MWH etc.). Similarly, consider the addition of units for the end level of the calculation shown.
10 |  |  |  | Commenter Note: All of the remaining sections, while correctly implementing a settlement formula, seem conceptually incorrect. (see the commenter note at the end of Section 1.1 above) in their treatment of CRR purchase settlement and payout settlement. When I use the term purchase settlement, I am referring to a purchase price determined on the basis of a shadow price computed in an optimization engine. And when I use the term payout settlement, I am referring to the payment or charge made to the CRR Account Holder that is based on the SPP difference between the instrument’s source and sink points. The application of these concepts seem muddled in the following
11 | PUC | Siddiqi | p.12 A3 | What happens to CRR settlement? Should the system be designed so that it can settle all CRRs in RT if needed? | Rejected | MB | This is currently an open question. Once the solution is determined, this will be incorporated into the CRR Settlements requirements document. | DA CRR Settlements & RT CRR Settlements Requirements | DAM Energy
12 | Reliant | Wagner | p. 6 | Reliant: in general, we will need information on how missing data will be handled. Potentially columnar data could include the column header and some indication that the column is not populated. But how will missing rows be indicated? If ERCOT could comment generally on the plan for missing data it would be helpful. | Response | MB | - In general, all missing data / null data business errors or assumptions in the Charge Type requirements documentation are intended for internal use by the ERCOT Settlement System and ERCOT Settlement Analysts to allow for complete processing of an Operating Day. The errors that are captured within the Charge Type requirements documentation are not intended for distribution to the market participants. (However, it is possible that after review of an error, depending upon the nature of the error, it may prompt communication to the market.) - The method by which null values are communicated to the market in the data extracts will be addressed by the requirements for the Settlements data extracts. Keep in mind that the Settlement System cannot store null values for any interval; it must store something in place of a null value. Therefore, the extracts should not contain nulls (the data extract requirements can clarify this point.) | Data Extracts Requirements
13 | Reliant | Wagner | p. 16 A3, p. 20 A3 | p. 16: A3) When creating the DAES data cut for a Settlement Point, the interface will substitute a 0 value for a null value only if at least one interval within the Operating Day has a non-zero quantity for that Settlement Point. If there are no intervals with a non-zero quantity for the entire Operating Day, then the interface will not create a DAES data cut for that Settlement Point. (Reliant Comment—the data sets provided in extracts and posted to the web need to indicate with column headers coupled with a null character ---or via some other mechanism—so that Market Participant systems know not to ‘look further’ for data to populate these data cuts in their systems.) p. 20: (Please see Applicable Reliant Comment above) | Response | MB | Generally speaking, - The ERCOT Settlement System uses "interval data cuts;" these data cuts have all of the Operating Day's interval values "together;" they are not in individual columns. (The data extracts, however, contain the interval data in individual columns. Requirements for the settlements extracts are in a separate requirements document.) - Because the interval data is all stored "together", every interval must have a value; the system cannot store a null value in any interval. Therefore, if a value exists for at least one interval in an Operating Day, the entire interval data cut must be created for that data element. The intervals that did not originally have a value cannot remain null, therefore they are populated with a zero value. - ERCOT plans to define one or more data elements to act as the "driver" of a Charge Type calculation. If an interval data cut exists for the driver data element(s) for a given Operating Day/QSE/Resource/Settlement Point, for example, the Settlement System will execute the Charge Type Calculation for that Operating Day/ QSE/Resource/Settlement Point. If an interval data cut does not exist for the driver data element(s) for the Operating Day/QSE/Resource/Settlement Point, the System will not execute that Charge Type for that Operating Day/QSE/Resource/Settlement Point. (A result of this logic is that processing time is not spent on something that is known to result in a zero data cut, and the zero data cuts are not created, stored, and sent in the extracts.) - The data interface between the source system and the Settlement System is responsible for creating the interval data cuts. Therefore, in this document, only assumptions can be made about when an interval data cut should be created and how "missing values" will be handled within that interval data cut. | Data Interface Requirements
14 | Reliant | Wagner | p. 13 | The original source system for the Settlement Point Prices will maintain a history of the prices. Therefore, if a DASPP is corrected after a settlement run, the price that was used for the settlement run is still available. [Reliant Comment—it is not clear that the RT Market Engine will be keeping historical prices. It may be the case that the RT market engine runs and the prices are saved off to a DB/archive…we should strive to have a clear understanding of the interfaces and where potential price corrections exist.] | Response | MB | Agreed. The design process will address exactly where a historical price can be accessed, when it will be archived, etc. Additionally, there will be interface requirements that address how the price is interfaced into the Settlement System. | Data Interface Requirements/Design and Design for MMS
15 | Reliant | Wagner | p. 13 | Reliant: What is the explicit nomenclature for Shadow Price? We may need this if we keep the TXU comments? | Response | MB | Shadow Price is not used by the Charge Types documented in this requirements document. The requirements document that addresses the Charge Types that use the Shadow Price will provide this detail. (Per the Protocols, the Shadow Price is used when calculating the DA and RT "INFO" price cuts for PTP Options. Therefore the requirements that address settlement of PTP Options will discuss the "INFO" price and the Shadow Price used to obtain that "INFO" price. The Settlement for PTP Obligations Bought in DAM Charge Type does not utilize a Shadow Price.) | DA CRR Settlements & RT CRR Settlements Requirements | DAM Energy
16 | Reliant | Wagner | p. 16 FR7, p. 20 FR16, p. 25 FR25, p. 28 FR32, p. 33 FR48 | p. 16Reliant: do we need volumes by Settlement Point?, I.e. total DAES by SP by hour? Same for purchases. p. 20: Please see comments above p. 25: (Reliant: do we need volumes, by SP, per hour as well?) p. 28: Reliant: Do we need volumes as well? Or is this the comment in yellow immediately above? p. 33: Reliant: do we need total volumes by SP by hour? | Response | MB | - If bill determinants are desired to represent the aggregation of a data element to the market level by Settlement Point, it needs to be included in the Protocols. The current aggregations identified in the Protocols are just to the market level. - The comment highlighed in yellow is actually in reference to a price and is related a concern about publishing the price to the market. | Raj - I'm not sure where this goes? Possibly that committee deciding on MIS outputs? Do we need to include this item in this list???
17 | Reliant | Wagner | p. 17 FR9, p. 20 FR 17 | p. 17: Reliant: The missing data element should have some type of indicator in the data provided for Market Participants—so that their systems populate correctly. p. 21: Please see comments above regarding missing data | Response | MB | A separate requirements document will address how the data is published in the data extracts. (See comments above.) | Data Extracts Requirements
18 | Reliant | Wagner | p. 17 | —Reliant: do we need any type of tracking for potential revisions---for example if a price is posted immediately after RT, but is changed by ERCOT by 1000 the next day when prices are final—do we need something in the DB to indicate this? | Response | MB | If an indicator of a price correction is required, it needs to be included in the Protocols. | Raj - I'm not sure where this goes? Possibly that committee deciding on MIS outputs? Do we need to include this item in this list???
19 | Reliant | Wagner | p. 13 | If ERCOT is unable to execute the Day-Ahead process, ERCOT may abort all or part of the Day-Ahead process and require all schedules and trades to be submitted in the Adjustment Period. (PR 4.1.2 (2)) If such an Emergency Condition occurs, Day-Ahead Energy settlements may not be necessary. (The Settlement system should provide notice to this effect on Settlement Statements—so that a clear history is maintained of any market exceptions of this type. For example, when the Settlement System does not receive expected data from the market system, it should trigger some type of exception reporting that flows to the settlement statements.) | Response | MB | This is a good suggestion and will be relayed to the team working on Settlement Statements. | Settlement Statement Requirements
20 | TXU | Mr. Spangler | p. 10 | {How will the market identifier be structured? For example date and interval stamped? Is <M> actually carried or inferred by variables such as RUSQ (refer to A4 on page 37 for instance)?} | Response | jsha | Initially ERCOT had considered including a specific nomenclature requirements, but ultimately decided that this is a part of Design. As such this will be reflected in the Conceptual System Design. | RT AS Design | RT AS
21 | Reliant | Ms. Wagner | p.12 FR8 | (Reliant: Does the indicator need to be alphanumeric—something like M1 or SASM1?) | Response | jsha | Initially ERCOT had considered including a specific nomenclature requirements, but ultimately decided that this is a part of Design. As such this will be reflected in the Conceptual System Design. | RT AS Design | RT AS
22 | Reliant | Ms. Wagner | p.15 FR8 | (Reliant: Does the indicator need to be alphanumeric—something like M1 or SASM1?) | Response | jsha | Initially ERCOT had considered including a specific nomenclature requirements, but ultimately decided that this is a part of Design. As such this will be reflected in the Conceptual System Design. | RT AS Design | RT AS
23 | Reliant | Ms. Wagner | p.18 FR8 | (Reliant: Does the indicator need to be alphanumeric—something like M1 or SASM1?) | Response | jsha | Initially ERCOT had considered including a specific nomenclature requirements, but ultimately decided that this is a part of Design. As such this will be reflected in the Conceptual System Design. | RT AS Design | RT AS
24 | Reliant | Ms. Wagner | p.21 FR8 | (Reliant: Does the indicator need to be alphanumeric—something like M1 or SASM1?) | Response | jsha | Initially ERCOT had considered including a specific nomenclature requirements, but ultimately decided that this is a part of Design. As such this will be reflected in the Conceptual System Design. | RT AS Design | RT AS
25 | Reliant | Ms. Wagner | p. 67 | Daylight Savings Time shall be recognized in Nodal Market settlements. | Response | jsha | This should be addressed within the Conceptual System Design. | RT AS Design | RT AS
26 | Reliant | Wagner | p 49 A2 | The Original Source system should only make available, or appropriately flag, AABP data, as a 15-minute weighted average value across all of the SCED intervals during the 15-minute settlement interval, for Resources that are required to pay a Base Point Deviation, as defined by the ERCOT Nodal Protocols. Essentially, the Original Source system should not propagate AABP data for any RMR Units [Reliant---disagree with this approach---see suggestion below—this should be propagated---perhaps the interface should validate and not propagate for Resources that fail validation…], Dynamically Scheduled Resources (except as described in §6.4.2.2 of the Nodal Protocols,) Qualifying Facilities that do not submit an Energy Offer Curve for the Settlement Interval, or Generation Resources which meet the specified exclusions laid out in §6.6.5 (e.g. violation of Resource Parameters), §6.6.5.1(2), and §6.6.5.1(3) of the Nodal Protocols. | Response | Raldridge | This will be addressed in the interface requirements. | Interface Requirements Document | RT AS
27 |  |  |  | The Interface shall appropriately evaluate and propagate data from the original source system in a fashion to create an AABP interval data cut for an entire day, substituting zeros for the intervals that have null values. As such, the Settlement System will settle based upon any AABP data created, or flagged appropriately, by the original source system. [Reliant: should be designed so that the calculation is done for every Resource—with a validation that propagates the values only for resruces that are not self scheduled or not RM, or not QFs…----because the universe of these changes---but the Resource universe itself is much more stable.] | Response | Raldridge | This will be addressed in the interface requirements. | Interface Requirements Document | RT AS
28 | Reliant | Wagner | p 7 | Is there a design document for the Data Agg system? | Response | M Bauld | Yes, there is a Data Agg requirements document that will address the needs for calculation of AML, LRS, etc. Currently it is scheduled to go to TPTF in October 2006. | Data Aggergation Requirements Document | RT Energy
29 | Reliant | Wagner | p 10, FR 10 | (RTEIAMT) Reliant: At times a Resource could be a net load, this is handled by the net amount (before * by -1) being negative, right? This could occur if RTMG is negative—does the convention for this term allow it to be negative? If not, do we need the RTAML term in this equation? | Response | M Bauld | All modification to the RT Energy requirements document to handle net metering will be incorporated through a change request. | RT Energy Addendum (initiated by a Change Request) | RT Energy
30 | Reliant | Wagner | p 25 A2 | MMS will have the appropriate values for RTDCIMP. If the DC Tie Schedule flows as planned [Reliant: where will the validation of ‘flow as planned’ occur, and what is the validation metric? What is the business process and link of this tie meter cross check to settlement data? These questions apply to similar statements about DC tie flows throughout this document.], then ERCOT shall use schedules as the deemed meter readings for Real-Time settlement. If the interconnected non-ERCOT Control Area schedule changes during the Operating Period, then ERCOT shall use the changed interconnected non-ERCOT Control Area schedule as the deemed meter reading for Real-Time settlement. (PR 4.4.4.2 (2)) If the DC Tie Schedule for import flows as planned, then the actual data from MMS will be the original schedule. If the schedule changed during the Operating Period, then the value from MMS will be the altered schedule. | Response | M Bauld | The assumption is that MMS will provide the appropriate value to the settlements system. The settlement system will nto be responsible for validating the "flow as planned." | MMS Requirements Document | RT Energy
31 | Reliant | Wagner | p 36 A4 | A DC Tie Schedule must be transaction-specific, i.e., one schedule per transaction per DC Tie, rather than aggregate (net) schedules per DC Tie. (PR 4.4.4 (1)) When the interface system creates the RTDCEXP data cut it will aggregate all of the individual import transactions for the QSE, DC Tie, and Operating Day by 15-minute interval. [Reliant: will the interface system net the DC Tie schedules by QSE?] | Response | M Bauld | The interface will keep all of a QSE's exports and imports at a DC Tie separate - it will not net them. The interface will get the total of all of the exempt export transactions and run it through the exempt export charge; liekwise, it will get the total of all import transactions at the DC Tie and run it through the import payment. | Interface Requriements | RT Energy
32 | Reliant | Wagner | p 47 | Additional Comments: The AABP calculation process needs to adhere to §6.4.2.2, §6.6.5.1(2), and §6.6.5.1(3). For example (but not limited to), the AABP should equal zero for a 15-minute settlement interval where the Resource’s BP deviation is in a direction that contributes to frequency correction that resolves an ERCOT System frequency deviation and the ERCOT System frequency deviation is greater than ±0.05 Hz at any point during the 15-minute settlement interval. [Reliant: is this charge cross checked with the operating system? How will the validation of this work?] | Response | JSHAdams | Settlements is anticipating that this check will take place on the Operation's Side, given that the relavent information is available on that side of the business. | EMS or MMS Requiremetns | RT Energy
33 | Reliant | Wagner | p 61 | (ESACAMT) [Reliant: given the recent PUCT decision to allocate the nodal interim surcharge on generation ratio share, ERCOT may want to configure this part of the new settlement system to allow for more flexible allocation of ERCOT fees.] | Response | M Bauld | When the NPRR for the Nodal Surcharge is approved, it will be incorporated as a new Charge Type (most likely through a change request.) and included in the RT Energy requirements document. | RT Energy Addendum (initiated by a Change Request) | RT Energy
34 | Reliant | Wagner | p 64 | 4. [Reliant: will all validation occur in the interface?] | Response | M Bauld | Where and how the validation will occur will be determined and documented in the design phase. Some of the validation may occur in the interface, some of it may occur as a "pre-processor" in the Settlement system, and there may also be some additional manual validation of certain elements prior to execution. All of these details are being worked out as part of design. | Interface Requriements | RT Energy
35 | LCRA | Bascom | p 42 | Added a requirement for calculation of AABP | Rejected | JSHAdams | Settlements intentionally left that calculation out of the Settlements Business Requirements. The purpose of the Assumptions is to delineate that this calculation process should occur on the EMS / LFC side of the Business given they have the data and the system structure to perform the calculation. The Settlement System does not have the capability to handle this type of data or calculation process, and in an effort to minimize the build of new system structures when an existing system had the capability seemed redundant. Concomitantly, Settlements wants to keep the Interface Structure streamlined to enhance transparency and validation processes. | EMS / LFC Requirements | RT Energy
36 | TXU | Spangler | p. 6 | 1. The dependencies show that the DAMWELIGFLAG is generated in the Settlement System. While this can be done it may be that generating this flag in the EMS/MMS and passing it to Settlement is a better approach. | Response | mb | The eligibility evaluation process is currently under discussion at TPTF. The eligibility process will be documented in its own Business Requirements, TN.COMS.63C01.STARTUPELIGIBILITY.REQUIREMENTS.A. | Eligibility Requirements | DA Make-Whole Settlements
37 | TXU | Spangler | p. 6 | 2. The DAMWELIGFLAG flag determines whether or not a DAM committed unit’s guaranteed payment includes the startup part of its three part offer and whether or not the unit is eligible for a Make-Whole payment. The DAMWELIGFLAG must be set at some time during any hour during which a DAM committed unit is eligible for a make-whole payment. | Response | mb | The eligibility evaluation process is currently under discussion at TPTF. The eligibility process will be documented in its own Business Requirements, TN.COMS.63C01.STARTUPELIGIBILITY.REQUIREMENTS.A. | Eligibility Requirements | DA Make-Whole Settlements
38 | TXU | Spangler | p. 6 | 3. A DAM committed unit is deemed to have started-up to meet a DAM commitment if its output breaker status reflects a change from an off-line resource status (refer to 3.9.1(4)(b)(ii) to a synchronized resource status (refer to 3.9.1(4)(b)(i). This change in status can occur at any time during the adjustment period and will be reflected in real-time data and not the responsible QSE’s COP. | Response | mb | The eligibility evaluation process is currently under discussion at TPTF. The eligibility process will be documented in its own Business Requirements, TN.COMS.63C01.STARTUPELIGIBILITY.REQUIREMENTS.A. | Eligibility Requirements | DA Make-Whole Settlements
39 | TXU | Spangler | p. 6 | 4. The DAMWELIGFLAG can only be set if the resource status change from off-line to synchronize occurs after an elapse time of at least 5 minutes from the last time the DAMWELIGFLAG flag was in the cleared state. The DAMWELIGFLAG should be cleared immediately upon a status change from synchronized to off-line. | Response | mb | The eligibility evaluation process is currently under discussion at TPTF. The eligibility process will be documented in its own Business Requirements, TN.COMS.63C01.STARTUPELIGIBILITY.REQUIREMENTS.A. | Eligibility Requirements | DA Make-Whole Settlements
40 | TXU | Spangler | p. 6 | 5. The adjustment period runs from 1800 hours in the Day-ahead to one hour prior to the start of the operating hour. | Response | mb | The eligibility evaluation process is currently under discussion at TPTF. The eligibility process will be documented in its own Business Requirements, TN.COMS.63C01.STARTUPELIGIBILITY.REQUIREMENTS.A. | Eligibility Requirements | DA Make-Whole Settlements
41 | TXU | Spangler | p. 6 | 6. EMS/MMS has access to all of the data inputs necessary to determine the state of the DAMWELIGFLAG flag. We suggest that either EMS or MMS be responsible for the state of the flag and that the flag state be provided to Settlement its use. This flag must be examined for each committed hour to complete the settlement calculation. | Response | mb | The eligibility evaluation process is currently under discussion at TPTF. The eligibility process will be documented in its own Business Requirements, TN.COMS.63C01.STARTUPELIGIBILITY.REQUIREMENTS.A. | Eligibility Requirements | DA Make-Whole Settlements
42 | TXU | Spangler | p. 6 | 7. The DAMWELIGFLAG is required for the level 1 DAMGCOST calculation, to determine the need to include the startup cost {not currently shown} in addition to the level 2 DAMWAMT calculation {as currently shown}. | Response | mb | -The eligibility evaluation process is currently under discussion at TPTF. The eligibility process will be documented in its own Business Requirements, TN.COMS.63C01.STARTUPELIGIBILITY.REQUIREMENTS.A. - Based upon the outcome of the Eligibility discussions at TPTF, the diagram may need to change to reflect a different application of the DAMWELIGFLAG. The eligibility flag may need to be applied to the DAMGCOST calculation. | Eligibility Requirements | DA Make-Whole Settlements
43 | TXU | Spangler | p. 6 | 8. Some other factors that may need consideration with regard to Make-whole logic: If the DAM committed unit starts-up during the adjustment period in anticipation of being on-line at the start of its DAM commitment obligation but goes off-line any time after the start, it is eligible in guaranteed amount for the start-up portion of its 3-part offer. Whether or not it is eligible for minimum energy in the guaranteed amount is dependent on whether or not the unit was synchronized during a committed hour. Whether minimum energy is paid for the entire hour or a pro ratio of the hour in which a synchronized to off-line status change occurs remains to be resolved. A good faith effort to start-up that fails the 5 min. criteria may still be eligible in it’s guaranteed amount for all or a portion of the start-up part of its three part offer if the resource requests such from ERCOT and ERCOT agrees. The foregoing points are not explicitly stated in protocols but we believe they were intended during TNT discussions of make-whole. | Response | mb | The eligibility evaluation process is currently under discussion at TPTF. The eligibility process will be documented in its own Business Requirements, TN.COMS.63C01.STARTUPELIGIBILITY.REQUIREMENTS.A. | Eligibility Requirements | DA Make-Whole Settlements
44 | TXU | Spangler | p. 12 | STARTTYPE {where does this value originate?} | Response | mb | It is planned that this value will be an output from the eligibility process (most likely within settlements, but as a preprocessor to the settlements process.) | Eligibility Requirements | DA Make-Whole Settlements
45 | TXU | Spangler | p. 13 | MEO - Note: while only one start-up is eligible for the guaranteed amount in each DAM; Minimum energy is eligible for the guaranteed amount and can be the basis for a make-whole payment in all DAM commitment blocks ffor each resource, provided the resource is in a synchronous status during the DAM commitment hour. | Response | mb | The eligibility evaluation process is currently under discussion at TPTF. The eligibility process will be documented in its own Business Requirements, TN.COMS.63C01.STARTUPELIGIBILITY.REQUIREMENTS.A. | Eligibility Requirements | DA Make-Whole Settlements
46 | NRG | Mai | p. 8 | 4. EMS may need to keep track of the number of starts, and the Start Type of each, for each DAM-committed resource for the day-ahead, for Settlement use. | Response | mb | EMS will provide breaker status data for tracking eligibility. At this point, it has been assumed that the Settlement System will use that data along with resource parameter data to determine the appropriate start type. | EMS/LFC Requirements | DA Make-Whole Settlements
47 | NRG | Mai | p. 8 | 5. The hourly DAMWELIGFLAG may be maintained internally by Settlement, but input data come from the EMS. A process is needed to assure consistency between Settlement and EMS, and between Settlement and QSEs in case EMS data is not available. | Response | mb | The eligibility evaluation process is currently under discussion at TPTF. The eligibility process will be documented in its own Business Requirements, TN.COMS.63C01.STARTUPELIGIBILITY.REQUIREMENTS.A. | Eligibility Requirements | DA Make-Whole Settlements
48 | Reliant | Wagner | p. 36 A5 and extract comments throughout the doc | • DAWASF [Reliant: Seems like this should be public data for each constraint that affects a particular Source Sink Pair] • DASP [Reliant: Seems like this should be public data for each constraint that affects a particular Source Sink Pair] | Response | KR & SQ & SW | We would like TPTF to clarify as to if these two bill determinants should be made public. (Per TPTF, "data extracts" business rqmts will need to clarify what goes to "public extract" and what goes "private extract".) TN.COMS.63C01.DAMCRR.REQUIREMENTS.A. | Data Extracts Requirements | DAM CRR Settlements
49 | TPTF |  |  | Settlement Statement Issues |  | kh | Remanded to COPS to resolve open issues | Settlement Statements | Settlement Statements
50 | TPTF |  |  | Settlement Invoice Issues |  | kh | Remanded to COPS to resolve open issues | Settlement Invoices | Settlement Invoices
51 | TPTF |  |  | Financial Transfer Issues |  | kh | Remanded to COPS to resolve open issues | Financial Transfer | Financial Transfer
52 | GP&L | R. Hoeinghaus | p. 7 | Comment: Add Variable Definitions for following variables: EBP, EBPPR, & TLMP as found in Protocol 6.6.9.1 | Rejected - Move to Punchlist | M. Bauld | - The Settlement System will not receive these bill determinants and use them as an input into a Settlement System calculation, therefore they are not defined as Input Bill Determinants. - A data element is only listed in the Input Bill Determinants if it literally is used by a calculation that is occurring within the Settlement System. - As noted on the Base Point Deviation Charge Types, the Settlement System can't handle data that does not use a consistent time interval - The Settlement System will receive AEBP and EBPWAPR, already calculated and at the 15-minute level. - EBP, EBPPR, and TLMP varaibles/calculations should be documented by the system responsible for calculating AEBP and EBPWAPR. Please note that this will be added to the punchlist and may still be under negotiations with the identified source systems (EMS and MMS). If after negotiations EMSand MMS are not the source for this data, the calculations should be documented by whatever system ends up performing the calculation. | EMS and MMS | Emergency Operations
53 | LCRA | F. Bryan | p7 Added FR6 | Addition of a requirement to capture the calculation of AEBP. | Rejected - Move to Punchlist | M. Bauld | - The AEBP calculation is not defined within this requirements document because calculation of this value is not a requirement of the Settlement System - Currently, it is assumed that EMS will calculate and provide this data. As an input from EMS, this should be included in the EMS requirements. Please note that this will be added to the punchlist and may still be under negotiations with the identified source system (EMS). If after negotiations EMS is not the source for this data element, the AEBP calculation should be documented by whatever system ends up performing the calculation. - See response to #2 | EMS | Emergency Operations
54 | Reliant | M. Wagner | p. 8 | (AEBP) [Reliant---why wouldn’t this be done in Settlements? EMS will send the signals out, and these instructions will flow to settlements….so we need the “time” at the LMP---which is a function that is always needed in settlements---given that ERCOT has the obligation to kick off a SCED run upon any significant system change---inherently the ‘time at the LMP’ is generally 5 minutes, but it could be a shorter period or a longer period and the Settlements system will need to accommodate this flexibility. This appears to be captured in A3 below---and we don’t see the conditions here being much different.] | Response - Move to Punchlist | M. Bauld | -The goal is to treat the Emergency Base Point in the same manner as the Base Point. The Settlement System will not receive the EBP in inconsistent intervals. The Settlement System will reveive the time-weighted average of the EBP in the 15-minute interval. -A3) addresses this exact requirement/assumption - the Settlement System will not deal with EBP. EMS will calcualte AEBP as the time-weighted average across all of the SCED intervals during the 15-minute settlement interval. | EMS | Emergency Operations

## EDW
Number | Issuing Entity | Name | Page Number | Description | Accept/Reject/Response | Reviewer | Comments/Reasons | Document Incorporated | Original Requirements

## Integration
Number | Issuing Entity | Name | Page Number | Description | Accept/Reject/Response | Reviewer | Comments/Reasons | Document Incorporated | Original Requirements

## MIS
Number | Issuing Entity | Name | Page Number | Description | Accept/Reject/Response | Reviewer | Comments/Reasons | Document Incorporated | Original Requirements
| TXU | Mr. Spangler | p. 41 § 3.9 | SPECIFY HOW THE BUSINESS REQUIREMENTS THAT WILL SPECIFY ERCOT TO MARKET INFORMATION INTERFACE FOR THE MIS AND WEB ACCESS PER SECTION 12 ARE TO BE ADDRESSED. | Rejected | rc / jsha | ERCOT should address these concerns within the Business Requirement Documents regarding the Extracts project and the MIS project. ERCOT will pass along these concerns to the relevant individuals to ensure that they are appropriately handled. | ??? | DAM AS