## Schedule
Draft TPTF Requirements Submission Schedule
Project | Sub-Project | Project Specific Breakdown | Artifact Type | Title | Initial Send to TPTF | Initial Presentation Date | Comments Due from MPs | Review of Comments Received & Likely Vote of Approval
COMS | S&B | RMR Service Settlements | Requirements | RMR Service | 2006-09-07 | 2006-09-12 | 2006-09-20 | 2006-10-10
COMS | S&B | RT CRR Settlements | Requirements | RT CRR Settlements | 2006-09-21 | 2006-09-28 | 2006-10-04 | 2006-10-10
COMS | S&B | CRR Balancing Account | Requirements | CRR Balancing Account, (Includes Credits to Balancing Accounts, Shortfall Charges, Refunds for short paid, CRR Balancing Closure) | 2006-09-21 | 2006-09-28 | 2006-10-04 | 2006-10-10
COMS | S&B | CRR Auction Settlements and Revenue Disbursement | Requirements | CRR Auction Settlement (Includes CRR Auction and CRR Revenue Disbursement) | 2006-09-21 | 2006-09-28 | 2006-10-04 | 2006-10-10
COMS | Credit Monitoring | Credit Monitoring | Requirements | Credit Monitoring | 2006-09-21 | 2006-09-28 | 2006-10-04 | 2006-10-10
COMS | S&B | Settlement Statements | Requirements | Statements | 2006-09-21 | 2006-09-28 | 2006-10-04 | 2006-10-10
COMS | S&B | Invoices | Requirements | Invoices | 2006-09-21 | 2006-09-28 | 2006-10-04 | 2006-10-10
COMS | S&B | Interface Inbound | Requirements | Interfaces, Inbound & Outbound | 2006-10-06 | 2006-10-10 | Propose 10/18/06 | Propose 10/25/06
COMS | Client Relations / S&B | Disputes | Requirements | Disputes | 2006-10-06 | 2006-10-10 | Propose 10/18/06 | Propose 10/25/06
COMS | Financial Transfer | Financial Transfer | Requirements | Financial Transfer | 2006-10-06 | 2006-10-10 | Propose 10/18/06 | Propose 10/25/06
COMS | Registration | Registration | Requirements | Registration | 2006-10-06 | 2006-10-10 | Propose 10/18/06 | Propose 10/25/06
COMS | S&B | Misc Charge Types | Requirements | MISC Charge Types, Misc Charge type adjustments | 2006-10-06 | 2006-10-10 | Propose 10/18/06 | Propose 10/25/06
COMS | Data Agg | AS Obligation calculation | Requirements | Data Aggregation - Including AS Obligation Calculation, Load Profiling, and Metering | 2006-10-18 | 2006-10-25 | 2006-10-27 | Propose 11/7/06
COMS | S&B | AIEC | Requirements | Average Incremental Energy Cost Calculation (AIEC) | 2006-10-18 | 2006-10-25 | 2006-10-27 | Propose 11/7/06
COMS | S&B | Verifiable Costs | Requirements | Verifiable Costs | 2006-10-18 | 2006-10-25 | 2006-10-27 | Propose 11/7/06
COMS | S&B | Start-Up Eligibility | Requirements | Start-Up Eligibility | 2006-10-18 | 2006-10-25 | 2006-10-27 | Propose 11/7/06
COMS |  | Extracts | Requirements | Extracts for Commercial Operations | 2006-10-18 | 2006-10-25 | 2006-10-27 | Propose 11/7/06
CRR |  |  |  | Requirements - 2nd Issue | 2006-10-03 | NA | 2006-10-05 | 2006-10-09
MIS |  |  |  | Requirements | 2006-09-22 | 2006-09-27 | 2006-10-04 | 2006-10-09
EMS |  |  |  | SCADA/ICCP | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | Dynamic Ratings | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | Forced Outage Detection | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | Load Frequency Control | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | Load Forecasting | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | Wind Power Forecasting | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | State Estimator | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | Security Analysis | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | Voltage Scheduler | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | Outage Evaluation | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | EMS System | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
EMS |  |  |  | EMS Data Modeling | 2006-11-27 | 2006-11-28 | 2006-12-06 | TBD
MMS |  |  |  | DAM & SASM | 2006-10-23 | 2006-10-24 | 2006-10-30 | 2006-11-06
MMS |  |  |  | SCED-RT | 2006-10-23 | 2006-10-24 | 2006-10-30 | 2006-11-06
MMS |  |  |  | RUC | 2006-10-23 | 2006-10-24 | 2006-10-30 | 2006-11-06
MMS |  |  |  | CCT | 2006-10-23 | 2006-10-24 | 2006-10-30 | 2006-11-06
MMS |  |  |  | Other | Mon, 10/23/2006 (Tentative) | Tue, 10/24/2006 (Tentative) | Mon, 10/30/2006 (Tentative) | Mon, 11/6/2006 (Tentative)
EDW |  |  |  | IMM Requirements | 2006-10-20 | 2006-10-26 | 2006-11-02 | 2006-11-06
EDW |  |  |  | Compliance Requirements | 2006-10-20 | 2006-10-26 | 2006-11-02 | 2006-11-06
Integration |  |  |  | Requirements | After all other requirements complete | TBD | TBD | TBD