## Open MCT Action Items
Date Opened | Action Item | Resolution | Status | Date Last Updated
August, 2006 | Safety Net Reject Code from TDSP to ERCOT on 814_04 – Change control needed for 814_11? | Catherine Meiners to write TX SET Issue. | Pending | 2006-08-14
September, 2006 | Update MCT Issues Log | Susan Munson to update and bring to October 3 MCT meeting | Still Completing; will post before next MCT | 2006-10-03
October, 2006 | What does "dummy data" on Customer Billing Contact Information File for new CRs look like? Who will provide? Add clarification to Market Requirements Document | ERCOT to bring to October 24 meeting | Pending | 2006-10-03
October, 2006 | Discuss F2, F3, F4 (RMG) - File layouts for Mass Transition ESI ID spreadsheets to POLR CRs. Add POLR Customer Class and Voluntary/Non-Voluntary CR Status | ERCOT to bring to October 24 meeting | Pending | 2006-10-03

## Closed Action Items
Date Opened | Action Item | Resolution | Status | Date Last Updated
August, 2006 | Email box for MCT questions/issues – Post FAQs to MCT website. | Susan Munson to have mailbox set up for MCT questions/issues; Post FAQs to MCT page of ERCOT.com | Closed | 2006-10-03
August, 2006 | Impacts to TML for TX SET 3.0? | ERCOT will report back on TML Changes at next MCT meeting. | Closed | 2006-09-11
September, 2006 | Update Market Requirements document with ERCOT solutions to POLR Rule requirements | ERCOT to redline Market Requirements document; October 3 MCT meeting to review | Closed | 2006-10-03
September, 2006 | Review Test Script Brainstorm list; add new script ideas | All MCT bring ideas to October 3 MCT meeting | Closed | 2006-10-03
September, 2006 | CRs & TDSPs come up with ideas for solution to 650_01 reconnect issue (CR submits standard; CR submits Priority; CR cancels standard; TDSP rejects Priority and cancels standard - how to handle?) | Revisit this issue at October 3 MCT meeting; discuss ideas and "pain points" for all MPs; Discussed at 10/3 meeting - CRs to review their processes; CRs will not get reconnects done faster by submitting priorities; no change control at this time | Closed | 2006-10-03
September, 2006 | Determine acceptable error threshold on Customer Billing Information file validation by ERCOT | Decision at October 3 MCT meeting; decided to set no threshold - ERCOT will handle "one-off situations with CRs" as needed; ERCOT will report to PUCT what was sent by CRs | Closed | 2006-10-03

## Parking Lot Items
Date Opened | Parking Lot Item | Resolution | Status | Date Last Updated