## Slide 1: PR50121_07 Retail Business Processes (RBP) Project Update Retail Market Subcommittee October 11, 2006 Adam Martinez Mgr, Market Operations DPO

## Slide 2: Current Events
Project Status – Currently on target for Schedule, Scope, and budget
Project Phases
  Initiation – Completed 08/01/2005
  Planning – Completed 05/08/2006
  Execution
    Go-Live on 12/10/2006 weekend; Stabilization through 02/09/2007
  Closing – Target to complete February 2007
Recent Activities
  Completed Build for Reprocessing and ETS
  Completed Build for Retail TML (Find ESIID, Find Transaction, Customer Switch)
  Finalize Migration Plan for cut-over weekend
Next Steps
  Continue UAT of Core Components
  Continue Data Conversion activities
  Begin UAT on Reprocessing, ETS, and TML

## Slide 3
Project Milestones
Requirements (pens down) – Completed April 12, 2006
Design (internal document) – Completed July 14, 2006
Build – Completed July 28, 2006 for Core Components
Internal Testing – Target Completion Date of December 1, 2006
Internal Training – Target Completion of November 18, 2006
Production (Go live) – Weekend December 10, 2006 **Code Migration, Data Conversion, and Production Verification

## Slide 4: Testing Status
Testing Schedule
  Transaction Processing: Start 08/28 – 60% complete (approx. 600 scripts)
  Retail TML: Start 10/02 – 0% (approx. 50 scripts)
  Reprocessing: Start 10/02 – 0% (approx. 70 scripts)
  ETS Testing: Start 10/02 – 0% (approx. 60 scripts)
  Load/Performance Testing: Starts 10/30 – 0%
  Monitoring Testing: Starts 10/30 – 0%
Defect Status
  5 currently open
  80 total defects to date. Breakdown:
    Code – 27 Configuration – 14 Environment – 19
    Invalid – 7 Unknown – 13

## Slide 5: SLA exception Migration Weekend
Dates/Time Window Required
  Start: 7:00 AM Friday, 12/08/06
  End: 11:30 PM Sunday, 12/10/06
  Migration window Schedule accommodates Migration, Data Conversion, and Verification activities , and avoid high-volume transaction weekends)
Additional Information – Functions Affected
  Market Participants utilizing NAESB WILL be able to send to ERCOT but will NOT be able to Receive from ERCOT during the outage.
    NAESB will be offline between 8:00AM to 9:00AM Saturday, 12/9/06 for server reboot.
  867 Transactions will NOT be forwarded during the outage.
  997 Functional Acknowledgements will NOT be sent during the outage.
  Cancel/Notification batch exception in the event of a roll-back on 12/10/06
  Retail components of the TML and API will NOT be available including
    - Report Explorer / Search Reports - Find ESI
    - Find Transaction - Submit Transactions
    - USA Functionalities

## Slide 6: SLA exception Migration Weekend (cont)
Data Conversion Load Mitigation
  54 hours to complete
  Reduce the outage to the Market by launching Go-Live with 3-6 months of 2006 descending transactional data (previously stored in Seebeyond TCH Database)
  Phase in remaining years on following weekends. (Low to zero Risk)
  Retail TML and API Find Transaction will be limited to Data Conversion Load
  ETC by late December 31st, 2006 / January 7th, 2007
SLA Exception Approval
  ERCOT requesting approval of exception migration support of this project

## Slide 7: Migration Weekend Timeline

## Slide 8: Questions / Contact
Adam D. Martinez
Mgr, Market Operations
Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Hope Parrish
Project Manager, Market Operations
Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com