## Slide 1: Market Coordination Team Update Retail Market Subcommittee October 11, 2006 Susan Munson Retail Market Liaison

## Slide 2
Project Status
Status:
  On target for schedule, budget, and scope
Project Phases:
  Initiation – Completed
  Planning – Target completion date December 9, 2006
  Execution – Mandated completion date July 1, 2007
  Closing – Target completion is post go-live
Recent Activity:
  ERCOT started internal Conceptual Designs
  MCT developed recommendations for TTPT Script Sub-team Market Testing requirements
Next Steps for MCT:
  Create Production Implementation and Contingency Plans
  Continue to monitor Market issues and progress
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 3
Milestones
Market Requirements (pens down) – Completed August 10, 2006
Design (internal document) – December 9, 2006
Planning Phase Exit – December 9, 2006
Build – Target completion of February 27, 2007*
Internal Testing – Target completion of June 16, 2007*
Market Testing – Target completion of May 29, 2007*
Internal Training – TBD
Production (Go live) – June 24, 2007
* Dates to be confirmed upon Planning Phase exit
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 4: Project Schedule
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 5: Risks / Issues
Issue | Mitigation | Owner
PR50121_07 RBP – Stabilization necessary for successful implementation | Schedule management Milestone completion | ERCOT
PUCT Mandate of 07/01/2007 poses tight timeline | Schedule and resource management Milestone completion | All
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 6
Meeting Dates and Locations through 2006
  October – ERCOT in Austin (10/24)
  November - ERCOT in Austin (11/6)
  December – CenterPoint in Houston (12/11)
(Note: all meetings are held in conjunction with TX SET meetings)
Future Meetings/Market Communications
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 7: ERCOT Contacts
ERCOT Project Manager ERCOT SR. Business Analyst
Hope Satterfield Jennifer Frederick
hsatterfield@ercot.com jfrederick@ercot.com
512-248-6522 (w) 512-248-6733 (w)
512-771-9582 (c) 512-413-0815 (c)
ERCOT Market Liaison
Susan Munson
smunson@ercot.com
512-248-3881 (w)
512-826-0564 (c)
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 8: Voting Item
Implementation Date
  MCT requests RMS approval for the implementation of TX SET V3.0 over the weekend of June 23 – 24, 2007 with a contingency implementation weekend of June 30 – July 1, 2007
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 9: Questions?
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO