## Slide 1: Enhancements to FasTrak PR 50007 Project Update Retail Market Subcommittee October 11, 2006 Adam Martinez Mgr, Market Operations DPO

## Slide 2: Issue Resolution
September RMS – ERCOT reported two issues impacting schedule and budget
  Excel Scientific Notation Issue – when downloading long numbers from data to Excel (e.g. ESI IDs), number converts to scientific notation because field not recognized as text
  Mass Update Issue – when a mass update request submitted by several users at same time, updates for some fail while others are successful
  RMS approved support for ERCOT recommendation to move forward with project using new schedule and budget increase
    Must have fix for Scientific Notation issue
    Work-around okay for Mass Update issue; but fix preferred
Both issues now successfully resolved!
  Product will launch with Mass Update functional and ESI-IDs not converting to scientific notation in download

## Slide 3: Current Events
ERCOT presented at September Board of Directors meeting a request for approval of budget increase & schedule change
  Budget Impact
    Budget increase, EXCLUDING fix for Mass Update issue, estimated $188K
    Total project budget cap increasing from $2.5MM to $2.7MM
  Schedule Impact
    If proceed with project immediately and avoid continued delay from Mass Update issue, remaining activities will consume up to a 10-week period
    New Market go-live date is November 11
    New schedule minimizes impacts from ERCOT planned blackout periods and conflicts from other projects in pipeline (RBP & TX SET 3.0)
ERCOT Board of Directors approved requested changes

## Slide 4: Current Schedule
Project Activity | Duration | Dates | Status
ITest Environment Migration | 1 week | 9/18 – 9/24 | Complete
ERCOT UAT – GUI & API Regression Test | 4 weeks | 9/25 – 10/20 | In Progress
GUI Sandbox | Approximately 4 weeks | 9/27 – 10/20 | In Progress
Market Training | 3 days | 10/12 – 10/16 | Not Started
Migration to CERT Environment | 1 week | 10/23 – 10/29 | Not Started
Market CERT Test – API | 2 weeks | 10/30 – 11/10 | Not Started
Production Migration & Stabilization Prior to Market Release | 2 weeks | 10/30 – 11/10 | Not Started
Go Live | 1 Day | 11/11 | Not Started

## Slide 5: MarkeTrak Training
ERCOT to conduct “refresh” training for Market Participants
  Houston – October 12th (at CenterPoint Energy)
  Dallas – October 13th (at TXU)
  Taylor – October 16th (at ERCOT)
This is designed to be “hands on” training
Based on Market feedback, the training will focus on:
  General Overview
  D2D Issues
  Reporting
  Bulk Insert
Space is limited for these training classes so please register with Scott Egger (segger@ercot.com) or 512-248-3162

## Slide 6: Reminders
User Profile Spreadsheet due no later than October 13th
Allows ERCOT to load your MarkeTrak users into the system prior to implementation
  TDSP submission rate at 100%
  CR submission rate at 55%
If you do not submit a User Profile Spreadsheet, your MarkeTrak Administrator will have to manually load your users into the system AFTER implementation
Submit spreadsheets to Scott Egger (segger@ercot.com). Contact at email or 512-248-3162 with questions about the User Profile Spreadsheet

## Slide 7: Questions / Contact
Adam D. Martinez
Mgr, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com