## Slide 1: ERCOT Outage Evaluation & Resolution Phases I & II PR 60006_01 Project Update Retail Market Subcommittee October 11, 2006 Adam D. Martinez Mgr, Market Operations DPO

## Slide 2: Project Status
Project Status
  On target for Scope & Budget
  Schedule impact to testing & production migration
Project Phases
  Initiation & Planning Phases completed
  Execution Phase underway
  Closing Phase scheduled for First Quarter ‘07
Recent Activities
  Development testing completed
  Migrations plans to CERT and ITEST completed
Next Steps
  Systems configuration and software installation in ITEST/CERT
  Market Participant testing

## Slide 3: Schedule Revision / Market Impacts
Schedule Revision
  Migration to ITEST environment to support Testing was delayed due to storage capacity limitation. Issue resolved, however new schedule required
    PaperFree fileserver will be installed in ITEST/CERT week of 10/16/06
    PaperFree fileserver production installation rescheduled for 11/11/06 Retail Release
    Market Ad Hoc Connectivity Test Window for NAESB now scheduled for late Nov. 2006 after current Flight Test ends on 11/21/06
    NAESB replacement production migration rescheduled for late Dec. 2006
Market Impacts from NAESB Cut-over
  New Production NAESB URL (NAESB.ercot.com) available mid to late December
  Will require Market Participants to implement changes within MP environment
    Change to new URL
    New User ID/Password
    New PGP key
    New SSL certificates (if necessary)
    IP address changes to firewalls (if necessary)
  Existing NAESB will remain in parallel production until all MPs are using new system

## Slide 4: Metrics Reporting
Production Metrics
  Metrics based on improvements from SCR 745 will not be available until all affected MPs complete NAESB changes
  Scripts will be made available to assist in transition to new system
  Existing NAESB system will remain in place until all MPs are successfully using the new system
Availability of Metrics based on SCR 745
  Until all MPs have converted to the new NAESB URL, production metrics will be based on stats from both current and new NAESB sites
  ERCOT recommends that the Market complete NAESB changes by agreed-upon date. Proposed cut-off for use of existing NAESB: January 31, 2007

## Slide 5: Questions / Contact
Adam D. Martinez
Mgr, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com