## Slide 1: Texas Nodal Market Implementation TAC Meeting Budget Rationale and Review October 6, 2006 Kathy Hager, Market Redesign Program Director

## Slide 2: Purpose and objectives
This document provides a high-level overview of the proposed Nodal budget
This material has been reviewed by TPTF
  Options for value engineering changes to the project scope were considered
  TPTF concurred that the materials presented meet the:
    Scope of the requirements of the Nodal Protocols
    Timeline for implementation approved by TPTF and TAC
    Requirements of the TAC approved Nodal Transition Plan
  TPTF made no finding with regard to the total amount of the proposed budget
We seek TAC’s concurrence with TPTF’s findings prior to its consideration by the ERCOT Board of Directors
Following such concurrence, ERCOT will baseline1 the budget (to complement the scope and timeline) and prepare the updated Nodal market implementation cost filing for 11/21/06
1 The baseline represents the accepted cost-schedule-scope equilibrium on the project, and forms the basis for comparing progress. Changing the baseline is a big deal as it represents a change in the equilibrium and requires explicit approval.

## Slide 3: The program is driven by PUCT Order and requirements developed with Market Participants
The principal binding document (the Protocols signed into Order, Docket #31540) established the major requirements for the Nodal Program:
  The scope of Nodal
  The implementation date (1/1/09)
Market Participants established the ERCOT Nodal Transition Plan, which sets requirements for approach and implementation:
  The requirements for Market Participants review of all business requirements and design documents provides transparency in development
  The market trials sequence and requirements for Early Delivery Systems (EDS) to enable Market Participants to test and gain confidence in the new systems and processes
  The comprehensive training curriculum enables Market Participant and ERCOT staff readiness

## Slide 4: The Nodal budget is driven by a number of factors
This document describes Nodal budget submission, its rationale and key drivers
It is predicated on:
  The scale and complexity of the changes
  The vendor and integration approach
  The implementation sequence and timeline
  Zonal/Nodal interdependencies

## Slide 5: Next steps
Week commencing 9/25
  9/25 – Nodal Steering Board approves BoD “storyboard” (this document)
  9/27 – TPTF reviews/challenges detailed estimates and options for reduction
  9/29 – Nodal Steering Board approves funding sources/accounting paper
Week commencing 10/2
  10/6 – TAC reviews/challenges/concurs with TPTF/ERCOT
Week commencing 10/9
  10/9 – BoD material submitted
  10/10 – TAC Nodal Budget workshop
  10/11-10/13 – BoD member and PUCT “deep-dive”
Week commencing 10/16
  10/17 – Updated Nodal program briefing at BoD meeting
Week commencing 11/20
  11/21 – Updated Nodal market implementation cost filing

## Slide 6: Nodal major events
Dec 2005
March 2006
Sept 2006
Dec 2006
Creation of April Budget Submission
4/24: Nodal Budget Estimates submission
4/26: Nodal Program Charter approved
9/4: TPTF reviews full program, excluding budget
9/11: TPTF endorsed phased implementation scenario
9/14:TAC concurs with TPTF scenario
9/19: BoD presentation of recommended TPTF/TAC/ERCOT scenario and a budget update
10/31: Nodal requirements completed
11/21: Updated Nodal Market implementation cost filing
Staffing & mobilization
RFPs
Vendor selection & SOW1 contracting
Joint requirement development
Vendor SOW2 preparation
Protocol clarifications
Architecture development
Stakeholder engagement
“Accountable executive” endorsement
Program scenario planning
Project bottoms-up planning & estimating
Budget development
10/17: BoD updated Nodal program briefing

## Slide 7: The current budget has been through multiple cycles of elaboration and due diligence
Staffing & mobilization
Identified & allocated available ERCOT staff to projects
Developed external staffing strategy to fill capability and capacity gaps
Vendor selection & SOW1 contracting
Developed “best of breed” product and integration strategies and selected preferred vendors
Established time-boxed, time & materials contracts for joint requirements development
RFPs
Initial market testing against Nodal Protocols to provide initial vendor estimates and inform selection
Joint requirement development
Establishing clear understanding of Nodal requirements and extent of Nodal customs to inform revised vendor estimates for SOW 2
Protocol clarifications
Raised Protocol clarifications with TPTF to remove ambiguity and limit scope
Vendor SOW2 preparation
Evaluating SOW 2 estimates against expectations and experience elsewhere prior to concluding SOW 2 negotiations
Architecture development
Established high-level architecture including hardware specifications and integration standards (supportable by all preferred vendors)
“Accountable executive” endorsement
Achieved TAC endorsement to the “accountable executive” concept to establish a single point of contact for Market Participant plans and progress
Stakeholder engagement
Engaged TDSPs to enlist support for network model & telemetry improvements
Engaged ERCOT governance bodies to achieve consensus on the schedule and raise confidence in detailed planning
Program scenario planning
Achieved TAC/TPTF concurrence on preferred implementation timeline
Budget development
Compared bottoms-up project estimates with previous estimates and assumptions to establish current budget proposal and rationale
Project bottoms-up planning & estimating
Established and reviewed detailed, resourced work breakdown schedules for each project

## Slide 8: The proposed baseline budget
 | Total
Internal Resource Costs | 46,587,631
External Resource Costs | 76,576,360
Vendor Labor | 47,559,590
Hardware, Software, misc. | 66,639,498
Finance Charges | 10,600,000
Contingency | 15,000,000
Total | 262,963,079
Total
15,752,316
36,755,404
6,482,000
37,281,455
5,313,468
24,067,794
125,652,437
Total
-
-
-
-
Not included
-
78,429,600
11/04 CBA (KEMA)
Dimensions
30 months
$100/hour
25%
Dimensions
18 months
$137.5/hour
35%
 | Dimensions
Project duration | 32 months
Composite fee rate | $100.5/hour
Contingency (vs base) | 6%
9/06 Program Estimate
12/05 High-Level Estimate
12/05Assumptions:
  Funding from Zonal includes: 50% Network Security Upgrade, EMS upgrade, 80-90% of NMMS
  OTS scope narrower (expanded as a result of ABB MMS selection)
  Model fidelity scope narrower (cf Nexant)
  Integration within projects, thus SOA would leverage Zonal resources and cost when needed
  MIS enhancement, not re-design
  Excluded SAS 70 and a greater proportion of ERCOT Readiness and Transition is O&M
11/04 CBA Assumptions:
  Use of automated Regression Testing tools limited to Commercial Systems
  Included facilities labor and activities (modifications to existing data centers and work area and incremental hardware)
  Minor incremental hardware
  Single vendor for EMMS (EMS, MMS and CRR); only modifications to Operator Actions, LFC/SCED, NSA, LMP calc and AS Monitoring. Excluded Load forecasting, Outage Scheduling and OTS.
  Few ERCOT.com and MIS changes, DAM and (Zonal) Portal Replacement Project will absorb some of these costs
  Training resource estimated at 6 FTE for 6 months (EMS, MMS and CS)
  Auction-based DAM will be implemented prior to Nodal; related ADAM costs considered sunk.
+66%
+109%
65% of Nodal Program budget is labor: $170MM

## Slide 9
Major differences between the current estimate and the interim fee case (by Project)
Project | Current Estimate $M | Interim Fee Case $M | Differences $M | Internal Labor $M
Program Management (PMO) | 7.1 | 2.0 | 5.1 | 0.2
Integration & Design Authority (IDA) | 6.8 | 2.0 | 4.7 | 1.0
Network Model Management System (NMMS) | 12.7 | 0.6 | 12.1 | 1.0
Energy Management System (EMS) | 17.5 | 4.3 | 13.2 | 4.3
Market Management System (MMS) | 26.3 | 10.9 | 15.4 | 3.4
Congestion Revenue Rights (CRR) | 6.3 | 4.5 | 1.8 | 1.1
Commercial Systems (COMS) | 14.8 | 9.1 | 5.7 | 5.6
Enterprise Integration (EIP) | 12.3 | 0.5 | 11.9 | 2.9
Enterprise Data Warehouse (EDW) | 4.0 | 2.5 | 1.5 | 2.5
Market Information System (MIS) | 7.8 | 0.4 | 7.4 | 0.3
Infrastructure (INF) | 61.8 | 32.9 | 28.9 | 2.2
Integration Testing (INT) | 17.0 | 7.4 | 9.6 | 4.7
MP Engagement & Readiness (MER) | 13.7 | 8.6 | 5.1 | 4.2
ERCOT Readiness & Transition (IRT) | 29.3 | 10.7 | 18.6 | 13.1
Finance Charges | 10.6 | 5.3 | 5.3 | N/A
Contingency | 15.0 | 24.1 | (9.1) | N/A
TOTAL | 263.0 | 125.7 | 137.3 | 46.6

## Slide 10
Explanation of major differences
Item | Commentary | Increase over $125M
Infrastructure | Unix end-of-life previously assumed Zonal Data center virtualization previously assumed Zonal EDW storage, Oracle support and hardware previously assumed Zonal | $28.9M
ERCOT Readiness & Transition | Greater effort and longer duration than previously estimated (includes training for 393 ERCOT staff – 67 hours average) | $18.6M
MMS | Vendor cost previously under-estimated. Selected vendor (ABB) providing a modern product, consistent with ERCOT’s architecture roadmap Development split to deliver SCED in advance of balance of MMS | $15.4M
EMS | EMS upgrade previously under-estimated and assumed Zonal Nodal customs previously under-estimated New outage scheduler previously under-estimated (vendor selection – ABB – governed by MMS selection) | $13.2M
NMMS | Majority of NMMS development and all SE/Network Model fidelity work previously assumed Zonal | $12.1M
Integration | Much greater complexity of integration than previously assumed (much larger number of vendors resulting from best-of-breed product selection & greater complexity of ERCOT-specific data elements e.g. CIM extensions) | $11.9M
PMO & IDA and Audits | PMO, architecture and RUP consulting support to enhance program & technical delivery capability previously under-estimated SAS 70 (part 1), Security & Program Control audits not included in previous estimate | $9.8M
Integration Testing | Longer duration and more functional (end-to-end) testing than previously estimated | $9.6M
MIS | Need to enhance usability and user experience requires portal replacement | $7.4M
Commercial Systems | Greater effort and vendor costs than previously estimated | $5.7M
MP Engagement & Readiness | More training and customer care required by market participants than previously estimated | $5.1M
Miscellaneous | Miscellaneous increases against previous estimates in CRR, EDW | $3.3M
Finance charges | Current estimate $10.6M (previous $5.3M) | $5.3M
Contingency | Current contingency $15M (previous $24.1M) | ($9.1M)
 |  | $137.3M

## Slide 11: Nodal budget big picture
Budget | Description
$125.7M | Basis for Interim Nodal surcharge, budget created December 2005 Submitted to PUCT in April 2006
 | +
$51.3M | Zonal / Nodal project dependencies Zonal labor force - $31.3M EMS - $8M NMMS, network model & telemetry - $12M
 | =
$177M | “Normalized” Nodal budget (December 2005)
 | +
$69M | Underestimated cost Market trials and training Architecture, RUP, PMO, and integration Product cost Miscellaneous (e.g. audits, testing)
 | +
$17M | Infrastructure opportunity Data center virtualization Zonal hardware end-of-life
 | =
$263M | Total cost of Nodal

## Slide 12: Appendices

## Slide 13: The program is driven by PUCT Order and requirements developed with Market Participants
The principal binding document (the Protocols signed into Order, Docket #31540) established the major requirements for the Nodal Program:
  The scope of Nodal
  The implementation date (1/1/09)
Market Participants established the ERCOT Nodal Transition Plan, which sets requirements for approach and implementation:
  The requirements for Market Participants review of all business requirements and design documents provides transparency in development
  The market trials sequence and requirements for Early Delivery Systems (EDS) to enable Market Participants to test and gain confidence in the new systems and processes
  The comprehensive training curriculum enables Market Participant and ERCOT staff readiness

## Slide 14: ERCOT’s challenge is laid out in the protocols
Directly assign congestion costs
Increase transparency of energy prices
Enhance reliability and increase market efficiency
And deliver technical capability to:
Compute LMPs for 100% of settlement points, 100% of the time
Move from portfolio based dispatch to resource-specific dispatch
Run and settle the nodal markets to comply with 100% of the Nodal protocol requirements as measured by the accuracy of calculations and compliance with prescribed operational timelines
Create a CRR market to adequately hedge the directly assigned congestion charges/credits
While achieving agreed program targets of:
Zonal market continuity
Customer satisfaction
Budget
Zonal Market
Nodal Market
While ERCOT shares end goals of market efficiencies with other ISOs, it faces unique challenges of its own
ERCOT’s Charge: Design and implement the nodal market system and transition from the current Zonal market to the Nodal market by January 2009 (as defined in the protocols approved in the order signed by the PUCT on April 5th, 2006). The transition will allow ERCOT to:
Notes: Zonal market continuity – as measured by adherence to existing target levels of availability
Customer satisfaction – as measured by surveys of market participant and internal satisfaction of the program and constituent projects timeliness – as measured by achievement of key program milestones
Budget – as measured by achievement of budget goals
Specific exclusions are those items not yet embodied in the protocols (e.g. real-time co-
optimization) that have a material impact on the scope, time and cost of the program.

## Slide 15: There are essential, “environmental” differences between ERCOT and other ISOs
Characteristic | Implication
Intra-state electric interconnection 1 of 3 North American interconnections “Island” - Connected to other ISOs by DC ties only One of 10 NERC Regional Reliability Councils | FERC pro-forma open access transmission tariff does not apply to ERCOT, except across DC tie lines, allowing for uniqueness in scheduling and power delivery protocols At ERCOT, annual capacity supply is driven by Market Participant investments rather than ISO coordinated capacity synergy as in US Northeast. There is no Installed capacity market (ICAP) at ERCOT, reducing the complexity of the real time market 99% of power generation provided within Texas. At ERCOT, Ancillary Service products are limited and different than other ISOs. Other ISOs, due to tight interconnections, can share reserves and procure from adjacent areas for shortages, while ERCOT must provide all AS capacity to satisfy its needs. Sensitivity of the ERCOT grid to disturbances is generally higher
Single regulatory jurisdiction – Public Utility Commission of Texas (PUCT) | Single authority for Texas power governance for wholesale, retail, planning and any other power related topic. Together with its isolation as an electric grid, this allows unique ERCOT market protocols compared to all other ISOs
Registration is unique in Texas | All MPs must register all generation units, markets, legal entities etc with ERCOT ERCOT has multiple QSE level registration (level 1 – 4) Level 4 QSEs must perform fidelity tests for generation units under unique protocols
Unique provisions for Non Opt-In Entities (Munis and Coops) in Texas | Customization required for NOIE provisions in ERCOT such as ability to carry CRRs to Real-Time, Dynamically Scheduled Resources, Pre-Assigned CRRs, Self Schedules
Requirement to model equipment at lower voltages (down to 60kV) | Increased complexity with respect to system observability and measurements Enforcement of constraints to a more granular level adds complexity to network modeling process at ERCOT when compared to other ISOs in the high frequency of model changes (ERCOT has thousands compared to other ISOs having hundreds)
High pace of economic growth in Texas | Increased complexity in maintaining network models. Many model/field changes require significant modification within the power grid model in order to predict power flow and power consumption
Wholesale and Retail scope impact | Size of retail choice responsibilities is significantly larger than any other ISO in North America. ERCOT is the central hub of the Retail transaction system. There is a big difference in metering, load profiling and data aggregation (ERCOT deals with 7M ESI Id’s while other ISOs may deal with aggregated data from TDSPs)

## Slide 16: Texas Nodal protocols differ from other nodal markets, driving the need for customization (1 of 2)
Component | Implication | Impact on customization
Common, time-based network model for all major ERCOT applications | Multiple consuming applications including EMS, MMS, CRR and Outage Scheduler Multiple file formats and layouts creates unique interfaces for each application Significant impact on culture, business processes, software for planning and operations | 
Congestion Revenue Rights: CRRs are available between any two Settlement Points, in the form of Options or Obligations Non Opt-In (NOIE) Entities (Munis and Coops) are allowed to carry all CRRs to be settled in the Real Time energy market | Ability to create millions of market product permutations increases complexity of solution CRR Bilateral trading forces multiple source systems to settlements (MMS and CRR application) Additional feature for NOIE CRR secondary market increases complexity for CRR settlements | 
Day Ahead Market: Requirement to co-optimize markets in the Day Ahead for Ancillary Services capacity, point-to-point obligation CRRs and forward financial energy markets is unique to ERCOT DAM is not necessary for reliability of the electric grid - participation in DAM is voluntary, except for RMR units | Detailed differences require custom code | 
Reliability Unit Commitment: RUC rules are unique to ERCOT, and have significant implications to unit commitment | Direct assignments of DRUC and HRUC costs are unique in each nodal market | 
Real Time Market: Protocols specify a unique, automated methodology for establishing offer caps Protocols specify the use of average losses in the calculation of LMPs | Methodology for offer caps creates uniqueness and forces MPs to understand the distinctions in the ERCOT market Other markets specifically include the calculation of marginal losses in their LMPs | 

## Slide 17: Texas Nodal protocols differ from other nodal markets, driving the need for customization (2 of 2)
Component | Implication | Impact on customization
Settlement is unique to ERCOT | Market rules for settlements are unique across ISOs – all settlements must be built from scratch | 
Credit Monitoring creating limited exposure to ERCOT markets | ERCOT will evaluate credit exposure and collateral for every market participant on a daily basis, updating the MPs credit limits for any ERCOT market Additional credit checks will be performed as part of the CRR Auction optimization. This unique aspect of ERCOT’s transmission rights market is intended to maximize revenues from CRR auctions, and therefore value to Loads Increases the complexity of the solution system and the volume of data transactions to the systems | 

## Slide 18: The nodal budget is driven by a number of factors
The scale and complexity of the changes
The vendor and integration approach
The implementation sequence and timeline
Zonal/Nodal inter-dependencies
Notes: Add notes on the zonal market creation and it’s lessons learned (concerns with turn key solutions)

## Slide 19: Nodal will introduce significant changes in the Texas wholesale market
Current Zonal Market Characteristics | Nodal Market Characteristics
Transmission Congestion Rights (flowgates) | Congestion Revenue Rights (PTP Options, Obligations, Flowgates)
No Day-Ahead Energy Market Ancillary Services Market Day-Ahead | Day-Ahead Energy and Ancillary Services Co-optimized Market
Replacement Reserve Service (RPRS) | Daily Reliability Unit Commitment (DRUC)
Hour Ahead Studies | Hourly Reliability Unit Commitment (HRUC)
Balancing Energy Service every 15 minutes Zonal by portfolio for CSCs Unit Specific for Local | Security Constrained Economic Dispatch every 5 minutes (still 15 minute settlement) All Unit Specific
Zonal Average Shift Factors for Resources | Actual Shift Factors for Resources
Zonal Market Clearing Price for Balancing Energy for Generation and Loads | Nodal Locational Marginal Prices (LMP) for Generation Zonal weighted LMPs for Loads
Notes: The going-in position on high-level components is as follows.

## Slide 20: This will profoundly impact the core business processes of ERCOT, Inc and MPs

## Slide 21: This requires significant change to, or replacement of, the wholesale market, network model, power operations systems and settlements
MP Reg
Market Operations
OS
CRR
NMMS
EDW
MIS
EMS1
DAM
Commercial Applications
CM&M
LF
SCED
RUC
Business and Engineering Model
Settlement
Mid Term
Day Ahead
Real Time
User Interface
Power Operations
IMM2
Integration (information bus and/or point to point )
CRR Congestion Revenue Rights
CM&M Credit Monitoring & Management
DAM Day-Ahead Market
EDW Enterprise Data Warehouse
FT Financial Transfer
IMM Independent Market Monitor
LF Load Forecast
RPPF Renewable Product Potential Forecast
MIS Market Information System
MP Reg Market Participant Registration
NMMS Network Model Management System
OS Outage Scheduler
RUC Reliability Unit Commitment
SCED Security Constrained Economic Dispatch
Degree of change
100% New/replacement
>50% Upgrade/enhancement
<10% Enhancement
Notes:
1 Includes State Estimator and Telemetry Criteria
2 To satisfy section 17.3 of the Nodal protocols, ERCOT will deploy COGNOS and SAS to provide PUCT with the ability to generate reports
QSE Systems
RPPF
Every interface, API and process will change – every aspect of training is different
Notes: Processes:
Integration testing – substantial replacement (100% new)
Training – education and training for ERCOT, Market Participants and Operators (100% new)
Market Participant readiness – communication, impact assessment, Readiness Criteria, development and testing (100% new)
ERCOT, Inc readiness – communication, impact assessment, business process change (all Markets), organizational preparation and testing (100% new)
Market Trials – preparation, execution and Readiness Declaration (100% new)
Transition to live operations – cut-over & business continuity (100%)
Systems:
Registration System – minor enhancements (<10% functionality)
Network Model Management System (NMMS) – replacement of Genesys (100% replacement plus significant additional functionality)
Energy Management System (EMS) – substantial upgrades and enhancements (>50% of functionality)
Market Management System (MMS) – replacement (100% replacement)
Congestion Revenue Rights (CRR) – new (100% new)
Commercial Systems (Settlements and Billing) – substantial upgrades and enhancements (>50% of functionality)
Monitoring applications for Credit, Market & Compliance – substantial upgrades and enhancements (>50% of functionality)
Reporting/Analysis (Enterprise Data warehouse/Enterprise Information Services) – substantial upgrades and enhancements (>50% of functionality)
Interfaces within ERCOT, and external Interfaces between ERCOT and participants – substantial enhancements (>50%)
Infrastructure – substantial enhancements (>50%)

## Slide 22: The nodal budget is driven by a number of factors
The scale and complexity of the changes
The vendor and integration approach
The implementation sequence and timeline
Zonal/Nodal inter-dependencies
Notes: Add notes on the zonal market creation and it’s lessons learned (concerns with turn key solutions)

## Slide 23
Conventions
- ERCOT Process
- Group of related entities
Acronyms
  AS: Ancillary Services
  BOD: Board of Directors
  FERC: Federal Energy Regulatory Commission
  LSE: Load Serving Entity
  NERC: North American Electrical Reliability Commission
  PUC-T: Texas Public Utilities Commission
  QSE: Qualified Scheduling Entity
  TAC: Technical Advisory Committee
  CRR: Congestion Revenue Rights
  TDSP: Transmission/Distribution Service Provider
With numerous players, integration is one of our biggest challenges
External and internal entities
Resource
LSE
Public
QSE 1
Marketer
ERCOT
Governance
Regulatory
TDSP
QSE 4
Resource, AS
QSE 2
Load
QSE 3
Resource
BOD
NERC/FERC
TAC
PUCT
Retail
Wholesale
Market
Network Model
Grid
Operations
Settlements
Registration
Communication
CRR Account
Holders***
System
Planning

## Slide 24: Motivators for ERCOT’s role as integrator
Belief that ISO systems can be assembled from a core of best of breed COTS1 systems
Consistent data architecture based on the industry standard Common Information Model (CIM) with extensions to meet the ERCOT business model
Consistent user experience across all ERCOT systems
Multi-layered approach to system architecture to achieve a highly scalable, flexible and secure architecture
Operational efficiency through standardized infrastructure (AIX, Oracle, tools)
Leverage mature e-commerce technologies and prevailing B2B and B2C technology standards
Flexibility to respond to business and technical evolution
Notes:
1 COTS - Commercial Off The Shelf
Notes: <number>
<footer>
<header>
<date/time>

## Slide 25
A best-of-breed product vendor strategy was adopted to mitigate risk
Rigorous selection criteria have been applied, consistent with the Nodal Charter:
  No “green” software – code in production will have fewer bugs, more robust, with proven integration
  Consistent with ERCOT’s technology roadmap/footprint – to provide flexibility, minimize total cost of ownership
  Proven track record of delivery – client references have been leveraged to validate predicted performance
  Strength of vendor team – demonstrate adequate commitment of skills and experience, particularly project management
 | Preferred Vendor | Other comments
Credit Monitoring | ROME Corporation | 
CRR | Nexant, Inc. Energy Solutions Division | 
EMS | AREVA T&D, Inc. (current vendor) | 
Market Operations | ABB, Inc.PSN/Power Systems Division | 
Network Modeling & Telemetry | Nexant, Inc. Energy Solutions Division | Assessment and improvement of model and SE – short- and long-term
NMMS | Siemens Power Transmission & Distribution, Inc. | 
Outage Scheduler | ABB, Inc.PSN/Power Systems Division | Vendor governed by MMS selection
RPP forecast | AWS Truewind, LLC | 
Market Information System | Enterpulse | 
Integration | UISOL | Vendor for architecture & design
Note – Enterprise Data Warehouse and Commercial Systems (including Financial Transfer, Billing and Settlement) to be developed internally.

## Slide 26: A strategy for integration is established
The strategy – apply the appropriate integration tool
  Embrace the Rational Unified Process (RUP) – proven integration methodology
  Specialized program organization design and transition approach
  Focus on information architecture- applications need common definitions to communicate
  Messaging for non-real time with specialized solutions for real time and bulk data
  Applications are loosely coupled through the message layer – insulating each application from changes in other applications
  Adhere to widely adopted open standards (i.e. XML, SOAP, WSDL, ICCP) to reduce technology implementation issues
Preferred vendors can all support this strategy

## Slide 27
Systems of Systems (SoSA): looks at the customers of the system and how they expect to use it and it links business traceability with system integration
ERCOT is building a UML model of Nodal using IBM Rational’s “System of Systems” approach. This is the application of a modern system engineering approach, proven on large systems projects across multiple industries
27 Nodal level uses cases have been identified.
…
Use Case 1
Use Case 27
Actor
Nodal
Actor
Validate bid…
Includes approximately 57 operations (interactions between Nodal and outside entities).
System 1
Actor
Validate bid…
System 2
System 3
ERCOT estimates this will result in 200 integration points between the 19 Nodal systems.
Operations
Integration Pts

## Slide 28: Market Redesign technical integration going-in tactical plan
NMMS
EDW
MIS
Commercial
Systems
Retail
CRR
MMS
EMS
Messaging
Service
Point to Point Connections
Near Term Message Bus Connections
Future Message Bus Connections
Real Time
Bulk data
Bulk data
Bulk data

## Slide 29: SOW #1 (requirements & conceptual design) has been executed with all strategic vendors
Key
ERCOT
Siemens
ABB
Areva
ROME
AWS Truewind
Nexant
LODESTAR
Enterpulse
UISOL
Other
MP Registration
Market Operations
OS
CRR
NMMS
EDW
MIS
EMS
DAM
CM&M
LF
SCED
RUC
Business and Engineering Model
Settlement
Mid Term
Day Ahead
Real Time
User Interface
Power Operations
QSE Systems
Commercial Applications
Integration
Architecture and Design by UISOL
IMM
RPPF
Application Vendors, and Consultants
Various consultancies provide project management, training, development, and other services.
Notes: There are 15 applications that have to be integrated;
Access should be provided to 500+Market Participants for integration with their systems
Rational Unified Process (RUP, IBM methodology) has been enlisted to provide for an iterative development process

## Slide 30: The nodal budget is driven by a number of factors
The scale and complexity of the changes
The vendor and integration approach
The implementation sequence and timeline
Zonal/Nodal inter-dependencies
Notes: Add notes on the zonal market creation and it’s lessons learned (concerns with turn key solutions)

## Slide 31: The benefits value chain has determined how we plan to lay down the Nodal system
Increased dispatch efficiency
(unit-level)
Nodal RT operations
New Day-Ahead Energy Market
New CRR Market
Additional participation in and increased liquidity for Texas energy sales
More granular, locational price signals
Increased transparency of energy prices
Reduction in congestion costs
Benefits passed on to consumers
Efficient location of new generation
Efficient location of new transmission
Direct assignment of congestion costs
Reduction in Energy/AS prices
Reduction in undesirable market behavior
True commodity-based pricing
Opportunity hedge real-time energy and day ahead congestion costs
Enforcement of open access and real customer choice
Reduction in incentive for aberrant market behavior
Increased potential for locational demand-side participation
Key Nodal capabilities…
…have direct impacts …
…that drive efficient market behaviors…
…and deliver improved economic outcomes for market participants and benefits to consumers
Accurate, time-based models are a key enabler

## Slide 32: TPTF’s requirements for trials using Early Delivery Systems drives the back-end critical path
EDS 1/2 – Single Entry Model
Basic Network Model & SE Criteria NMMS (UI internal only) ICCP (RTU migration) Nodal EMS (non-live)
EDS 3 – Real Time Operations
NMMS (without Planning model) Nodal EMS Outage Scheduler SCED RUC SASM COP Emergency Operations Trades, Schedules Offers (3 part) CRR (settled in RT) CMM (part) MIS (part) Commercial operations (for RT) EDW (for RT) Integration (part) LMPs published 8*5 support
EDS 4 – Day Ahead Market/CRR
NMMS (full) DAM CRR (full) CMM (full) MIS (full) Full back-end (x4) 8*5 support (24*7 for MP ITEST) ERCOT & Market Readiness Criteria approved
EDS 4 Trial outcomes
All MP Registration complete for Go Live All market facing interfaces complete Testing of all markets complete 168 Hour test complete All interfaces validated Training complete MP financial & operational qualification complete Market Readiness Declarations met “Home Team” transitioned (as needed)
Real Time Operations GO/NO GO Day Ahead Market/CRR GO/NO GO
EDS 3 Trial outcomes
6 month SCED test completed EMS enhancements complete MP offers LFC, OS, RPP complete All MP Registration complete for Go Live “Home Team” transitioned (as needed)
LMP Market Readiness Criteria- MET EDS4 - GO/NO GO
Q2 2008
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2007
Q1 2008
Q1 2009
Q3 2007
EDS 3
EDS 4
Go-live Trans.
EDS 3 Mote and ERCOT UAT
EDS 1/2
EDS 1/2 Trial outcomes
SE Criteria achieved Telemetry criteria achieved
Single Entry Model (with stable and capable SE) GO/NO GO
EDS3 Training

## Slide 33: The budget is significantly influenced by the recommended timeline Nodal Market & Zonal Shutdown December 2008
EMS
Trials & Implementation
MMS
CRR
MIS
NMMS
Commercial Systems
ERCOT & MP Readiness
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q1 2008
Q3 2006
Q1 2009
Integration
EDW
Q2 2009
EDS 3
MMS FAT
ITEST
CRR Design, Build, Pre-FAT
CRR FAT
ITEST
Final MP Interface Specs 3/31
12/01/08 Real Time Operations GO LIVE
MIS (EMS/MMS/CRR) Design, Build, Pre-FAT
EDW FAT
ITEST
Statements Layout
Script test
ITEST
EMS
EMS FAT
EMS Requirements, Conceptual Design
ITEST
MIS (SCED) Design, Build, Pre-FAT
MIS FAT
MMS Design, Build, Pre-FAT
MMS Requirements, Conceptual Design
ITEST
OS Build
FAT
OS Requirements, Conceptual Design
CRR Requirements, Conceptual Design
Commercial Systems Design, Build, Pre-FAT
CS FAT
ITEST
EDW Requirements, Conceptual Design
ITEST
SCED Build
SCED FAT
SCED Requirements, Conceptual Design
Registration ready
Business Requirements complete 10/30
Preliminary MP Interface Specs 12/31
CS Requirements, Conceptual Design
EDW Design, Build, Pre-FAT
MIS FAT
ITEST
EDS 4
Go-live Trans.
EDS 3 Mote & ERCOT UAT
Planning UI
FAT
ITEST
Naming Convention DB
Common model update process
NMMS Conceptual Design
Naming Convention information collection
Model Data Certification
Model Data Remediation Reconciliation
NMMS Build
Outage Scheduler
EDS 1/2
Build
FAT
ITEST
Requirements, Conceptual Design
ITEST
OS FAT
6/30/08 LMP Market Readiness Criteria MET
Q3 2007
Operations UI
Qualification Freeze
Registration complete
168 hour market trials
End of Trials
MP Nodal Registration
MP Financial & Operational Qualification
MPSCED Offers
Begin MP trial participation
3/31/08 Single Entry Model GO LIVE
12/08/08 Day Ahead Market/CRR GO LIVE
Zonal Shutdown GO/NO GO
EDS 3 Training

## Slide 34: Delivery experience of other nodal implementations
ISO | Characteristic | Duration | Commentary
ISO-NE | Zonal to Nodal | 2 yr (23 mo) | Market rules purchased from PJM, leveraged PJM market rules and Areva’s experience with PJM systems Duration ignores mobilization work prior to Areva contract (duration measured from Areva start to go-live) Single phase implementation (RT operations, DAM and FTR)
NYISO | Nodal to Nodal | 3 yr (35 mo) | Duration measured from ABB engagement to go-live (data from Kema)
MISO | Direct to Nodal | 3 yr (38 mo) | Duration measured from FERC approved Tariff to Midwest Markets Launch Single phase implementation (RT operations, DAM and FTR)
CAISO | Zonal to Nodal | 5 yr (60 mo) | Duration measured from PUC Order to projected go-live (11/07) Single phase implementation (RT operations, DAM and CRR)
ERCOT | Zonal to Nodal | 2.7 yr (32 mo) | Duration measured from PUCT Order to go-live (12/08)

## Slide 35: The nodal budget is driven by a number of factors
The scale and complexity of the changes
The vendor and integration approach
The implementation sequence and timeline
Zonal/Nodal inter-dependencies
Notes: Add notes on the zonal market creation and it’s lessons learned (concerns with turn key solutions)

## Slide 36: Nodal budget big picture
Budget | Description
$125.7M | Basis for Interim Nodal surcharge, budget created December 2005 Submitted to PUCT in April 2006
 | +
$51.3M | Zonal / Nodal project dependencies Zonal labor force - $31.3M EMS - $8M NMMS, network model & telemetry - $12M
 | =
$177M | “Normalized” Nodal budget (December 2005)
 | +
$69M | Underestimated cost Market trials and training Architecture, RUP, PMO, and integration Product cost Miscellaneous (e.g. audits, testing)
 | +
$17M | Infrastructure opportunity Data center virtualization Zonal hardware end-of-life
 | =
$263M | Total cost of Nodal

## Slide 37: Texas Nodal Market Implementation Program Project Budget Analyses

## Slide 38: Contents
Market Participant Engagement & Readiness
ERCOT Readiness & Transition
Integration & Design Authority
Network Model Management System
Energy Management System
Market Management System
Congestion Revenue Rights
Commercial Systems
Enterprise Data Warehouse
Infrastructure
Integration
Integration Testing
Program Office

## Slide 39: Market Engagement and Readiness (MER) Project Budget Analysis

## Slide 40: MER: Package Summary
Description: Market Participant approval of Nodal designs, preparation for and participation in testing and trials, training and readiness live nodal operations.
Vendor(s): N/A
Project Manager: Trip Doggett
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Training design (to accommodate several learning styles) development & delivery, and web-based training Communications TML replacement with new MIS web portal Market Participant Readiness Criteria, status reporting & Declarations Customer Care
Key Assumptions: TPTF is the primary Market Participant representative body for Nodal Engagement with Market Participants will comply with the requirements of the ERCOT Nodal Transition Plan
Challenges/Risks: Market Participant mobilization and active engagement in support of overall nodal project Number and heterogeneity of Market Participants Competing demands – including training development – for SME resource bottlenecks
Comments: Market Participant Accountable Executive concept being implemented TPTF workgroups being established (for MIS portal and Training consultation) where needed

## Slide 41: MER (excluding MIS): Cost Summary
 | Total
Internal Resource Costs | 4,184,440
External Resource Costs | 8,812,280
Vendor Labor | 57,900
Hardware, Software, misc. | 664,163
Total | 13,718,783
Total
-
-
-
-
3,036,000
11/04 CBA (KEMA)
Dimensions
10 months
$137.5/hour
35%
 | Dimensions
Project duration | 30 months
Composite fee rate | $122/hour
Contingency (vs base) | (see summary)
11/04 CBA assumptions:
  Training included planning, curriculum design & development.
  Training resource estimated at 6 FTE for 6 Months (split evenly between EMS, MMS and Commercial Operations topics. Excluded basic ERCOT training as ERCOT already performs these
  Change Management includes MP interactions requiring NPPR approval (TPTF activities)
+184%
Total
2,547,568
5,944,326
64,820
67,940
8,624,654
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Includes training and LMS
  Excludes approval process
9/06 Program Estimate
+59%
Cost drivers for Training:
  PUCT concern that MPs have adequate opportunity to learn more about the Nodal model
  Training targeted for over 10,000 training attendees
  Multiple training delivery mechanisms: face-to-face, Web-Ex, Self-Paced web-enabled
  7500 Hours of Face to Face course delivery prior to 12/1/08
  Very large curriculum of training supported – 38 courses hosted, 19 developed by project team
  TPTF Concern over training readiness requires extensive team support
  Cost drivers for Customer Care:
  Ratio of 1 Account Manager per 10-14 QSEs.
  Includes an Online Help Center (web-based) and “extension 3900” support.
  Includes sending required market notices.
  Cost drivers for TPTF:
  5 meeting days per month; at the MET center (no travel or outside facility costs)
  Cost drivers for Communications:
  Current publications and web work, including postings
  Cost Drivers for MP Readiness Criteria:
  Four auditors will make 45 site visits each, with a travel budget, to Market Participants to gather data from Market Participants on their progress toward meeting the criteria, and will report that progress to the MRA. MRA not in MER budget.
Budget reduction options to be discussed with TPTF & TAC
Structural options:
  Consolidation of generation courses ($910,000 Reject by TPTF on 9/12/06)
  Reduce course duration ($200,000 Reject by TPTF on 9/12/06)
  Delay development of certain courses until after transition ($737,000 Reject by TPTF on 9/12/06)
  Reducing number of channels to be presented (78,000 Reject by TPTF on 9/12/06)
  Reducing number of internally-focused (ERCOT, Inc) courses
Cost reduction options:
  Replace readiness auditors with self-reporting my MP Accountable Executive ($1.3M approved by TPTF 9/28/06)
  Decrease ratio of Account Manager per QSEs
  Eliminate website / communication activities
  Find a more cost effective way to print ($100,000 Completed)
  Only deliver courses once a month ($400,00 Completed)
  Reduce the quality of the training deliverables. ($800,000 Reject by TPTF on 9/12/06)

## Slide 42: MER (MIS): Cost Summary
11/04 CBA (KEMA)
Dimensions
10 months
$137.5/hour
35%
11/04 CBA assumptions:
  ERCOT.com and MIS changes low assuming DAM and (Zonal) Portal Replacement Project would absorb some of these costs
Cost drivers:
  Scope: over 300 Protocol Requirements
  Large number of integration points and dependencies from numerous sources
  Vendor selected to ensure required level of performance, functionality is delivered in the necessary timeframe
  Software licenses
  Length of project (dependent on drops from multiple product projects)
  Enhancements to user experience (improved navigation, based on end-user feedback; personalizable "My Page" that allows users to tailor their home page; dashboard that presents data graphically; consistent look and feel with other new ERCOT applications and ERCOT.com)
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Assumed TML enhancement, not re-design
  Assumed using current ERCOT portal licenses and technology
  Assumed little re-write of existing Portal, only enhancements due to Nodal protocols
 | Total
Internal Resource Costs | 319,410
External Resource Costs | 2,582,500
Vendor Labor | 4,319,309
Hardware, Software, misc. | 603,876
Total | 7,825,095
Total
-
-
-
-
660,000
 | Dimensions
Project duration | 30 months
Composite fee rate | $96/hour
Contingency (vs base) | (see summary)
-34%
Total
72,540
169,260
-
193,440
435,240
9/06 Program Estimate
+ 1,698%
Budget reduction options to be discussed with TPTF & TAC
Structural options
  TML can be retained to reduce the overall cost of implementing a portal for Nodal, foregoing user experience/usability enhancements (essentially a “link farm”) Savings potential ~ $5M (Rejected by TPTF on 9/27-28/06)
  Cost reduction options
  Reduce functionality to include only the minimum to meet the Protocols Savings potential ~ $0.5M (Rejected by TPTF on 9/27-28/06)

## Slide 43: MER: Schedule and Resource Effort
Note:
  Resource graph corrected from version reviewed by TPTF & TAC

## Slide 44: MER: Budget Assumptions (1)
Key Assumptions for MIS: Budget begins July 06 Testing and release management staff resource costs not included No vendor expenses (travel, hardware/software, lease) included No payment/expenses for Market Participant involvement (including Market Participant site integration expense) included Vendor will provide system-level training, documentation, operation manuals in costs listed under VENDOR No integration at Market Participant site expense is covered Current WAN or other network structure will support the new MIS portal Scope of expense does not extend past MIS web portal (does not include changes to ERCOT.com or other sites) No changes or additions to Protocols that affect MIS portal functionality will be accommodated past Feb 1, 2007 (prototype 1 delivery) No new reporting or re-work of existing reporting is included in MIS portal scope or budget Transition from MIS portal project to ERCOT maintenance staff will occur thru staff participation on project during 2008 Key Assumptions for Training: No inclusion of WebEx sessions costs. ERCOT departments are allowed to use WebEx sessions without specifying the actual charge in budgets Use current LMS with no purchased extension Level of effort is based on training courses identified by the Market Participants in the "Curriculum" document Market Participant support & travel is not included Internal ERCOT required training or training for supporting system deployment is not yet identified or included LMS contract is good for two years - can not guarantee same price in 3rd year The Nodal project team is not responsible for the operator seminar until 2008, however the team will provide whatever support is needed for the current seminars

## Slide 45: MER: Budget Assumptions (2)
Key Assumptions for TPTF: Only Leader and Stakeholder Services Specialist will charge to the TPTF Project. Anyone else attending TPTF meetings will charge to other projects. Any other support from ERCOT will be budgeted by the “Home Team”, not MER. Leader will be provided by the “Home Team” after December, 2007 5 meeting days per month; at the MET center (no travel or outside facility costs) Updates to TAC once per month; no updates to other groups Key Assumptions for Communications: 4 big “events” per year Current publications and web work, including postings, will continue at current pace Key Assumptions for MP Readiness Criteria: ERCOT will hire a firm to serve as Market Readiness Advisor (MRA) who will provide services similar to the MRA at MISO, including creating proposed MP readiness criteria, gain TPTF’s approval of the criteria, build a data collection tool and prepare a dashboard to share progress. 4 auditors will make 45 site visits each, with a travel budget, to Market Participants to gather data from Market Participants on their progress toward meeting the criteria, and will report that progress to the MRA. All data to measure Market Participant personnel readiness will be based on training test results and MP systems. Key Assumptions for Customer Care: Provide critical support to Market Participants. Includes an Online Help Center (web-based) and “extension 3900” support. Includes sending required market notices. A ratio of 1 Account Manager per 10-14 QSEs. Maintenance of FAQ to cross-train other reps and as a resource for the Online Help Center. Does not include travel expenses. Will be funded by the “Home Team” starting July, 2008

## Slide 46: MER: Overview of current threats to success
 | TPTF, MP Readiness Criteria, Communications and Customer Care | MIS | Training
Scope/Plans |  | Plans dependent on finalizing program approach & schedule | 
Resourcing | New internal resources must be hired |  | Future resources are dependent on course delivery dates
Costs |  | Costs for vendor are unknown, but staff costs are firm | Resource driven
Timescales |  | Ready for finalization of timelines | 
Critical dependencies |  | 1-Requirements approval 2-Timely SOW 3- Architecture Document | 
Business Modeling & Requirements | N/A |  | N/A
Analysis & Design | N/A |  | N/A
Vendors | N/A |  | N/A
External Stakeholders |  |  | Continue to work to establish a repeatable process for approval from TPTF sub-group
Internal Stakeholders | N/A |  | 
Communications | N/A | N/A | 
Overall |  | Plan in place & staff in place | 
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 47: Integrated ERCOT Readiness and Transition (IRT) Project Budget Analysis

## Slide 48: IRT: Project Summary
Project area: Integrated ERCOT Readiness and Transition Project
Description: Preparation of the ERCOT organization and final verification of all parties’ readiness to operate under the Nodal Protocols in live operations.
Vendor(s): N/A
Project Manager: Steve Grendel
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Early Delivery System (EDS) strategy and plans ERCOT Readiness Criteria ERCOT Readiness & Transition Plans (by function) ERCOT readiness preparations EDS Market Trials ERCOT Readiness Declarations
Key Assumptions: Management of the EDS trials will be the responsibility of the IRT Project Team Planning and preparations for each ERCOT function will be the responsibility of the respective ERCOT Director
Challenges/Risks: Balance of staffing (including contractors and employees) between Zonal, Nodal program and Nodal transition activities
Comments: RFP process in progress for 3rd Party readiness advisor RFP process in progress for Transition experts

## Slide 49: IRT: Cost Summary
Cost drivers:
  EDS Labor Effort
  Internal (43%) / External (57%) labour cost
    Necessary for running two parallel environments (Zonal / Nodal) without adding significant FTEs
  Readiness Activities (393 significantly impacted FTEs)
    Average of 67 class-room training hours (IRT paying for attendance only)
    Average of 2 months of hands-on Nodal simulation (via EDSs)
  Multiple overlapping application environments to operate (Motes, EDS 3, EDS 4)
  Market Participant Registration, Financial & Operational Qualification
  3rd Party Market Readiness Advisor (MRA)
  Operating Guides, and internal procedures documents to update / maintain, training staff on process changes
11/04 CBA (KEMA)
Dimensions
6-10 months
$137.5/hour
35%
11/04 CBA assumptions:
  Includes documentation and 6 months of Trials
  Assumed 2 major trial activities (not the complexity envisaged in the EDS sequence)
  Excluded SAS70 audits
Dimensions
26 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Assumed 6 months of market trials
  Assumed significant effort by internal FTEs
  Assumed 6 months of pilot
Total
-
-
-
-
7,260,000
+47%
Total
2,770,425
6,464,326
713,020
722,380
10,670,151
+174%
Budget reduction options to be discussed with TPTF & TAC
  Reduce EDS 3 by 3 months. Start EDS 3 on April 1, 2008 with completion on Sept 30, 2008 Savings potential ~ $670k (Rejected by TPTF on 9/27-28/06)
  Internal/External Readiness Advisor Approach. Confirm readiness criteria by Feb 2007, track progress using internal resources for 7 month, starting 2008 use 3rd-party Savings potential ~ $1.1M
 | Total
Internal Resource Costs | 13,133,224
External Resource Costs | 16,146,615
Vendor Labor | -
Hardware, Software, misc. | -
Total | 29,279,839
 | Dimensions
Project duration | 34 months
Composite fee rate | $104.5 hour
Contingency (vs base) | (see summary)
9/06 Program Estimate

## Slide 50: IRT: Schedule and Resource Effort

## Slide 51: IRT: Budget Assumptions
Assumptions: Key project resources will transition from FAT to ITEST to EDS trial operations Impacts on Corporate divisions are not included in the IRT EAC Resources are available for the IRT Project as listed in the EAC EDS 3 and 4 will be treated as separate releases with different PM’s EDS 3 is required to run 9 full months, EDS 4 will last 4 months The full testing period will be required to achieve the exit criteria for each EDS The test harnesses/simulators used during ITEST will be sufficient to support EDS trials Applications entering EDS trials will not have level 1, 2 or 3 defects Each EDS is the incremental build of the ultimate TXMACS 1.0 environment and will include all redundancies and DR capabilities required for production EDS 3 and 4 will require 8x5 support except for the 168 hour test that requires 24x7 A 3rd party (Market Readiness Advisor) will be used to provide readiness assessments and dashboards The MER project will gather MP’s readiness status and provide this information to the IRT’s Market Readiness Advisor Trial and production hardware is included in the Infrastructure Project EAC All software licenses are included in other Nodal projects EAC’s through September 1st, 2009 Vendor software maintenance, warranty and technical support is the responsibility of the respective development project Vendor relationships will be transitioned to the “home team” just prior to Go Live Software maintenance, warranty and technical support contracts are a derivative of business SLA’s and negotiated by business and IT. This scope is not within the IRT charter Vendors will provide application training to both users and It support personnel that is specific to the ERCOT implementation. The costs for this training is covered by other projects in their EAC Infrastructure will be ready as outlined by the IRT build schedule (next slide) All extracts/market information will be available during the appropriate EDS Trails phase EDS 1 and 2 execution will occur in the NMMS and/or EMS project

## Slide 52: IRT: Budget Assumptions
Assumptions: Each EDS 3 and 4 will be built in a separate environment to allow subsequent EDS preparations to occur in a parallel fashion Market Participant qualification will be accomplished via EDS trails (in the EDS environment) IRT does not own the Nodal Program staffing strategies or execution IRT does owns ERCOT Nodal Organization Design IRT assumes all MPs will not have Severity 1,2 or 3 errors when entering an EDS. Nodal Qualification is assumed to be limited to LFC verification of individual resource. Assuming 40 level 4 QSE will be qualified for LFC related ancillary services. QSE qualification will be conducted in MOTE environments IRT will only budget for the cost of the home team to attend class-room training. The cost of development and delivery will be in MER's EAC and or within vendor contracts Business process training / job function training is included in the IRT budget. Performance / stress / load testing will be done during ITEST The EDS 3 environment will be reallocated after the completion of EDS 3 The EDS 4 environment will become production

## Slide 53: IRT: Build Schedule
MOTE 3 Server/Application build begins July 1st, 2007, ends October 1st, 2007
  Assumes that IRT is responsible for the MOTE build scheduling and execution
EDS 3 Server/Application build begins September 2nd, 2007, ends December 15th
  Assumes same system will be used for UAT
  Resources being unavailable during Holidays include in timeline
  Assumes capability to test local failover, site to site failover and DR for any systems based on business and supplemental requirements
MOTE 4 Server/Application build begins March 1st, 2008, ends April 29th, 2008
  Assumes that IRT is responsible for the MOTE build scheduling and execution
  Assumes smaller build due to MOTE 3
EDS 4 Server/Application build begins February 1st, 2008, ends April 1st, 2008
  Assumes smaller build due to production build in EDS 3
  Assumes this build is the final build before Go Live
  Assumes capability to test local failover, site to site failover and DR for any systems based on business and supplemental requirements

## Slide 54: IRT: Milestones Schedule

## Slide 55: IRT Confidence Matrix –Current Threats to Success
 | Current Status
Scope/Plans | Plans under developed
Resourcing | Contention for ERCOT SME’s
Costs | 
Timescales | Tracking to Plan
Critical dependencies | Key Resource Availability, Application Delivery
Business Modeling & Requirements | Current Review Continues Satisfactory
Analysis & Design | 
Vendors | N/A
External Stakeholders | N/A
Internal Stakeholders | 
Communications | Ongoing Director’s Communication Cascade
Overall | Key Resource Availability, Application Delivery
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 56: Integration and Design Authority (IDA) Project Budget Analysis

## Slide 57: IDA: Project Summary
Description: Business and technical architecture, design standards and design assurance for the Program
Vendor(s): IBM
Project Manager: Jeyant Tamby
Key deliverables/short term deliverables: Guidance on contracts and Vendor selection Overall business and technical architecture Strategies & Roadmaps – Integration, EDW, MIS, hardware, security, database hosting, UI design, XML standards RUP artifacts and training Technical architecture assistance Quality assurance Requirements traceability (e.g. RequisitePro) User interface standards
Key Assumptions: Current top-level business architecture is solid All systems will conform to the integrated Data Dictionary based on CIM standards Program will follow concepts of Rational Unified Process Methodology of iterative development All critical documentation will go through QA process
Challenges/Risks: Integration – across multiple projects, vendors and applications Quality and rework due to complexity and changes Testing Strategy for complex overall Nodal “system”
Comments:
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD

## Slide 58: IDA: Cost Summary
11/04 CBA (KEMA)
Dimensions
3 months
$137.5/hour
35%
11/04 CBA Assumptions:
  The numbers above only include Requirements Definition activities.
  It assumed that independent quality assurance will be provided by development groups and production support groups under different managers and teams (2004 ERCOT organization).
  These development groups work with vendors up till FAT; ITEST, UAT and Regression stages are performed by Production Support and Business Teams.
  Design fidelity and assurance was the responsibility of Release Management, Production Support and Business Owners.
  This organizational structure was abandoned in 2005.
Cost drivers:
  Consultants for additional capability in Business Architecture, Enterprise Architecture and Project Management
  IBM RUP training & adoption
  KEMA Study
  Software licenses (ReqPro, Business Process Modeler)
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Includes enhancement of technical delivery capability: RUP artifacts and training, solution architects, and delivery environment and tools (e.g. ReqPro)
  Excluded RUP/SDLC development
  Excluded RUP training
  Excluded Rational Tool suite
  Excluded external solution Architects
  Excluded Rational Support
 | Total
Internal Resource Costs | 1,020,825
External Resource Costs | 3,855,940
Vendor Labor | -
Hardware, Software, misc. | 1,893,961
Total | 6,770,726
Total
-
-
-
-
1,056,000
 | Dimensions
Project duration | 20 months
Composite fee rate | $121/hour
Contingency (vs base) | (see summary)
+92%
Total
476,049
1,110,781
194,460
241,260
2,022,550
9/06 Program Estimate
+235%
Budget reduction options to be discussed with TPTF & TAC
  None proposed

## Slide 59: IDA: Schedule and Resource Effort
2006
2008
2007
2009
Vendor Sourcing
Strategic
Vendor
Sourcing
Assurance
Requirements
Traceability
Enterprise
Architecture
Project Management
Architecture, Strategy, Standards & Approach, EA Organization Forum
RUP Training and Adoption
RUP
Quality Assurance & Certification, Design Issue Resolution
Project Start-up, Monitoring & Tracking
  Requirements Management, Configuration & Analysis

## Slide 60: IDA: Budget Assumptions
Assumptions: The core IDA team will comprise enterprise architecture and design assurance resources ERCOT FTEs will be supplemented by contractors/consultants to achieve the required capability and capacity Technical Architects (project-based) will be centrally coordinated but funded 100% by relevant projects starting on September 1, 2006. They will ramp down with their respective projects. Their contingency will also be managed by their respective projects IDA FTEs move to Home Team in December 2007

## Slide 61: IDA: Overview of current threats to success
 | Current Status
Scope/Plans | 
Resourcing | Non-nodal demands on internal IDA resources; Lack of external energy industry SMEs
Costs | 
Timescales | Potential slippage due to dependencies on projects
Strategic Vendor Sourcing | 
Enterprise Architecture | Delayed due to late start of resources
RUP Adoption | Late artifact definition
Requirements Traceability | 
Assurance | 
Overall | Resources and Timescales
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 62: Network Model Management System (NMMS) Project Budget Analysis

## Slide 63: NMMS: Project Summary
Description: Capability to generate Planning and Network Models for Real-Time, Day-Ahead and Future applications and studies
Vendor(s): Siemens Power T&D, Inc. (NMMS); Nexant, Inc. (Network Modeling & Telemetry)
Project Manager: Raj Chudgar
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Naming Conventions State Estimator Criteria Network Modeling & Telemetry (proof of required fidelity) Requirements for TPTF approval Conceptual System Design for TPTF approval Time based Network Operations and Planning Model Management System
Key Assumptions: Factory Acceptance Testing – Pre-FAT on vendor premises; FAT on ERCOT premises Zero severity 1 or 2 bugs coming out of FAT or ITEST
Challenges/Risks: Integration - multiple interface, one-liner and data dependencies (MMS, EMS, CRR, outage scheduler, registration) There are no vendors with prior experience with development of time-based models
Comments: ERCOT will be the first ISO to utilize time-based model functionality for down-stream applications

## Slide 64: NMMS: Cost Summary
11/04 CBA (KEMA)
Dimensions
12 months
$137.5/hour
35%
11/04 CBA Assumptions:
  Assumed 10 FTEs for 12 months
  Estimates included a new transaction software tool for model changes submittal and tracking with TDSPs
  Additional telemetry costs were not included
  Additional model testing and evaluation environments needed
  7-8 modelers to handle a 6-8 months of project transition period was expected
Dimensions
30 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Excluded 80-90% of NMMS is funded by Zonal (~$7MM)
  Excluded majority of model fidelity cost, assumed as part of ERCOT O&M budget
  Excluded naming convention cost
  Narrower scope of model fidelity work (cf Nexant)
 | Total
Internal Resource Costs | 1,045,200
External Resource Costs | 1,372,600
Vendor Labor | 10,121,621
Hardware, Software, misc. | 150,000
Total | 12,689,421
Total
-
-
-
-
2,640,000
 | Dimensions
Project duration | 24 months
Composite fee rate | $110/hour
Contingency (vs base) | (see summary)
-78%
Total
174,438
407,022
-
-
581,460
9/06 Program Estimate
+2,082%
Cost drivers:
  Zonal $11.5MM cost assumed as part of budget
  Project Mgt, SME Consultants to supplement internal capability, support requirements & architecture are from many consulting firms
  Model Fidelity work as directed by TAC approved SE and Telemetry criteria
  TDSP coordination and assimilation into NMMS solution
  Siemens Licenses and Maintenance
Budget reduction options to be discussed with TPTF & TAC
Structural options:
  Ramp Nodal SE criteria to Zonal fidelity & eliminate EDS 1/2 with MPs Savings potential ~ $5M (Rejected by TPTF on 9/27-28/06 – contrary to Protocols)
  Elimination of time-based models/NMMS Savings potential ~ $7.5M (Rejected by TPTF on 9/27-28/06 – contrary to Protocols)
Cost reduction options:
  Elimination of planning time based models Savings potential ~ $1M (Rejected by TPTF on 9/27-28/06 – contrary to Protocols)

## Slide 65: NMMS: Schedule and Resource Effort
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
NMMS
Planning UI
FAT
ITEST
Naming Convention DB
Common model update process
NMMS Conceptual Design
Naming Convention information collection
Model Data Certification
Model Data Remediation Reconciliation
NMMS Build
Operations UI
EDS 1/2
3/31/08 Single Entry Model GO LIVE

## Slide 66: NMMS: Budget Assumptions
Assumptions: Zonal work will gradually taper off in 2007 and 2008 and the remainder of Network Model operations staff will move to ERCOT Readiness project No Major change controls that affect Network Modeling project overall budget or schedule will be accepted All performance and integration issues can be solved with KNOWN technology All data outputs to other systems will be point to point All data from upstream systems will be provided under Network Modeling format specifications No significant diversion of current Network Modeling Staff to alternative Nodal or Zonal work EMS data dictionary can be provided early TSPs can provide updates or changes to model within a quick turnaround or provide a detailed plan for model data issues

## Slide 67: NMMS: Overview of current threats to success
 | Current Status
Scope/Plans | Extent of Model updates being defined
Resourcing | Core team complete; known threat to staff instability
Costs | 
Timescales | Model correction timelines at risk
Critical dependencies | TSP involvement; Vendor timeline; Integration
Business Modeling & Requirements | 
Analysis & Design | 
Vendors | 
External Stakeholders | Road show to educate solution
Internal Stakeholders | 
Communications | Network Modeling Forum
Overall | Resourcing, timeline, and critical dependencies
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 68: Energy Management System (EMS) Project Budget Analysis

## Slide 69: EMS: Project Summary
Description: Implement the necessary changes to ERCOT’s current Energy Management System (EMS) and implement the new Renewal Production Potential (RPP) function to satisfy the requirements set forth in the Texas Nodal Protocols approved by Order signed by the PUCT on April 5th, 2006. At the same time, upgrade the ERCOT EMS
Vendor(s): Requirements KEMA, AREVA (EMS, LF), AWS True Wind (RPP)
Project Manager: Al Hirsch
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Requirements for TPTF approval Conceptual System Design for TPTF review EMS platform upgrade & ERCOT customizations Full ICCP capability Network Security upgrade and Load Frequency Control Migration of enhanced Zonal Load Forecast to Nodal New RPP
Key Assumptions: Factory Acceptance Testing – Pre-FAT on vendor premises; FAT on ERCOT premises Zero severity 1 or 2 bugs coming out of FAT or ITEST
Challenges/Risks: Resource bottlenecks are delaying completion of business requirements for this critical path project Integration - multiple interfaces and data dependencies between the EMS and other systems (MMS, NMMS, Settlements, OS, etc.) Vendor Capability to deliver new software and application according to the Nodal Program timeline
Comments: Established mutually positive and collaborative relation with AREVA Reconstituting viable EMS team

## Slide 70: EMS: Cost Summary
Dimensions
9 months
$137.5/hour
35%
11/04 CBA assumptions:
  Assumed single vendor for EMMS (EMS, MMS & CRR)
  Included modifications to Operator Actions, Real Time Sequence and Dispatch (LFC and SCED), NSA Study Network Apps, procurement of LMP calculator and AS Monitoring
  Excluded Load Forecast, Outage Scheduling and Operator Training Simulator
Cost drivers:
  EMS upgrade, previously assumed to be part of Zonal, included in the Nodal implementation.
  New development in the EMS systems, specially LFC, to fulfill the Nodal requirements
  Renewable Production Potential system will be also part of the nodal implementation
  Major EMS/NMMS interface will be implemented along with the Texas Nodal Market
  Different vendor in the MMS system increased complexity of EMS/MMS interfaces
  New Outage Scheduler
Dimensions
18 months
$100/hour
25%
12/05 Assumptions:
  Assumed 50% Network Security upgrade funded by Zonal
  Assumed EMS upgrade was Zonal
  Assumed OTS scope narrower (expanded as a result of ABB MMS selection)
11/04 CBA (KEMA)
12/05 High-Level Estimate
 | Total
Internal Resource Costs | 4,333,160
External Resource Costs | 794,565
Vendor Labor | 10,104,225
Hardware, Software, misc. | 2,259,000
Total | 17,490,950
Total
-
-
-
-
5,770,000
 | Dimensions
Project duration | 32 months
Composite fee rate | $88/hour
Contingency (vs base) | (see summary)
-26%
Total
498,920
1,164,148
1,294,920
1,294,920
4,252,908
9/06 Program Estimate
+311%
Budget reduction options to be discussed with TPTF & TAC
  None proposed

## Slide 71: EMS: Schedule and Resource Effort
EMS (Energy Management System)
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
EMS1-2
EMS1/2 FAT ITEST
EMS Requirements, Conceptual Design
Business Requirements complete 10/30
EMS 3
EMS 3 FAT/ ITEST
EMS 4
EMS 4 FAT/ITEST
RPP DEV AWS
RPP FAT/ITEST
Renewable Potential Production (RPP)
RPP DEV ERCOT
EDS 1/2
Outage Scheduler
OS ITEST
OS Build
OS FAT
OS Requirements, Conceptual Design
Begin Ramp-down
OS Complete 7/1
Business Requirements complete 10/30
EDS
EDS 3
EDS 4
Go-live Trans.
EDS 3 Mote & ERCOT UAT

## Slide 72: EMS: Budget Assumptions
Assumptions: Assuming no delays due to Network Model or State Estimator Validation NMMS/EMS interface will be defined and operational on time to generate EMS models and databases. If not, assuming manual modeling using current AREVA’s GENESYS System Load Forecast requirements will be gathered for the Nodal implementation. However, at this time no development is expected, migrating from current Zonal system into the Nodal systems. EMS Upgrade will have a phased approach, starting with AREVA EMP 2.3 / Habitat 5.6 platform Development of new Nodal functionality will occur on application basis, to meet EDS development Resources in the EMS package will transition into subsequent packages RPP contracted as a subscription forecasting service. Monthly RPP subscription fee in EAC until Q3-2008 No SW license maintenance is included in the EMS EAC Vendor ITEST maintenance is not included in the EMS EAC Development of a Nodal OTS will be deferred beyond the initial release of Nodal (to be the subject of a Change Request). The Early Delivery Systems will be used for Operator training for Go Live

## Slide 73: EMS: Overview of current threats to success
 | Current Status
Scope/Plans | Approval process caused delays; Lack of SMEs for delivery review
Resourcing | Long term resources identified but need to be filled
Costs | 
Timescales | Behind schedule in the requirements definition
Critical dependencies | Business SME resource staffing constraints
Business Modeling & Requirements | Behind Schedule
Analysis & Design | 
Vendors | 
External Stakeholders | 
Internal Stakeholders | Key resources performing production support task in the Zonal System
Communications | Improve EMS ability to communicate with TPTF and Market Participants
Overall | Behind Schedule
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 74: Market Management System (MMS) Project Budget Analysis

## Slide 75: MMS: Project Summary
Description: Business processes and systems for the Nodal Real-Time and Day-Ahead Energy and AS Markets and Outage Scheduler
Vendor(s): ABB, Inc.
Project Manager: Al Hirsch
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Requirements for TPTF approval Conceptual System Design for TPTF approval Day Ahead Market capability Supplemental AS Market capability Reliability Unit Commitment capability Security Constrained Economic Dispatch (Real Time Market) capability DC Tie Data for Wholesale Market Monitoring Outage Scheduler (Added November 2006)
Key Assumptions: Factory Acceptance Testing – Pre-FAT on vendor premises; FAT on ERCOT premises Zero severity 1 or 2 bugs coming out of FAT or ITEST
Challenges/Risks: Inadequate or Flawed Nodal System Design – Critical impact to performance, robustness, dependability, reliability Integration, Architecture & System Construction - multiple interface and data dependencies causing major impacts to schedule, cost, operation Substantial rework over the extended life of the project impacting schedule, cost & performance due to directed changes
Comments: ABB is fully committed and has stepped up as a member of the joint project team

## Slide 76: MMS: Cost Summary
Dimensions
15 months
$137.5/hour
35%
11/04 CBA Assumptions:
  Auction-based DAM will be implemented prior to Nodal; related ADAM costs considered sunk.
Cost drivers:
  Significant cost driver is splitting early delivery of SCED from balance of MMS
  Significant cost driver is lack of system design/specification prior to start of MMS design
  Secondary cost driver is length of “market trials” following development
  Secondary cost driver is lack of SMEs from existing ERCOT staff
Dimensions
30 months
$100/hour
25%
12/05 Assumptions:
  One (1) build cycle
  Excluded multiple market trials
  Included significant ERCOT staff available for development
11/04 CBA (KEMA)
12/05 High-Level Estimate
 | Total
Internal Resource Costs | 3,409,120
External Resource Costs | 6,007,200
Vendor Labor | 13,500,000
Hardware, Software, misc. | 3,355,000
Total | 26,271,320
Total
-
-
-
-
3,762,000
 | Dimensions
Project duration | 20 months
Composite fee rate | $101/hour
Contingency (vs base) | (see summary)
+190%
Total
1,485,792
3,466,848
2,983,200
2,983,200
10,919,041
9/06 Program Estimate
+141%
Budget reduction options to be discussed with TPTF & TAC
Structural options:
  Single release of MMS Savings potential ~ $1M (Rejected by TPTF on 9/27-28/06 – contrary to ERCOT Transition Plan)
  Divert ERCOT resources from Zonal projects Savings potential ~ $2.5M
  Eliminate vendor support through EDS Savings potential ~ $3.5M

## Slide 77: MMS: Schedule and Resource Effort
MMS
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
MMS ITEST
Begin Ramp-down
Business Requirements complete 10/30
Base Software 4/13
SCED/MMS Requirements
MMS FAT
MMS Build
SCED FAT complete 7/1
SCED Build
SCED FAT
SCED ITEST
EDS
EDS 3
EDS 4
Go-live Trans.
EDS 3 Mote & ERCOT UAT

## Slide 78: MMS: Milestone Schedule

## Slide 79: MMS: Budget Assumptions
Assumptions: MMS installed as Black Box with COTS Standard Transfer Function (No Customs) FAT on site at ERCOT (No FAT at vendor site) Minimal level of MMS Project Technical Staff support for ITEST and EDS (8/15 - Changed to add required Bus/Proj Staff) Budget includes technology/operational knowledge transfer to ERCOT staff sufficient to operate and support All custom work is limited to Nodal Protocol compliance and User Interface Screen Layout All standard product security and access authorizations included Total releases limited to original plus two (2) Input data will be direct from Market Participant/Operator Interface and other sub-systems (Portals) without edit/manipulation Key Resource staffing will be provided timely with Texas Nodal orientation provided prior to joining MMS project (No budget in MMS) All ERCOT approvals will be provided timely and expeditiously within time period budgeted in schedule TPTF Approval Cycle will not exceed three (3) weeks

## Slide 80: MMS: Overview of current threats to success
 | Current Status
Scope/Plans | 
Resourcing | 
Costs | 
Timescales | RT/RUC/SCED
Critical dependencies | Internal Key Resource Availability
Business Modeling & Requirements | 
Analysis & Design | 
Vendors | 
External Stakeholders | 
Internal Stakeholders | Internal stakeholders have yet to engage
Communications | See Internal Stakeholders
Overall | Internal Collaboration & Impact Mitigation
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 81: Congestion Revenue Rights (CRR) Project Budget Analysis

## Slide 82: CRR: Project Summary
Project area: Congestion Revenue Rights
Description: Business processes and systems to allow the CRR Owner to be charged or receive compensation for congestion rents that arise when the ERCOT Transmission Grid is congested in the Day-Ahead Market (DAM) or in Real-Time
Vendor(s): Nexant, Inc.
Project Manager: Shawna R. Jirasek
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Short term deliverables: Requirements for TPTF approval, Conceptual System Design for TPTF approval Key deliverables: PCRR and MCFRI allocation capability CRR auction capability CRR ownership tracking capability and Bilateral trading capability
Key Assumptions: Factory Acceptance Testing – Pre-FAT on vendor premises; FAT on ERCOT premises Zero severity 1 or 2 bugs coming out of FAT or ITEST
Challenges/Risks: New CRR process to ERCOT, new technology to ERCOT, and implementation different than that in other ISOs Integration - multiple interface and data dependencies (NMMS, MMS, Registration, Settlement, Credit Monitoring) Early CRR delivery – may result in rework to fit into integrated Nodal program
Comments: Solution vendor accepting fast delivery timeline Market Participant specialist on board and integrated in the project team

## Slide 83: CRR: Cost Summary
Dimensions
14 months
$137.5/hour
35%
11/04 CBA Assumptions:
  Tighter and more complex interactions with Planning and Operations Engineering models and staff.
  Assumed new products, new 3rd party software; considered new SW license costs.
Cost drivers:
  Untested nodal protocols; protocol design decisions increase costs
  Complicated solution requiring highly specialized SME and vendor knowledge
  Fixed price software development contract with perpetual license
  Early delivery of completed CRR product
  Entirely new CRR business processes and ongoing business team
  No CRR ‘Home-Team’ in the ERCOT business until 2008
Dimensions
30 months
$100/hour
25%
12/05 Assumptions:
  Excluded CRR statements and bills (COMS)
  Excluded credit limit generation (COMS)
  Excluded Registration (COMS)
  Excluded CRR interface with MMS (MMS)
11/04 CBA (KEMA)
12/05 High-Level Estimate
 | Total
Internal Resource Costs | 1,065,480
External Resource Costs | 1,800,840
Vendor Labor | 792,000
Hardware, Software, misc. | 2,600,186
Total | 6,258,506
Total
-
-
-
-
5,580,000
 | Dimensions
Project duration | 21 months
Composite fee rate | $128/hour
Contingency (vs base) | (see summary)
-20%
Total
1,346,400
3,141,600
-
-
4,488,000
9/06 Program Estimate
+39%
Budget reduction options to be discussed with TPTF & TAC
Structural options:
  Direct allocationto loads Savings potential ~ $5M (Rejected by TPTF on 9/27-28/06 – contrary to Protocols)
Cost reduction options:
  Reduce scope to exclude Multi-Period Auction Optimization Savings potential ~ $0.5M

## Slide 84: CRR: Schedule and Resource Effort
Congestion Revenue Rights
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
EDS 4 ITEST
Ramp-down complete
Business Requirements complete 10/30
Base software installed 12/15
CRR Requirements Design, Build, Pre-FAT
CRR FAT
CRR “Pre-ITEST”
FAT complete 7/1
EDS
EDS 3
EDS 4
Go-live Trans.
EDS 3 Mote & ERCOT UAT

## Slide 85: CRR: Key Milestones

## Slide 86: CRR: Budget Assumptions
Assumptions: ERCOT will hire fulltime CRR Market Operators (~6) as additional Home Team staff to be carried in the project budget until 2008 ‘Stub data’ from CRR interfacing systems will be available in February 2007 CRR will finish development, documentation, and FAT by July 2007. However, if multi-period annual auctions are eliminated, FAT could be completed by May 2007 FAT will be supported by the Integration Testing project (INT) Vendor cost for development of multi-period annual auctions is <$500k (NPRRs in-flight) CRR will complete ITEST with the other applications in EDS 4 but will also conduct a 3 month Pre-ITEST During ITEST there will be two FTEs assigned half-time to serve as ITEST liaisons CRR team will test and validate the newly created business processes following Pre-ITEST and prior to handing over to the business at the end of 2007 Vendor consulting time will be for practice allocation and auction (outside software customization costs) Some CRR team travel to vendor site will be necessary

## Slide 87: CRR: Overview of current threats to success
 | Current Status
Scope/Plans | September 2005 to August 2006 Protocols Impact being assessed
Resourcing | Core team; contention for ERCOT SME’s
Costs | 
Timescales | 
Critical dependencies | Internal Key Resource Availability; Vendor SOW
Business Modeling & Requirements | Feasibility of Protocols Undetermined
Analysis & Design | Unproven Capability/Solution
Vendors | 
External Stakeholders | 
Internal Stakeholders | 
Communications | 
Overall | Unproven Capability/Solution
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 88: Commercial Systems (COMS) Project Budget Analysis

## Slide 89: COMS: Project Summary
Project area: Commercial Systems
Description: Business processes and systems for Settlements and Billing, Data Aggregation, Metering, Load Profiling, Credit Monitoring, Registration, Disputes, Financial Transfer
Vendor(s): LODESTAR®, Siebel®, ROME®
Project Manager: Raj Chudgar
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Requirements for TPTF approval Settlement payments and charges for Day Ahead, RUC, Real Time, Ancillary Services, and CRRs Credit monitoring and management capabilities Invoicing capabilities Registration capabilities Disputes capabilities Financial Transfer capabilities
Key Assumptions: Zero severity 1 or 2 bugs coming out of FAT or ITEST
Challenges/Risks: Integration - multiple interface and data dependencies Probability of substantial re-work due to scope changes/clarifications introduced in Real-Time and Day-Ahead requirements
Comments: Nodal necessitates a complete re-write of Settlement due to volume of data and new methods of calculation ERCOT is leading the Settlement development internally

## Slide 90: COMS: Cost Summary
Dimensions
18 months
$137.5/hour
35%
11/04 CBA assumptions:
  Included Registration, MMS to COS interface, Data Aggregation, Credit and Risk Management, Settlements, Post LMP Mitigation and Dispute Resolution
Cost drivers:
  Sheer effort to re-write settlements (150,000 effort hours)
  Project Management, SME Consultants to supplement internal capability, support requirements & architecture are from many consulting firms
  ROME Licenses and Maintenance
  Additional Lodestar/Siebel Licenses
  Scope dictated by upstream systems
  High susceptibility to change requests
Dimensions
30 months
$100/hour
25%
12/05 Assumptions:
  Excluded training for settlements (MER)
  Excluded any changes to zonal settlements
  Excluded extracts (EDW)
  Excluded CRR settlements (CRR)
11/04 CBA (KEMA)
12/05 High-Level Estimate
 | Total
Internal Resource Costs | 5,561,400
External Resource Costs | 5,112,200
Vendor Labor | 3,905,235
Hardware, Software, misc. | 200,000
Total | 14,778,835
Total
-
-
-
-
8,844,000
 | Dimensions
Project duration | 27 months
Composite fee rate | $95/hour
Contingency (vs base) | (see summary)
+3%
Total
2,724,492
6,357,147
-
-
9,081,638
9/06 Program Estimate
+63%
Budget reduction options to be discussed with TPTF & TAC
Structural options:
  None proposed
Cost reduction options:
  None proposed

## Slide 91: COMS: Schedule and Resource Effort
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
Commercial Systems
Statements Layout
Script test
Commercial Systems Design, Build, Pre-FAT
CS FAT
ITEST
CS Requirements, Conceptual Design
Registration ready
EDS
EDS 3
EDS 4
Go-live Trans.
EDS 3 Mote & ERCOT UAT

## Slide 92: COMS: Budget Assumptions
Assumptions: ERCOT, with vendors, will complete all Business requirements by 10/31 ERCOT, with vendors, will create CSDs by end of 2006 All performance issues can be solved with existing application technology All data inputs from other systems will be as defined by Commercial Systems team ERCOT has sufficient staff for all Commercial System projects, and currently dedicated staff is not redirected to other projects ERCOT Commercial System Zonal projects will ramp down in 2007 and 2008 Vendor price quotes will not significantly change going forward Mini-Settlements and Billing development team (business and IT) will stay in project team until the end of project to support late changes and defects Go Live implementation strategy does not require additional manual or automated workarounds to settle the market

## Slide 93: COMS: Overview of current threats to success
 | Current Status
Scope/Plans | 
Resourcing | Resources being pulled for Zonal (eg. RPRS)
Costs | 
Timescales | Prototype slightly behind schedule
Critical dependencies | All upstream systems data
Business Modeling & Requirements | 
Analysis & Design | Settlement performance capability
Vendors | 
External Stakeholders | 
Internal Stakeholders | 
Communications | 
Overall | Upstream applications and performance, and resources
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 94: Enterprise Data Warehouse (EDW) Project Budget Analysis

## Slide 95: EDW: Project Summary
Description: Capability to collect historic data and provide information services to MPs, PUCT, WEMM and FERC, perform data analysis.
Vendor(s): N/A
Project Manager: Sylvia Shiroyama
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: EDW strategy and roadmap EDW Governance structure Requirements for TPTF approval Business Intelligence – dynamic reporting (CDW framework) Business Intelligence – standard reporting (including internal, MOMS, Market, Compliance, Credit reporting) Operational Data Stores (including Lodestar, EMMS ODS) Market data extracts Information replication (ODS, RSS replication)
Key Assumptions: EDW is a shared asset across ERCOT Zero severity 1 or 2 bugs coming out of FAT or ITEST
Challenges/Risks: Impact of extensive schema changes will require all output types to change EDW governance Requirements for extract capability rather than extracts will cause the subjects and volumes of data to grow significantly along with the implications of supporting and managing that data from an operational perspective
Comments: EDW Project Manager started 9/5/06 ERCOT is leading the EDW development internally

## Slide 96: EDW: Cost Summary
Dimensions
12 months
$137.5/hour
35%
11/04 CBA assumptions:
  Included Performance Monitoring changes and Nodal driven enhancements to general data extracts and reporting capabilities. A substantial EDW replacement project was under way at the time of the study therefore major EDW system changes were not included
Cost drivers:
  Number of new databases / systems
  Schema changes to existing systems
  External resource needs
  Data volumes
  Data latency to EDW
  Data retention
  Capture frequency
  Increased information services for ERCOT, PUCT, IMM, ERO, and Market
  IMM, ERO requirements least known
Dimensions
23 months
$100/hour
25%
12/05 Assumptions:
  Assumed substantial leveraging of Zonal
  Assumed leveraged zonal technology
  Excluded Compliance (ERO) reports
  Excluded rebuilding zonal extracts/reports
11/04 CBA (KEMA)
12/05 High-Level Estimate
 | Total
Internal Resource Costs | 2,492,800
External Resource Costs | 1,544,000
Vendor Labor | -
Hardware, Software, misc. | -
Total | 4,036,800
Total
-
-
-
-
1,452,000
 | Dimensions
Project duration | 32 months
Composite fee rate | $82/hour
Contingency (vs base) | (see summary)
+72%
Total
749,820
1,749,579
-
-
2,499,399
9/06 Program Estimate
+62%
Budget reduction options to be discussed with TPTF & TAC
Structural options:
  EDW latency, retention, access (Program team to put forward options)
Cost reduction options (savings potential 5%-10%):
  Reduced extract flexibility - a reduced number of views and subject tables would reduce cost. It would result in less ability to integrate data sources Savings potential ~ $0.5M

## Slide 97: EDW: Schedule and Resource Effort
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
EDW
EDW FAT
ITEST
EDW Requirements, Conceptual Design
EDW Design, Build, Pre-FAT
EDS
EDS 3
EDS 4
Go-live Trans.
EDS 3 Mote & ERCOT UAT

## Slide 98: EDW: Budget Assumptions
Assumptions: ERCOT business & Nodal projects will determine the tables to be replicated into the ODS At least 6 EIS FTEs will be involved in the Nodal EDW development All replication objects will be delivered at the same time as the project Extracts and standard reports identified in source system design will be delivered within 3 months of project FAT Resources are fungible and can be easily trained; will require additional staff to execute the nodal EDW project The cost estimate is based on currently known requirements All EDW hardware and software estimates are included in the Infrastructure project 20-25% level of EDW Project Technical Staff support for ITEST FAT will be supported by the Integration Testing project (INT)

## Slide 99: EDW: Overview of threats to success
 | Current Status
Scope/Plans | Charter not signed off
Resourcing | 5 dedicated resources, PM joined 9/5
Costs | Not identified yet
Timescales | High level timeline established
Critical dependencies | Not identified
Business Modeling & Requirements | Not started
Analysis & Design | Solution has been established
Vendors | Not known
External Stakeholders | Good relationship with PUCT, others are unknown
Internal Stakeholders | Governance model to be established
Communications | Communication plan to be established
Overall | Scope not established
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 100: Infrastructure (INF) Project Budget Analysis

## Slide 101: INF: Project Summary
Project area: Infrastructure
Description: Provision of development, testing, EDS and production environments across the Program
Vendor(s): IBM, EMC, Oracle
Project Manager: David Forfia
Budget: TBD
Actuals YTD: TBD
Actuals Total: TBD
Key deliverables/short term deliverables: Hardware specifications Hardware procurement Data center capacity resolution IT Services Catalogue Service Level Agreements for all Nodal projects Project development & test (FAT) environments Integration testing (ITEST) environments EDS environments Production environments
Key Assumptions: Infrastructure capacity can be incrementally added using IBM’s capacity upgrade on-demand model ICCP communications infrastructure included in EMS project
Challenges/Risks: Existing Data Center capacity (power)
Comments: IT Operations will be one of the first ERCOT function to transition to Nodal operations, starting with setting up development environments

## Slide 102: INF: Cost Summary
Dimensions
10 months
$137.5/hour
35%
11/04 CBA assumptions:
  Included facilities labor and activities (modifications to existing datacenters and work area and incremental hardware
  At the time ERCOT had just renovated their EMMS hardware and TCC 2 was under construction
Cost drivers:
  Number of distinct environments operating concurrently
  New enterprise class server platform adopted 7/2006
  Data center power and space recovery
  Accelerated deployment schedule of 1Q2007
Dimensions
27 months
$100/hour
25%
12/05 Assumptions:
  Included all standard OS costs
  Included all Oracle licenses
  Included all hardware licensing and maintenance costs
  Included internal labor to build hardware
  Assumed adequate Data Center capacity
11/04 CBA (KEMA)
12/05 High-Level Estimate
 | Total
Internal Resource Costs | 2,191,800
External Resource Costs | 5,547,520
Vendor Labor | 1,759,300
Hardware, Software, misc. | 52,341,787
Total | 61,840,407
Total
-
-
-
-
10,600,000
 | Dimensions
Project duration | 30 months
Composite fee rate | $108/hour
Contingency (vs base) | (see summary)
+210%
Total
724,800
1,691,200
-
30,487,455
32,903,455
9/06 Program Estimate
+88%
Budget reduction options to be discussed with TPTF & TAC
Structural options:
  Reduce the number of concurrent deployed environments. Savings potential ~ $8M
  Fund Zonal Unix end of life and storage projects. Savings potential ~ $17M
Cost reduction options:
  Reduce database and integration software license costs. Savings potential ~ $2M
  Reduce data retention period. Savings potential ~ $2-3M
  Allow cost recovery of ongoing maintenance, database license fees and hardware residual value to fund Nodal. Savings potential ~ $5M

## Slide 103: The budget is significantly influenced by the recommended timeline Nodal Market & Zonal Shutdown December 2008
EDS 3 Release
NMMS
Computing Infrastructure
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
EDS 3
Design, Build, Pre-FAT
FAT
ITEST
12/01/08 Real Time Operations GO LIVE
ITEST
Build
FAT
Requirements, Conceptual Design
Requirements, Conceptual Design
EDS 4
EDS 3 Data Validation
Planning UI
FAT
ITEST
Common model update process
Conceptual Design
Build
6/30/08 LMP Market Readiness Criteria MET
Q3 2007
Operations UI
3/31/08 Single Entry Model GO LIVE
12/08/08 Day Ahead Market/CRR GO LIVE
Zonal Shutdown GO/NO GO
Storage
Software
Data Center Capacity
Design to Min Requirements
Database Licensing Strategy
Portal/Integration Licensing Strategy
Decommissioning plan
Data center virtualization
Colocation
Existing Data Center Upgrade
New Data Center Facility
EDS 4 Release
Capacity Upgrade
Dev Disaster Site #1
Design to Min Requirements
Prod #1
Prod #2
Dev DR #2
Capacity needs met?
Capacity Planning
Capacity Upgrade on Demand Enabled
Sufficient Power Recovered ?
Sufficient Power Recovered ?
Capacity Upgrade
Initial Storage Upgrade
Capacity Planning
Capacity Upgrade
Capacity Upgrade
Capacity Upgrade
Capacity Upgrade

## Slide 104: INF: Schedule and Resource Effort
Q2 2008
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q1 2008
Q3 2006
Q1 2009
Q3 2007
Shared Service Deployment
Phase 1 Nodal FAT CDW Dev & PTEST
Phase 2 CDW Itest Nodal Production #1
Phase 3 CDW/Nodal Production Cluster
Phase 4 Nodal Disaster Recovery Cluster
Phase 5 Hardware Upgrade DR Site
Phase 6 Hardware Upgrade Production
Vendor Development Environments Purchased
EMS Environment Builds
Logical configuration of Shared Environments
Project Based Deliverables

## Slide 105: INF: Budget Assumptions
Assumptions: Sufficient data center capacity can be reclaimed at both data centers to house the Nodal infrastructure Sufficient effort exists in the deployment plan and contingency to meet the needs of both the Nodal and any Zonal equipment retirements necessary to reclaim the data center capacity ERCOT IT staff will be capable of operating the new infrastructure and database infrastructure in a production environment in Q1 2007 Multiple logical release environments can be deployed on the same server without violating security policy Only enhancements are necessary to the networking infrastructure to meet the Nodal requirements Operations testing and load profiling can be completed at the IBM test lab ERCOT Deployment of IBM’s P6 based architecture will occur in Q3 2007 ICCP costs included in EMS project

## Slide 106: INF: Overview of current threats to success
 | Current Status
Scope/Plans | 
Resourcing | SME balance between zonal operations and nodal installation
Costs | 
Timescales | Delivery Timeframe for environments significantly accelerated
Critical dependencies | Data center capacity recovery
Business Modeling & Requirements | Project level capacity plans not complete
Analysis & Design | 
Vendors | 
External Stakeholders | 
Internal Stakeholders | 
Communications | 
Overall | Delivery of shared infrastructure no longer on program critical path
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 107: Integration and Product Testing (INT) Project Budget Analysis

## Slide 108: INT: Cost Summary
Dimensions
6 months
$137.5/hour
35%
11/04 CBA assumptions:
  ERCOT integration Testing and User Acceptance Testing
  6 months and 17 FTEs
  Use of automated Regression Testing tools limited to Commercial Systems
  Release Management Department already owned those tools
  EMMS regression testing limited to the utilization of project developed Test Scripts
Cost drivers:
  Testing scope:
    Smoke (1% of functional testing)
    Functional (for CRR, MIS, EDW)
    Integration (all)
    Security (all)
    Regression (5% of functional testing)
    Performance (all)
  50/50 internal/external staffing
Dimensions
30 months
$100/hour
25%
12/05 Assumptions:
  Assumed 1 ITEST phase
  Assumed composition included significant ERCOT FTE staff
11/04 CBA (KEMA)
12/05 High-Level Estimate
 | Total
Internal Resource Costs | 4,691,272
External Resource Costs | 11,349,461
Vendor Labor | -
Hardware, Software, misc. | 936,650
Total | 16,977,383
Total
-
-
-
-
2,640,000
 | Dimensions
Project duration | 32 months
Composite fee rate | $88/hour
Contingency (vs base) | (see summary)
+179%
Total
1,608,737
3,753,721
972,300
1,019,100
7,353,858
9/06 Program Estimate
+131%
Budget reduction options to be discussed with TPTF & TAC
  None proposed

## Slide 109: INT: Schedule and Resource Effort

## Slide 110: INT: Budget Assumptions
Assumptions: COMS/NMMS/MMS/EMS projects are responsible for All functional testing of their projects Creation of Test Cases and Test Scripts for their projects using the templates provided by INT Requirements-driven non-integrated performance testing of their projects Creation of any stub-ins and test data required for functional testing of their projects Tracking all defects from their projects using Quality Center Delivering completed Test Cases and Test Scripts for their projects to INT prior to the beginning of FAT Meeting the exit criteria for FAT and the entrance criteria for ITEST INT is responsible for the following for COMS/NMMS/MMS/EMS projects Ensuring Quality Center is available to COMS/NMMS/MMS/EMS for functional testing and for training COMS/NMMS/MMS/EMS on its use Developing Smoke and Regression suites from the test scripts delivered by COMS/NMMS/MMS/EMS INT will provide four or five resources, funded by INT, to the FAT process for the purpose of establishing sustainable processes for testing COMS/NMMS/MMS/EMS. These resources will have full access to all project documentation, full access to all subject matter experts, and full access to the FAT environment and systems. INT is responsible for integration testing INT is responsible for the following for CRR/EDW/MIS projects All functional testing of their projects Creation of Test Cases and Test Scripts Requirements-driven non-integrated performance testing Creation of any stub-ins and test data required for functional testing Tracking all defects using Quality Center INT is responsible for integration testing INT is responsible for integration performance testing

## Slide 111: INT: Budget Assumptions
Assumptions: Budget begins in February of 2006, no budget impacts prior to 2/1/2006 Budget does not include development of any software Budget does include development of testing tools and testing tool environments Budget does not include any assistance, training, or development required of INT by FAT (performed by other project teams), EDS, UAT, MOTE, or Market Participant testing Contractors are all-inclusive All hardware expenses for the ITEST environment have been transferred to Infrastructure and will not be managed by INT The infrastructure team will staff resources necessary to build the ITEST environment (physical and hardware) Budget includes staff necessary to migrate applications to ITEST and support them during testing phases Budget assumes releases will follow the Program schedule as detailed in BOD presentation v0.10. Turn-around time for defects will be minimal and will not be managed by INT Release management will be funded by INT Applications migrating into ITEST will have no severity 1, 2, or 3 defects COMS, NMMS, EMS, and MMS will have full accountability for and will pay for the expenses related to full functional testing including requirements driven non-integrated performance testing. INT will not perform functional testing for COMS, NMMS, EMS, or MMS including requirements driven functional performance testing The ITEST environment will include one complete end to end environment sized like production plus one environment sized to handle NMMS stand-alone (production like) and one environment capable of handling one-off integration point testing Configuration of the complete end to end ITEST will be identical to EDS (Production) The ITEST environment will not be integrated with the Retail test system All data required from Retail will be stubbed in

## Slide 112: INT: Overview of current threats to success
 | Current Status
Scope/Plans | Revised WBS for New Schedule
Resources | 
Costs | 
Timescales | 
Critical dependencies | 
Business Modeling & Requirements | N/A
Analysis & Design | 
Vendors | 
External Stakeholders | N/A
Internal Stakeholders | Final FAT Plan for EMS & MMS
Communications | 
Overall | Upstream Project Dependencies
 | Major threat (or unknown) – “hair of fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 113: Enterprise Integration (EIP) Project Budget Analysis

## Slide 114: EIP: Cost Summary
11/04 CBA (KEMA)
Dimensions
6 months
$137.5/hour
35%
11/04 CBA assumptions:
  Assumed 6 months & 17FTE
  Assumed single vendor for EMMS (EMS, MMS & CRR) – hence majority of effort was needed on MMS to Lodestar, EMMS to EDW, EMMS to MP User Interface.
  All interfaces point to point using Oracle gateways
Cost drivers:
  Number of interfaces (200)
  Number of critical applications where backup solution (P2P) is needed
  ECIM definitions (400-600)
  Common integration infrastructure that can be leveraged
  Large number of external staff required
Dimensions
15 months
$100/hour
25%
12/05 High-Level Estimate
12/05 Assumptions:
  Integration assumed to be within projects thus SOA would leverage Zonal resources and cost when needed
  Included integration effort within base projects
11/04 CBA (KEMA)
12/05 High-Level Estimate
 | Total
Internal Resource Costs | 2,917,200
External Resource Costs | 7,799,200
Vendor Labor | -
Hardware, Software, misc. | 1,607,460
Total | 12,323,860
Total
-
-
-
-
2,244,000
 | Dimensions
Project duration | 25 months
Composite fee rate | $152/hour
Contingency (vs base) | (see summary)
-80%
Total
135,988
317,306
-
-
453,294
9/06 Program Estimate
+2,619%
Budget reduction options to be discussed with TPTF & TAC
  None proposed

## Slide 115: EIP: Schedule and Resource Effort
Integration high-level schedule
Q2 2008
Q3 2009
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
Requirements
Design
Build – Iteration 1
Build – Iteration 2
Build – Iteration 3
Test
EDS
EDS 3
EDS 4
Go-live Trans.
EDS 3 Mote & ERCOT UAT

## Slide 116: EIP: Budget Assumptions
Assumptions: Nodal requires 100 interfaces to be developed UISOL will do the following tasks for Nodal Requirements Design Quality Assurance (including FAT) An Integration Implementation vendor will be hired for developing the integration solution ERCOT Integration team will be transitioned and trained on the new integration platform Enterprise Integration project will deliver components in line with the EDS strategy Travel expenses are assumed to be 15% of labor cost Assumes integration work will be completed by the end of Q3 2008

## Slide 117: EIP: Overview of current threats to success
 | Current Status
Scope/Plans | Charter not signed off
Resourcing | 
Costs | Nominal, P2P mitigation built in
Timescales | Not defined
Critical dependencies | Not identified as yet
Business Modeling & Requirements | 
Analysis & Design | 
Vendors | 
External Stakeholders | Establish meetings with vendors
Internal Stakeholders | Project communication to be started
Communications | See Internal Stakeholders
Overall | Late start
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)

## Slide 118: Program Management Office (PMO) Project Budget Analysis

## Slide 119: PMO/PC: Project Summary
Description: Program leadership, organization, mobilization, strategic planning and delivery assurance.
Vendor(s): N/A
Project Manager: Michael Collins
Budget: $TBD
Actuals YTD: $TBD
Actuals Total: $TBD
Key deliverables/short term deliverables: Program organization & governance Program Charter Program Management Corporate Standard & Operating Procedures Integrated plans, controls and reporting Program risk management Executive stakeholder management
Key Assumptions: The resource model envisages a lean core team (including “super” Project Managers and assurance functions) – ‘contracting’ with internal and external providers for deliverables (rather than resources) The Program Charter establishes the Program scope, schedule and budget baseline – any changes will be subject to formal change control
Challenges/Risks: Balance of staffing (including contractors and employees) between Zonal, Nodal program and Nodal transition activities
Comments: External consultants (PA) have been retained to provide PMO/Program Management support External consultants (IBM) have been retained to provide independent review of Program Controls

## Slide 120: PMO/PC: Cost Summary
Dimensions
21 months
$137.5/hour
35%
11/04 CBA Assumptions:
  PMO of 10 FTEs spread over two phases
Cost drivers:
  Duration
  Consultants to supplement Program Management capability
  Program Control independent audit (IBM), SAS70, Security Audit
  9 PMO staff excluded package PMs, schedulers, controllers, etc
Dimensions
30 months
$100/hour
25%
12/05 Assumptions:
  Significantly lower estimate of program management consulting support for PMO
  10 PMO 50% FTE, 50% contractors
  Excluded Program Control Independent Audits
11/04 CBA (KEMA)
12/05 High-Level Estimate
 | Total
Internal Resource Costs | 222,300
External Resource Costs | 3,851,440
Vendor Labor | 3,000,000
Hardware, Software, misc. | 27,415
Total | 7,101,155
Total
-
-
-
-
2,552,000
 | Dimensions
Project duration | 32 months
Composite fee rate | $118.5/hour
Contingency (vs base) | (see summary)
-22%
Total
436,346
1,018,142
259,280
271,760
$1,985,528
9/06 Program Estimate
+258%
Budget reduction options to be discussed with TPTF & TAC
  Divert ERCOT PMO resources from Zonal projects Savings potential ~ $0.5M

## Slide 121: PMO/PC: Schedule and Resource Effort
Current high
level schedule
Q2 2008
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Program Budgeting
Program Control Tools
EDS 3
Scheduling Tools
Regular & Ad Hoc Reporting
Program Delivery Assurance & Analysis
Program Change Control
PC Project Management
EDS 4

## Slide 122: PMO/PC: Budget Assumptions and High-Level Milestones
Q2 2008
Q4 2008
Q3 2008
Q2 2007
Q1 2007
Q4 2006
Q4 2007
Q3 2007
Q1 2008
Q3 2006
Q1 2009
Q2 2009
EDS 3
EDS 4
Security Audit
IBM Independent Reviews
Program Risk Reviews
SAS 70 Reviews
Assumptions:
  Number of changes by the TPTF will be minimal.
  Number of change requests will not exceed capacity of the Change Control Board.
  Annual rate of attrition will not exceed 10%.

## Slide 123: PMO/PC: Overview of current threats to success
 | Current Status
Scope/Plans | Program Control Tool creation is incomplete
Resourcing | 
Costs | Budget is not approved
Timescales | TBD
Critical dependencies | N/A
Business Modeling & Requirements | N/A
Analysis & Design | N/A
Vendors | 
External Stakeholders | Budget is not approved
Internal Stakeholders | PMO resources will be replaced by the “Home Team”
Communications | Plan in place, making progress
Overall | Program pulling together manageable deployment timeline
 | Major threat (or unknown) – “hair on fire” is the only acceptable response
 | Known and contained threat – continue to progress and maintain a watching brief
 | No major threats – blank (this is not a progress report)