## Slide 1: TPTF Update Trip Doggett

## Slide 2: Agenda
Item | Description | Purpose
1. Meeting Summary | Summary of recent TPTF activities | For review
2. Next Meetings | Upcoming activities | For review
3. Approval of Milestone | Request TAC approval of Milestone – Business Requirements Complete for CO Real-Time Energy Settlements CO DAM CRR Settlements CO Black Start Services RT Settlements CO Real-Time Emergency Ops Settlmnts CO Voltage Support RT Settlements | For Vote

## Slide 3
Meeting Summary – September 5-6
Meetings September 5-6, 11-12, 27-29
On September 5 and 6 TPTF had a special meeting dedicated to discuss the Nodal Program implementation approach and timeline. As part of this discussion, TPTF discussed in detail the following:
  Reviewed ERCOT Nodal Transition Plan
  Walked though the Early Delivery System and details of each Phase
  Kathy Hager presented details of plans for Nodal implementation, with review by TPTF of 3 possible scenarios and timelines for Texas Nodal Implementation
  Project Manager for each of the 13 Nodal Program Offices provided an overview of their program area.
  Meeting concluded that Market Participants should review the implementation options with their companies, and possibly provide alternatives, to vote on an implementation approach at the September 11 TPTF meeting

## Slide 4
Meeting Summary – September 11-12
On September 11, we discussed:
  Nodal Implementation Timeline
    Reviewed details of implementation option proposed by TXU.
    On September 11, TPTF approved motion to “approve in principle scenario three with a phased approach with phase one first and then phase two with phase three implementing seven days after phase two. If unable to implement phase three, the market would revert to Zonal” by a ballot vote of 75.7% in favor, 24.3% opposed, with two abstentions (CenterPoint and Constellation). All Market Segments were present.
    On September 11, TPTF approved motion for the phase two preferred implementation date to be December 1, 2008 by a ballot vote of 81.7% in favor, 18.3% opposed, and eight abstentions by 100% in favor, with eight abstentions (STEC, City of Greenville, CenterPoint, First Choice, StarTex Power, Accent Energy, BP Energy, and Constellation). All Market Segments were present.
    On September 11, TPTF approved motion for the phase one preferred implementation date to be March 31, 2008 by a ballot vote of 92.7% in favor, 7.3% opposed, and six abstentions (Medina, STEC, BTU, First Choice, Dynegy, Residential Consumers). All Market Segments were present.

## Slide 5
Meeting Summary – September 11 (continued)
On September 11, we also discussed:
  EMS Business Requirement Review
    Initial review of the SCADA Business Requirements
  CRR Business Requirements Review
    Initial review of the CRR Business Requirements
  ICCP Recommendation
    ERCOT recommended using ICCP for all Real-Time data (replace all RTUs)
    TPTF provided positive feedback, ERCOT to present to WMS and QSEMWG, and draft NPRR.
  Review of System of System Architecture (SOSA)

## Slide 6
Meeting Summary – September 12
On September 12, we discussed:
  Review of Managing Risks in Nodal System Architecture
  Market Engagement and Readiness (MER) Discussion
    Announced selection of Enterpulse as the MIS vendor
    Discussed Market and ERCOT Training in detail
    Filing paperwork for NERC certification of Nodal courses has begun
    Discussed training delivery timeline and delivery methods
      On September 12, TPTF approved support of each Texas Nodal course that is required for QSEs to be held twice in the Northeast. Motion carried by voice vote with three abstentions from the Consumer Segment. All Market Segments were present.
    ERCOT training presented options on decreasing training budget through reduction in deliverables on some courses
      On September 12, TPTF approved concept that TPTF leave plans as they stand and not adapt the training documents as a group, but encourage ERCOT to provide needed and accurate training in a cost-effective and expedient manner, and that ERCOT report any curriculum changes as approved by TPTF to TAC to provide a feedback loop. Motion carried on unanimous voice vote with all Market Segments present.

## Slide 7
Meeting Summary – September 12 (continued)
On September 12, we discussed:
  MER Training Update (continued)
    TPTF reached consensus on making the Dr.Ross Baldick’s LMP 201 course optional, and to rename the course to The Economics of LMP
  ERCOT presented draft NPRR with feedback from COPS, on settlement of CRRs if there is not a Day-Ahead Market.
    On September 12, TPTF approved the draft NPRR for CRR without the DAM (with corrections of the de-rating statement). The motion carried by ballot vote with 100% for the motion, with two abstentions (LCRA and CenterPoint). All Market Segments were represented.
  Commercial System Requirements
    ERCOT presented overview of initial requirements for: Real-Time Black Start Settlements, Real-Time Voltage Support Settlements, Real-Time Reliability Must-Run, Day-Ahead Make-Whole, RUC Start-Up, Real-Time Emergency Operations, and DAM CRR Settlement
    ERCOT reviewed market feedback on RT Energy requirements.
      On Sept 12, TPTF approved the Real-Time Energy Settlements Business Requirements document as being compliant with Nodal Protocols. The motion carried by ballot vote with 100% in favor and four abstentions (Greenville, NRG, Calpine, and Exelon). The Consumer Market Segment was not present for the vote.

## Slide 8
Meeting Summary – September 27-29
On September 27, we discussed:
  Nodal Program Budget Review
  Kathy Hager outlined the composition of scope, resources, and budget for each program. Within each program, the Nodal Project team identified potential areas for budget reduction for TPTF to consider.
  Each budget reduction that TPTF felt needed additional evaluation was put into a parking lot for future discussion.
    $1.3MM savings to remove Auditors that interview MPs from Market Readiness (revisit during project based on MP participation)
    $2.5MM savings to discontinue zonal enhancement work (assigned to PRS)
    Reconsider 19 additional training courses (TPTF to reconsider as training curriculum refined)
    Allow more latency in data warehouse. Current 36 second latency is very expensive, Nodal Program to assess from PUCT requirements and costs.

## Slide 9
Meeting Summary – September 28
On September 28, we discussed:
  Nodal Program Budget Review
    On September 28, TPTF approved following motion:
    “During its September 27-28, 2006 meeting, the TPTF reviewed the draft “Texas Nodal Market Implementation Budget Rationale” to be presented by the ERCOT Nodal Project Director to the ERCOT Board and TAC. During this review options for value engineering changes to the project scope were considered. TPTF believes the materials presented by ERCOT meet the scope of the requirements of the Nodal Protocols approved by the PUCT in Docket No. 31540, the timeline for implementation approved by TPTF and TAC, and the requirements of the TAC approved Nodal Transition Plan but makes no finding with regard to the total amount of the proposed budget.”
    TPTF approved the motion by a ballot vote with 89.6% in favor, 10.4% opposed, with seven abstentions (Greenville, Garland, Dynegy, City of Dallas, Town of Flower Mound, Residential Consumers, Cirro). All Market Segments were present for the vote.

## Slide 10
Meeting Summary – September 28 (continued)
On September 28, we discussed:
  EMS Requirements Update
    Al Hirsch presented that ERCOT is re-engineering the EMS requirements documentation, and will be subsequently released.
  Discussion of TDSP versus TSP and DSP
    TPTF confirmed that the protocol language distinction between TSP and DSP was to differentiate entities and functions within the wholesale market, but there were no intentions to affect ERCOT systems related to Retail or Registration.
  Draft NPRR for ICCP only
    TPTF agreed in concept, but will solicit input from ROS members prior to voting on this NPRR draft at a future TPTF meeting.
  Review NPRR024- Synchronization of zonal PRR627/640 for RMR
    TPTF reviewed an issue with erroneous baseline language
    On September 28, TPTF rejected a motion to remove part of PRR640 language which adds language in Section 3.14.1.13 related to Incentive Factor payments. The TPTF rejected the motion by a ballot vote with 65.7% in favor, 34.3% opposed, with six abstentions (City of Allen, Stream Energy, StarTex, Strategic Energy, Accent Energy, Cirro Group). All market segments, except cooperative, were present.

## Slide 11
Meeting Summary – September 28 (continued)
On September 28, we discussed:
  Initial review of MIS Requirements
  Training update to focus on review of market comments and modifications to the Training Curriculum and Market Participant Readiness
    Reviewed the nineteen new courses proposed by ERCOT, and removed two classes related to Operator Training Simulator
    On September 28, TPTF approved modifications to Training Curriculum in a unanimous voice vote, with all Market Segments, except cooperative, present.
    On September 28, TPTF approved modification and re-titling of the Market Participant Training Readiness in a unanimous voice vote, with all Market Segments, except cooperative, being present.
  Initial Review of Credit Monitoring Requirements
    To be considered for vote at October 9-10 meeting
    Interim meeting to be scheduled, inviting CWG and TPTF, to vet questions brought forward by project team within their requirements.

## Slide 12
Meeting Summary – September 29
On September 29, we discussed:
  LMP during EECP
    Brief discussion with agreement that there is more thought needed to effective language in Section 6.5.7.3, Security Constrained Economic Dispatch. Action item given to ERCOT to explore how other ISOs determine the LMP under EECP conditions.
  CRR Requirements Review
    Detailed discussion of CRR lifecycle, requirements to be released next week for TPTF consideration on October 9-10
  Commercial Operations
    Reviewed draft ERCOT comments for NPRR024 to be submitted to PRS
    Reviewed two draft NPRRs from ERCOT for clarifications related to Business Requirements for Black-Start (in Section 6.6.8 Black Start Capacity) and for Voltage Support (in Section 6.6.7 Voltage Support Settlement).
      On September 29, TPTF approved the two draft NPRRs. The motion was approved unanimously by a ballot vote with two abstentions (Calpine and City of Allen). All Market Segments were present.

## Slide 13
Meeting Summary – September 29 (continued)
On September 29, we discussed:
  Commercial Operations (continued)
    Reviewed disposition of market comments on Real-Time Black-Start Business Requirements
      On September 29, TPTF approved the Business Requirements for Real-Time Black-Start as being in compliance with the applicable Nodal protocols. TPTF unanimously approved the motion by a ballot vote with three abstentions (CPS, CenterPoint, City of Allen). All Market Segments were present.
    Reviewed disposition of market comments on Voltage Support Real-Time Settlement Requirements
      On September 29, TPTF approved the Business Requirements for Voltage Support Real-Time Settlements as being in compliance with the applicable Nodal protocols. TPTF unanimously approved the motion by a ballot vote with one abstention (CenterPoint). All Market Segments were present.

## Slide 14
Meeting Summary – September 29 (continued)
On September 29, we discussed:
  Commercial Operations (continued)
    Reviewed disposition of market comments on Real-Time Emergency Operations Business Requirements
      On September 29, TPTF approved the Business Requirements for Real-Time Emergency Operations as being in compliance with the applicable Nodal protocols. TPTF unanimously approved the motion by a ballot vote with four abstentions (CenterPoint, City of Dallas, Town of Flower Mound, Residential Consumers). All Market Segments were present.
    Reviewed disposition of market comments on RMR Services Real-Time Settlement Requirements. Deferred further discussion until next meeting, and to consider in conjunction with NPRR024 comments.

## Slide 15
Meeting Summary – September 29 (continued)
On September 29, we discussed:
  Commercial Operations (continued)
    Reviewed disposition of market comments on Day-Ahead Market for CRR Settlement Business Requirements
      On September 29, TPTF approved the Business Requirements for Day-Ahead Market for CRR Settlement as being in compliance with the applicable Nodal protocols. TPTF unanimously approved the motion by a ballot vote with one abstention (CenterPoint). All Market Segments, except cooperatives and consumers, were present.
    Initial Review of Business Requirements for Real-Time CRR Settlement, CRR Balancing Account, CRR Auction Settlement and Revenue Disbursement, Settlement Statements, and Invoice Requirements

## Slide 16
Next Meetings
Next meetings
  Monday, October 9 and Tuesday, October 10
  Tuesday, October 24 through Thursday, October 26
  Monday, November 6 and Tuesday, November 7
On October 9 &10, will be discussing:
  Potential approval of CRR Business Requirements
  Commercial Operations Requirements
    Potential Approval of: Credit Monitor Requirements, RT CRR Settlement, CRR Balancing Account, CRR Auction Settlement and Revenue Disbursement, Settlement Statements, Invoice Requirements, RMR Services Real-Time Settlements
    Initial Requirements Review of: Interfaces, Data Aggregation, Disputes, Average Incremental Energy Cost Calculation, Verifiable Costs, Financial Transfer, and Registration
  Discuss draft NPRR for ICCP, with ROS invited
  LMP for EECP (Oct 9-10 or later meeting)
  NPRR018 impacts to SASM
  MIS Update
  Training Update

## Slide 17
TAC Approval of Milestone
On September 12, TPTF approved the Real-Time Energy Settlements Business Requirements document as being compliant with Nodal Protocols. The motion carried by ballot vote with 100% in favor with four abstentions (Greenville, NRG, Calpine, and Exelon). All Market Segments, except the consumers, were present for the vote.
On September 29, TPTF approved the Business Requirements for Real-Time Black-Start as being in compliance with the applicable Nodal protocols. TPTF unanimously approved the motion by a ballot vote with three abstentions (CPS, CenterPoint, City of Allen). All Market Segments were present.
On September 29, TPTF approved the Business Requirements for Voltage Support Real-Time Settlements as being in compliance with the applicable Nodal protocols. TPTF unanimously approved the motion by a ballot vote with one abstention (CenterPoint). All Market Segments were present.
On September 29, TPTF approved the Business Requirements for Real-Time Emergency Operations as being in compliance with the applicable Nodal protocols. TPTF unanimously approved the motion by a ballot vote with four abstentions (CenterPoint, City of Dallas, Town of Flower Mound, Residential Consumers). All Market Segments were present.

## Slide 18
TAC Approval of Milestone (continued)
On September 29, TPTF approved the Business Requirements for Day-Ahead Market for CRR Settlement Business Requirements Real-Time Emergency Operations as being in compliance with the applicable Nodal protocols. TPTF unanimously approved the motion by a ballot vote with one abstention (CenterPoint). All Market Segments, except cooperatives, were present.
The Transition Plan says: “Any declaration of the accomplishment of a major milestone (business requirements, conceptual design, and successful completion of Market Participant testing) or a decision to proceed is contingent on the approval of both ERCOT and TAC.”
Request that TAC approve the milestones
  Approval of Real-Time Energy Settlements Business Requirements
  Approval of Real-Time Black-Start Settlement Business Requirements
  Approval of Real-Time Voltage Support Settlement Business Reqts
  Approval of Real-Time Emergency Operations Settlement Business Reqts
  Approval of Day-Ahead Market CRR Settlement Business Requirements

## Slide 19
Questions
?