## Slide 1: Texas Nodal Nodal Process COPs Meeting By Raj Chudgar, ERCOT Monday, 10/24/2006

## Slide 2: Agenda
Guiding Principles and Documents
What is complete
What is next
COMS Road Show
Other concerns and questions

## Slide 3: Guiding Principles and Documents
Guiding Principles:
  ERCOT is using the Rational Unified Process (RUP) to develop its software under a mature set of deliverables and processes
  ERCOT is tracing all protocols to requirements and future deliverables using the Requisite Pro IBM tool
  ERCOT is tracking all issues and questions that relate to Nodal, but not to Commercial Systems via the “Punchlist”
  ERCOT has established a set of controls and quality management to unsure successful project delivery
Nodal Key Documents
  Nodal Protocols
  Nodal NPRRs
  Nodal Transition Plan
    Details which items require TPTF approvals
    Details which items require TPTF reviews
    Details strawman test plan

## Slide 4: What is complete…
COMS: Completed to date
  Requirements:
    27 requirement documents
    22 reviewed at TPTF to date, last 5 to be reviewed at TPTF 10/25
    13 completed and Approved at TPTF
    3 currently deferred to COPs
      Statements
      Invoices
      CRR Revenue Disbursement
  Prototype
    Significant redesign of current Lodestar tool is underway
    Will be complete by end of November with architecture recommendations

## Slide 5: What is next….
COMS: Next Steps
  CSD: Conceptual System Designs for each process
    Process based and not to the detail level of the requirements.
    The “How” of the system
    Target to have first ones out in late November for COMS
    Created by ERCOT development teams, reviewed by ERCOT business, and Approved by TPTF
    What is COPs involvement ???
  ERCOT Development Team
    Once CSD is completed, team will rapidly start building code and detailed design
    Detailed design will be traced to Requirements
    Detailed Designs can be reviewed by TPTF
    What is COPs involvement ???
  ERCOT business teams roll will change once requirements are completed
    Creating/completing Use Case development
    Creating test cases and test scripts on a module basis
    Creating verification spreadsheets for internal ERCOT validation of Lodestar code base
    Creating data sets (stub data) for internal product/functional testing (FAT)
    What does COPs want to review ?

## Slide 6: COMS Road Show
High Level Summary
  To provide MPs with a dedicated time where ERCOT staff will provide open dialog and presentations around Nodal to MP staff (COMS staff).
Goal
  Increase education and awareness of ERCOT COMS changes and effects to MPs
  Provide availability for MPs to openly ask ERCOT questions in a private setting
  Provide guidance on MP solutions
  Build relationships between ERCOT staff and MP staff
Timeline
  Start in November and target 2/month
  Attempt to limit to 1-2 days
Question:
  Are COMS MPs interested ??
  If interest when ??
  If interest can we pilot with an MP, mock up an agenda, timeline, and presenters

## Slide 7: Nodal Information
Nodal Website
  http://nodal.ercot.com/
Raj Chudgar contact information:
  O: 512-248-6580
  rchudgar@ercot.com
Questions?