## MIS_All MP Comments
Document Name: TN MIS_67E030_01 Requirements
# | Issuing Entity | Name | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason | Status --
3 | LCRA | C. Bascom | 43 | FR 68 - Posting Category comment: "This is a must - it has to be Certified" | Response | MIS Team | We agree, we need NPRR | Punchlist
6 | LCRA | C. Bascom | 45 | FR 72 - Posting Frequency: Deleted "Not specified" & inserted "When an Ancillary Trade is reported to ERCOT" Added the following sentence to the end of the protocol text: "This includes purchases of Ancillary Services where ERCOT is the Supplier." | Response | MIS Team | The frequency is continuous. The last sentence is not in May 2006 protocols | NPRR.xls
10 | LCRA | C. Bascom | 71 | FR 125 - Inserted "INFO" into the PTP Option value formula: RTOPTPRINFO (j, k) | Response | MIS Team | We have kept to the May 2006 protocols in order to remain consistent | NPRR.xls synchronize with NPRR that modified formula (in August 2006 protocols)
41 | Reliant | M. Wagner | iv | Global Comment on Data for the Market: Nearly everything that is posted on the dynamic content area will need to be accessible to Market Participants in real time. To avoid too much screen scraping—thought should be given to providing this information in an API format as well as posting it on the Dynamic section of the MIS. That said, if screen scraping is required, then displays should be designed where the browser just renders the html. If this is the plan, we encourage ERCOT to refrain from using javascript or other impediments to scraping. Alternatively, ERCOT could choose to provide Market Participants with access to the infrastructure that feeds the displays. OR, ERCOT could provide an API for everything on the dynamic site (every display with applicable market data) along with all of the other public/secure/certified data. OR, ERCOT could provide a set of CSV or XML files that contain the data in the displays in real time—providing Market Participants with a schedule of when to download the files (for SCED we may need a “push” given that it may not execute every 5 minutes under certain conditions). | Response | MIS Team | This will be documented and addressed in design. This data will be available electronically as described in the Conceptual Design Document that TPTF will be able to approve. | Design
42 | Reliant | M. Wagner | iv | General Comment on MIS relationship to other systems: This document needs to be clear about whether ‘post on the MIS’ is happening through the MIS—or through an MIS access point to a window into various source system databases or source system UIs. Some of the source systems—Outage Scheduler and CRRs for example—will have user interfaces. And if information is posted on those UIs—should it be “mapped” to the MIS? Perhaps we could do a better job with a verbal discussion of the concern at the next TPTF. | Response | MIS Team | This will be documented and addressed in design. | Design
43 | Reliant | M. Wagner | v | Cite the protocols (with date so that version is clear). Do not copy protocol language into the requirements docs as the requirement. Write a requirement that meets the statement in the Protocols. All requirements should map to Nodal protocols. | Rejected | MIS Team | All protocols refer to May 2006 as documented in Assumptions. The requirement that meets the protocol is documented in the Description field. | NPRR.xls
44 | Reliant | M. Wagner | v | Define granular, specific, measurable (“Can we test it/track it to meet the requirement?”), unique (no overlap with other requirements) requirements. (This document appears to contain duplicate requirements—and this needs to be remedied.) | Rejected | MIS Team | We are required by the process to list every protocol, even if it is a duplicate. The granular, specific and measureable is something we don't know at this time- part of the design plan. | Design
45 | Reliant | M. Wagner | v | Document where existing data are posted (on the current portal/MIS) and use this as a proposal for the “posting category” for all of the currently posted data for which the posting category is labeled as “Not Specified.” After categorization a list of the data elements and proposed categorization should be presented to TPTF and COPS for a final determination of the categorization level. For requirements that exist –but for which nothing is posted—these should be listed and provided to Market Rules or ERCOT Legal for follow up. | Response | MIS Team | All part of a future design phase. These requirements address part of current work. | Design
46 | Reliant | M. Wagner | v | Eliminate all business process descriptions in this document. This document is about data availability through electronic interfaces. | Response | MIS Team | We are following a standard RUP methodology in these requirements and using an approved template. | Answer Provided - Close ?
47 | Reliant | M. Wagner | v | Coordinate with the other design teams (this is critical!) to make sure that requirements are synchronized and ownership lies with one team. (There should be an internal QA process that does this before these documents get issued!) | Response | MIS Team | This will be documented and addressed in design. | Design/Process
48 | Reliant | M. Wagner | 6 | Reliant General Question – In the specific post requirements, what is the process for resolving the “not specified” items under Posting Frequency? | Response | MIS Team | We are obtaining that information from the MIS subgroup -- ongoing. | ongoing
49 | Reliant | M. Wagner | 6 | First paragraph: The requirements in this document will provide a single point of access for Market Participants, the PUCT Reliant: does this mean that the Wholesale Electric Market Monitor (at the direction of PUCT) will access through the MIS? If not, perhaps the use of PUCT isn’t correct here. | Response | MIS Team | Investigating who this group is and what their access needs to be. | Open
50 | Reliant | M. Wagner | 6 | #2 - content displayed in Extract category: Reliant: does ‘extract data’ include ad hoc query request functionality described below, or does this mean standard data extracts? | Response | MIS Team | Refers to extract data in general. | Design
51 | Reliant | M. Wagner | 7 | Last bullet of MIS Objectives: Develop a catalog of procedures for handling, securing and protecting information. Reliant: does this mean that each data report will be assigned to a category—and the categories posted—or somehow provided to the Market Participants—so that we can figure out which level of access is needed for different data? | Response | MIS Team | Yes all part of design (through roles definition) | Design
52 | Reliant | M. Wagner | 8 | First bullet, MIS Components: Configurable 'My Page' Reliant: TPTF previously discussed that a user would be able to choose from the catalog of reported data and determine if it he/she required access to the specific data report. Is this included in the configuration of “My Page”? | Response | MIS Team | Yes - all implementation of the My Page is part of design | Design
53 | Reliant | M. Wagner | 8 | Fourth bullet, MIS Components: Dynamic-Update area Reliant: would the daily posting requirements be characterized as ‘dynamic’? | Response | MIS Team | Yes | Answer Provided - Close ?
54 | Reliant | M. Wagner | 8 | Last bullet, MIS Components: Dashboard Style Application Reliant: Is this dashboard similar to that discussed in TPTF? (i.e., eSuites? | Response | MIS Team | Yes | Answer Provided - Close ?
57 | Reliant | M. Wagner | 9 | Security, First paragraph: Reliant: it would be useful to have a diagram of the layers. | Response | MIS Team | That will come in design | Design
61 | Reliant | M. Wagner | 10 | Data and Applications, Fifth paragraph (fail-over defined the Disaster Recovery): Reliant: a document reference for what the guidelines are is required for this to ensure that the guidelines are met and are able to be tested in the failover process. | Response | MIS Team | Guidelines are being developed. | Open
62 | Reliant | M. Wagner | 10 | Data and Applications, Sixth paragraph (MIS will not develop user interfaces): Reliant: Is there any intention to attempt to standardize the interfaces? (This might be handled by the “my page” type of access point. | Response | MIS Team | Yes. | Answer Provided - Close ?
63 | Reliant | M. Wagner | 10 | Storage and Retention, Second paragraph (data retention responsibilitiy) Reliant: Where is the activity of data management living? Is this under the umbrella of the EDW? It is unclear that the ‘business owners’ will be managing the data and managing the data expiration program. All data managed under the protocols is subject to data retention requirements and there should be a defined management plan to do this—and it should also include a discussion of version control. | Response | MIS Team | This issue has been turned over to the Data Warehouse. | Answer Provided - Close ?
64 | Reliant | M. Wagner | 10 | Performance Reliant: will these be summarized in an appendix? Seems like it would be helpful to have a summary of the posting requirements/response times/data retention requirements in one document to facilitate data management and to ensure that statistics on meeting requirements can be developed from analysis of the function of the MIS. | Response | MIS Team | This is in process now in the form of our data inventory. | Open
65 | Reliant | M. Wagner | 10 | MIS Migration and Integration Reliant: will the plan include the existing ERCOT website or specifically portal applications (only)? Specificity is needed here to understand exactly what will be migrated? | Response | MIS Team | This is still under discussion with ERCOT. | Open
66 | Reliant | M. Wagner | 11 | Structure, protocol references Reliant: Please confirm that no posting changes have occurred due to the NPRRs that have passed since May. | Response | MIS Team | We are tracking all NPRRs and there will be an overall program strategy for dealing with these. | NPRR.xls
67 | Reliant | M. Wagner | 13 | FR 1, Description: Deleted all but the first sentence Reliant: the crossed out information is not a function of the MIS Reliant: it would be useful to provide a description of what the ‘list’ would look like. For example, it would be useful to have the various types of documents grouped together---discussions may be required around whether the groupings should be by functionality (Operating Guides, Registration) or topic: for exmple---dividing registration forms by market participant type. Separate from this project ERCOT business processes are required to effect many other elements of these Protocol requirements—including things documented above (crossed out) such as how to format the first pages of the docs, and document expiration, email requirements, etc. | Description Text change accepted Rejected description of list | MIS Team | Other binding documents are defined in protocol language. | Answer Provided - Close ?
68 | Reliant | M. Wagner |  | FR 2, Posting Frequency: Reliant: Effectively this is a rolling requirement. Each day new data become eligible for posting. Also, need to review PUC Substantive Rule 25.504 – Is there an NPRR needed? | Response | MIS Team | Agreed this is a rolling requirement. NPRR noted and will be investigated. | NPRR.xls
70 | Reliant | M. Wagner | 13 thru169 | FR 1 - 306, Protocol Text: Delete Reliant: it would be more consistent to reference the protocol language and not quote it in these documents in order to bring brevity to the documents and preparation and to avoid unintentional errors in transferring the protocol language. | Rejected | MIS Team | Protocol text is provided in every case to add clarity and specificity. This comment will not be responded to in every instance in this document. | Answer Provided - Close ?
71 | Reliant | M. Wagner | 16 | FR 5, Description: [Reliant: Might be useful to coordinate with the Outage Scheduler team. This requirement might be accomplished by a link to a ‘window’ in the Outage Scheduler system—with appropriate security measures.] | Response | MIS Team | We will coordinate this during the design phase with the Outage team. | Design
72 | Reliant | M. Wagner | 16 | FR 6, Under Posting Frequency: Reliant: Besides making a link on the web, this will require business process changes. Ensuring development of this business process might fit under Steve Grendel’s team. | Response | MIS Team | This issue will be communicated through the Punchlist with Steve Grendel's team. | Punchlist
73 | Reliant | M. Wagner | 17 | FR 7, Posting Category: Reliant: Might be useful to coordinate with the Outage Scheduler team. This requirement might be accomplished by a link to a ‘window’ in the Outage Scheduler system—with appropriate security measures. In general, it seems like the MIS team is taking responsibility for functionalities that were envisioned as requirements for the Outage Scheduler interface(s). Almost all of the requirements in this document where we have provided “coordinate with the Outage Scheduler team” comments seem like they are posting requirements that need to be developed for the OS—and then perhaps synchronized with MIS. Alternatively, MIS may be able to ‘cede’ responsibility for these postings if the OS team is willing to take them on. In any case, most of the info will arise through the OS, and close coordination is required. | Response | MIS Team | Agreed. This has been moved to the Punchlist. | Punchlist
74 | Reliant | M. Wagner | 18 | FR 8, Under Posting Frequency: Reliant: Might be useful to coordinate with the Outage Scheduler team. This requirement might be accomplished by a link to a ‘window’ in the Outage Scheduler system—with appropriate security measures. | Response | MIS Team | Agreed. This has been moved to the Punchlist. | Punchlist
75 | Reliant | M. Wagner | 18 | FR 9, Under Posting Frequency: Reliant: Besides making a link on the web, this will require business process changes. Ensuring development of this business process might fit under Steve Grendel’s team.] | Response | MIS Team | This issue will be communicated through the Punchlist with Steve Grendel's team. | Punchlist
76 | Reliant | M. Wagner | 19 | FR 10, Under Posting Frequency: Reliant: Besides making a link on the web, this will require business process changes. Ensuring development of this business process might fit under Steve Grendel’s team. | Response | MIS Team | This issue will be communicated through the Punchlist with Steve Grendel's team. | Punchlist
77 | Reliant | M. Wagner | 19 | FR 11, Under Posting Frequency: Reliant: Besides making a link on the web, this will require business process changes. Ensuring development of this business process might fit under Steve Grendel’s team. Also, it might be useful to coordinate with the Outage Scheduler team. This requirement might be accomplished by a link to a ‘window’ in the Outage Scheduler system—with appropriate security measures. | Response | MIS Team | This issue will be communicated through the Punchlist with Steve Grendel's team. | Punchlist
78 | Reliant | M. Wagner | 20 | FR 12, Under Posting Frequency: Reliant: Besides making a link on the web, this will require business process changes. Ensuring development of this business process might fit under Steve Grendel’s team. Also, it might be useful to coordinate with the Outage Scheduler team. This requirement might be accomplished by a link to a ‘window’ in the Outage Scheduler system—with appropriate security measures. | Response | MIS Team | This issue will be communicated through the Punchlist with Steve Grendel's team. | Punchlist
79 | Reliant | M. Wagner | 20 | FR 13, Under Posting Frequency: Reliant: The list of names that comprise the hub will likely need to come from the NMMS team. The elements that comprise the Hubs are defined in the Protocols, but the names don’t conform to the CIM standard that is being developed for NMMS | Response | MIS Team | This issue will be addressed in design. | Design
80 | Reliant | M. Wagner | 21 | FR 14, Under Posting Frequency: In addition to posting, this will require Business Process documentation that coordinates across NMMS, Operations (including the Market System), potentially the settlements group, and the CRR team. (The CRR team is the downstream user of NMMS info, so their requirements are limited.) Ensuring this coordination might require follow up from Steve Grendel’s team. | Response | MIS Team | This issue will be communicated through the Punchlist with all the appropriate teams. | Punchlist Coordinate with Other Teams
81 | Reliant | M. Wagner | 21 | FR 15, Under Posting Frequency: Reliant:: This requirement, is more ‘real time’ than a lot of the other posting requirements. The MIS team (mostly the market participants) need to give some thought to both the real time pages and the more static data presentation… | Response | MIS Team | Agreed. Adding "As soon as applicable with real -time implications". | (element of) Design
82 | Reliant | M. Wagner | 22 | FR 17, Under Posting Frequency: Reliant:: This particular requirement should be coordinated with the NMMS team and their posting requirements. | Response | MIS Team | The requirement was deleted as a duplicate. | Punchlist Coordinate with NMMS Team
83 | Reliant | M. Wagner | 22 | FR 18, Under Posting Frequency: Reliant:: This is another business process requirement—likely Steve Grendel’s team working with NMMS team and Operations. | Response | MIS Team | This issue will be communicated through the Punchlist with all the appropriate teams. | Punchlist Coordinate with Other Teams
84 | Reliant | M. Wagner | 23 | FR 19, Under Posting Frequency: Reliant: This is another business process interplay between NMMS and Operations with a ‘data element’ that will be posted… | Response | MIS Team | This issue will be communicated through the Punchlist with all the appropriate teams. | Punchlist Coordinate with Other Teams
85 | Reliant | M. Wagner | 24 | FR 20, Under Posting Frequency: Reliant: This is another business process for NMMS and Outage Scheduler with a ‘data element’ that will be posted…MIS team needs to work with the OS and NMMS teams to figure out who will take ownership for these posting requirements. | Response | MIS Team | This issue will be communicated through the Punchlist with all the appropriate teams. | Punchlist Coordinate with Other Teams
86 | Reliant | M. Wagner | 24 | FR 21, Under Posting Frequency: Reliant: This is another business process for Outage Scheduler team with a ‘data element’ that will be posted…MIS team needs to work with the OS team to figure out who will take ownership for these posting requirements. | Response | MIS Team | This issue will be communicated through the Punchlist with all the appropriate teams. | Punchlist Coordinate with Other Teams
87 | Reliant | M. Wagner | 25 | FR 22, Under Posting Frequency: Reliant: This is another business process for Outage Scheduler team with a ‘data element’ that will be posted…MIS team needs to work with the OS team to figure out who will take ownership for these posting requirements. | Response | MIS Team | This issue will be communicated through the Punchlist with all the appropriate teams, and will be slated for Design activities. | Punchlist Coordinate with Other Teams
88 | Reliant | M. Wagner | 25 | FR 23, Under Posting Frequency: Reliant: This is another business process for NMMS team with a ‘data element’ that will be posted…MIS team needs to work with the NMMS team to figure out who will take ownership for these posting requirements. | Response | MIS Team | This issue will be communicated through the Punchlist with all the appropriate teams, and will be slated for Design activities. | Punchlist Coordinate with Other Teams
89 | Reliant | M. Wagner | 26 | FR 24, Under Posting Frequency: Reliant: This is another business process for Outage Scheduler, NMMS, and CRR teams with a resulting ‘data element’ that will be posted…MIS team needs to work with the other teams to figure out who will take ownership for these posting requirements. | Response | MIS Team | This issue will be communicated through the Punchlist with all the appropriate teams, and will be slated for Design activities. | Punchlist Coordinate with Other Teams
90 | Reliant | M. Wagner | 26 | FR 25, Under Posting Frequency: Reliant: This is another business process for NMMS and CRR team with a resulting ‘data element’ that will be posted…MIS team needs to work with the other teams to figure out who will take ownership for these posting requirements. | Response | MIS Team | This issue will be communicated through the Punchlist with all the appropriate teams, and will be slated for Design activities. | Punchlist Coordinate with Other Teams
91 | Reliant | M. Wagner | 27 | FR 26, Under Posting Frequency: Reliant: This is a business process with resultant data elements for posting. The BP accountability likely rests with Steve Grendel’s internal readiness team. The MIS teams nees to ensure that there is a ‘location’ for the SE documents, but beyond that MIS has no responsibility here. | Response | MIS Team | We agree, and will coordinate this with IRT through the Punchlist. | Punchlist Coordinate with Other Teams
92 | Reliant | M. Wagner | 27 | FR 27, Under Posting Frequency: Reliant: This is a complex set of requirements for various ERCOT teams. From an MIS perspective, only a ‘location’ for the results of the mirrored test runs is required. However, as we move into testing, requirements for communication of test results will likely expand, so this effort would benefit from coordination with the testing and readiness teams. | Response | MIS Team | We agree, and will coordinate this with ALL the project teams through the Punchlist. | Punchlist Coordinate with Other Teams
93 | Reliant | M. Wagner | 28 | FR 28, Under Posting Frequency: Reliant: This is another business process for NMMS, Operations, and potentially ERCOT legal or Compliance teams with a resulting ‘data element’ that will be posted…MIS team needs to work with the other teams to figure out who will take ownership for these posting requirements. And the business process documentation for this might be appropriately distributed to the ERCOT Readiness team (S. Grendel). | Response | MIS Team | We agree, and will coordinate this with ALL the project teams through the Punchlist. This issue will be addressed and documented during Design Phase | Punchlist Coordinate with Other Teams
94 | Reliant | M. Wagner | 28 | FR 28, Protocol Text: Reliant Added bracketed, non-italicized text: ...If an interim update is implemented, ERCOT shall report changes to the PUCT Market Oversight Division and the Independent Market Monitor [need clean up NPRR to change this to WEMM]. ERCOT shall provide Notice via electronic means to all Market Participants and post on the MIS Secure Area detailing the changed model information and the reason for the interim update within two Business Days following report to PUCT and WEIMM. [Need clean-up NPRR?]. | Response | MIS Team | We have noted this potential need for NPRR and language cleanup, will track this issue | NPRR.xls
95 | Reliant | M. Wagner | 29 | FR 29, Under Posting Frequency: Reliant: this needs to be coordinated with the NMMS and Outage Scheduler teams. From MIS perspective, only a host location is required. | Response | MIS Team | Changed posting frequency to "When goes into production". Agreed coordination is required, added to punchlist. | Punchlist Coordinate with Other Teams
96 | Reliant | M. Wagner | 29 | FR 30, Under Posting Frequency: Reliant: this needs to be coordinated with the NMMS and Operations teams. From MIS perspective, only a host location is required. | Response | MIS Team | Agreed coordination is required, added to punchlist. | Punchlist Coordinate with Other Teams
97 | Reliant | M. Wagner | 30 | FR 31, Under Posting Frequency: Reliant: this needs to be coordinated with the NMMS and Outage Scheduler teams. From MIS perspective, only a host location is required. May require internal business process to ensure that updates are acknowledged and posting requirement is triggered. | Response | MIS Team | Agreed coordination is required, added to punchlist. | Punchlist Coordinate with Other Teams
98 | Reliant | M. Wagner | 30 | FR 32, Under Posting Frequency: Reliant: this needs to be coordinated with the NMMS and Outage Scheduler teams. From MIS perspective, only a host location is required. May require internal business process to ensure that ERCOT obtains and ‘stores’ switching plans, and that the posting requirements are acknowledged and triggered. | Response | MIS Team | Agreed coordination is required, added to punchlist. | Punchlist Coordinate with Other Teams
99 | Reliant | M. Wagner | 31 | FR 33, Under Posting Frequency: Reliant: this needs to be coordinated with the NMMS and Outage Scheduler teams. MIS and OS teams need to determine whether this requirement is best handled by the OS interface. | Response | MIS Team | Agreed coordination is required, added to punchlist. Design issue re:interfaces. | Punchlist - Coordinate with Other Teams Design
100 | Reliant | M. Wagner | 31 | FR 34, Under Notes: Reliant: This is primarily a business process with a resultant data element for posting. Should be assigned to ERCOT readiness. From MIS perspective, needs a ‘location’ near the ‘real time’ posting section of the web (a link would be useful). | Response | MIS Team | Will review with IRT through Punchlist added notes. | Punchlist - Coordinate with Other Teams
101 | Reliant | M. Wagner | 32 | FR 35, Under Posting Frequency: Reliant: Business process assignment to ERCOT readiness team. “Location” for posting applicable requirement for MIS team | Response | MIS Team | will track this through Punchlist coordinate with appropriate teams. | Punchlist - Coordinate with Other Teams
102 | Reliant | M. Wagner | 32 | FR 36, Under Posting Frequency: Reliant: Business process assignment to ERCOT readiness team. “Location” for posting applicable requirement for MIS team. | Response | MIS Team | will track this through Punchlist coordinate with appropriate teams. | Punchlist - Coordinate with Other Teams
103 | Reliant | M. Wagner | 33 | FR 37, Under Posting Frequency: Reliant: will require coordination with Operations—in particular the group overseeing real time ratings. “Location” for posting applicable requirement for MIS team. | Response | MIS Team | will track this through Punchlist coordinate with appropriate teams. | Punchlist - Coordinate with Other Teams
104 | Reliant | M. Wagner | 33 | FR 38, Under Posting Frequency: Reliant: Business process assignment to ERCOT readiness team—need to define and write up a methodology to identify elements that meet the conditions set forth. “Location” for posting applicable requirement for MIS team. | Response | MIS Team | will track this through Punchlist and pass on to IRT | Punchlist - Coordinate with Other Teams
405 | Reliant | M. Wagner | 34 | FR 39, Under Posting Frequency: Reliant: Business process assignment to ERCOT readiness team. “Location” for posting applicable requirement for MIS team. Also, MIS team needs to design the system for these postings, even if there is nothing to post initially…and to that end, will need to decide on what sort of “message” will open for users for data elements not yet developed | Response | MIS Team | will track this through Punchlist and pass on to IRT. This and similar issues to be resolved during Design | Punchlist - Coordinate with Other Teams Design
106 | Reliant | M. Wagner | 34 | FR 40, Under Posting Frequency: Reliant: Business process assignment to ERCOT readiness team. “Location” for posting all three items is applicable requirement for MIS team. | Response | MIS Team | will track this through Punchlist and pass on to IRT | Punchlist - Coordinate with Other Teams
107 | Reliant | M. Wagner | 35 | FR 41, Under Posting Frequency: Reliant: Needs coordination with Operations. Real time posting required. “Location” for posting applicable requirement for MIS team. Potentially discuss the dynamic vs. static page design requirements—and associated archiving procedures. | Response | MIS Team | Design Phase | Design
108 | Reliant | M. Wagner | 36 | FR 42, Under Posting Frequency: Reliant: Needs coordination with Operations. “Location” for posting applicable requirement for MIS team. Likely requires internal business process development—assign to ERCOT readiness team. | Response | MIS Team | Will review with IRT through Punchlist | Punchlist - Coordinate with Other Teams
109 | Reliant | M. Wagner | 36 | FR 43, Under Posting Frequency: Reliant: Needs coordination with Operations. Requires business process documentation from ERCOT readiness team---working with Operations and QSEs to define appropriate thresholds. MIS requirement is a ‘location’ for posting. | Response | MIS Team | Will review with IRT through Punchlist | Punchlist - Coordinate with Other Teams
110 | Reliant | M. Wagner | 36 | FR 44, Under Posting Frequency: Reliant: Needs coordination with Operations and Planning. Requires business process documentation from ERCOT readiness team---working with Operations and Planning to define and set forth the evaluation criteria. MIS requirement is a ‘location’ for posting. | Response | MIS Team | Agreed | Punchlist - Coordinate with Other Teams
111 | Reliant | M. Wagner | 37 | FR 45, Under Posting Frequency: Reliant: will require coordination with Operations and/or Settlements to get the aggregated data by RMR Unit. MIS requirement is for posting ‘location.’ | Response | MIS Team | Agreed | Punchlist - Coordinate with Other Teams
112 | Reliant | M. Wagner | 37 | FR 46, Under Posting Frequency: Reliant: will require coordination with Operations and Planning. MIS requirement is for posting ‘location.’ Recommend location on the real time page to provide immediate market notification. | Response | MIS Team | Agreed | Punchlist - Coordinate with Other Teams
113 | Reliant | M. Wagner | 38 | FR 47, Under Posting Frequency: Reliant: Will require coordination with Planning. Business Process requirement should be assigned to ERCOT readiness team. Process required to ensure that comments are posted in timely fashion. MIS requirement is ‘location’ for posting. | Response | MIS Team | Agreed coordination required, will review with IRT via Punchlist | Punchlist - Coordinate with Other Teams
114 | Reliant | M. Wagner | 39 | FR 48, Under Posting Frequency: Reliant: Will require coordination with Planning (and potentially ERCOT legal). Business Process requirement should be assigned to ERCOT readiness team. Process required to ensure that initial determination completed within 18 days and that generation entity notice occurs. MIS requirement is ‘location’ for posting. | Response | MIS Team | Agreed coordination required, will review with IRT via Punchlist | Punchlist - Coordinate with Other Teams
115 | Reliant | M. Wagner | 39 | FR 49, Under Posting Frequency: Reliant: Will require coordination with Planning and Legal. Business Process requirement should be assigned to ERCOT readiness team. Process required to ensure that processes are conducted in time to meet Protocols. MIS requirement is ‘location’ for posting. | Response | MIS Team | Agreed coordination required, will review with IRT via Punchlist | Punchlist - Coordinate with Other Teams
116 | Reliant | M. Wagner | 40 | FR 50, Under Posting Frequency: Reliant: Will require coordination with Planning. Business Process requirement should be assigned to ERCOT readiness team. Process required to ensure that studies, reports and data are posted in timely fashion. MIS requirement is ‘location’ for posting. | Response | MIS Team | Agreed coordination required, will review with IRT via Punchlist | Punchlist - Coordinate with Other Teams
117 | Reliant | M. Wagner | 40 | FR 51, Under Posting Frequency: Reliant: Will require coordination with Planning. Business Process requirement should be assigned to ERCOT readiness team. Process required to ensure that RMR alternatives are developed and evaluated and presented to the BOD (and are posted) in timely fashion. MIS requirement is ‘location’ for posting. | Response | MIS Team | Agreed coordination required, will review with IRT via Punchlist | Punchlist - Coordinate with Other Teams
118 | Reliant | M. Wagner | 41 | FR 52, Under Posting Frequency: Reliant: Will require coordination with Settlements and Legal. Business Process requirement should be assigned to ERCOT readiness team. MIS requirement is ‘location’ for posting. | Response | MIS Team | Agreed coordination required, will review with IRT via Punchlist | Punchlist - Coordinate with Other Teams
119 | Reliant | M. Wagner | 41 | FR 53, Under Posting Frequency: Reliant: Will require coordination with Operations. Business Process requirement should be assigned to ERCOT readiness team. Process required to ensure that voltage profiles are developed and posted in timely fashion. MIS requirement is ‘location’ for posting. | Response | MIS Team | Agreed coordination required, will review with IRT via Punchlist | Punchlist - Coordinate with Other Teams
120 | Reliant | M. Wagner | 42 | FR 54, Under Posting Frequency: Reliant: This is a Real Time posting requirement and it should ‘live’ on the RT page when the need is announced---so there needs to be a way to populate the RT page with dynamic messages like this. | Response | MIS Team | Agreed. Will be addressed in Design. | Design
121 | Reliant | M. Wagner | 43 | FR 56, Under Posting Frequency: Reliant: Should be a link from the RT page. | Response | MIS Team | This is Design | Design
122 | Reliant | M. Wagner | 44 | FR 57, In Notes: Data should be pushed to the QSE and available for random access? [Reliant: what does this mean? Is random access referring to the public site or querying capability? We should also be able to query for historical values and download current information—if that is what is meant by random access.] via web interface by all users. Retention period should be set based on further MP/ERCOT discussion. Retention for this Data element could be based on the rolling 7-day COP [Reliant: Recommend that AS requirements be saved off in files with weather and load forecast information for each day and kept available (online) for 2 years.] Under Notes: Reliant: ERCOT Operations will develop daily AS Plans (for the next day—the Operating Day). The Plan is the Systemwide need. This information should be posted to the public page at 0600 each day. It might also be useful to have a link to this posting from the RT page.] | Response | MIS Team | New Requirement, and not in scope now. This could be added but may require an NPRR. Random access was added by someone from the subgroup working on the matrix, and was only in NOTES, not a clear requirement. It means available for download. Much of this recommendation can be addressed during Desgn, we've made some notes but please be sure and bring these up as we move forward. | Design
123 | Reliant | M. Wagner | 44 | FR 58, In Notes: Data should be pushed to the QSE and available for random access? via web interface by all users. [Reliant: we take random access to mean that we can query for the historical information and that the current information will be posted.] Retention period should be set based on further MP/ERCOT discussion. This provision is an extension of (1) above and likely means that if ERCOT determines an Emergency condition, that it should notice that with the details when it makes the 0600 AS Plan posting discussed in (1) above. [Reliant: In general this value is not related to an emergency condition. It is the percent of RRS that can be supplied by load. It is a number determined by Operations and it should be posted with the daily AS Plan. BUT when ERCOT declares an emergency or determines that an “Emergency Condition may exist”, it can change the level of Load providing the Service and to that end, it would be posted on the Public page and potentially with any Emergency Notification. This reference envisions posting by 0600---so it isn’t as dynamic as posting other ‘emergency’ conditions.] | Response | MIS Team | there is no mention of historical data being available here other than in notes. If necessary for historical data to be available, and any requirements for data rentention periods, we will pass this along to EDW team via the Punchlist. | Design to determine Punchlist - Coordinate with Other Teams
124 | Reliant | M. Wagner | 44 | FR 59, Under Posting Frequency: Reliant: MIS requirement is for 0600 Posting. Data requirement for Settlements to pass to Market System and or MIS. Need to figure out if the 0600 data info will come from Market System or from the other systems… | Response | MIS Team | working on issues such as this in Integration team -- this is part of Design | Punchlist - Coordinate with Other Teams
125 | Reliant | M. Wagner | 45 | FR 59, In Notes: Data should be pushed to the QSE and available for random access?[Reliant: No—it is on the Certified Area—but we should be able to query for it if we want it—if this is what is meant by random access.] via web interface by all users. Retention period should be set based on further MP/ERCOT discussion. Retention for this data may be dependent on resettlement timelines. [Reliant: the AS Obligation is determined using applicable data from the most recently available initial settlement data. So for the 0600 posting, this would not rely on resettlement data—only on initial settlement data. See Protocols 4.2.1.2(1). | Response | MIS Team | Downloadable, yes. Retention should be passed to EDW as requiement (via Punchlist, we have done that). Other information noted. Thanks! | Punchlist - Coordinate with Other Teams
126 | Reliant | M. Wagner | 46 | FR 60, In Notes: Data should be pushed to the QSE and available for random access? [No—This is the Certified Area] via web interface by all usersposted on the Certified Area. [Reliant—but we should be able to query for historical information this if we have the appropriate security level.] Retention period should be set based on further MP/ERCOT discussion. | Response | MIS Team | Agreed, should be able to query with appropriate security level, retention must be noted to EDW, passed along now via Punchlist | Punchlist - Coordinate with Other Teams
127 | Reliant | M. Wagner |  | FR 61, In Notes: Data should be pushed to the QSE and available for random access? via web interface by all users posted on the Secure Area and historical information should be available through query. Retention period should be set based on further MP/ERCOT discussion. | Response | MIS Team | Agreed, should be able to query with appropriate security level, retention must be noted to EDW, passed along now via Punchlist | Punchlist - Coordinate with Other Teams
129 | Reliant | M. Wagner |  | FR 63, Under Posting Frequency: | Response | MIS Team | Will be coordinated with all the appropriate teams in the design phase. | Punchlist - Coordinate with Other Teams
130 | Reliant | M. Wagner |  | FR 64, Under Posting Frequency: | Response | MIS Team | Will be coordinated with all the appropriate teams in the design phase. | Punchlist - Coordinate with Other Teams
131 | Reliant | M. Wagner |  | FR 65, Under Posting Frequency: | Response | MIS Team | Will be coordinated with all the appropriate teams in the design phase. | Punchlist - Coordinate with Other Teams
133 |  | M. Wagner |  | FR 67 Under Posting Frequency: changed to On Demand |  | MIS Team
134 | Reliant | M. Wagner |  | FR 67, Under Posting Frequency: | Response | MIS Team | Will be coordinated with all the appropriate teams in the design phase. | Punchlist - Coordinate with Other Teams
145 | Reliant | M. Wagner |  | FR 79, Under Posting Frequency: As soon as practicable upon determination by the Market System | Response | MIS Team | We don't understand your reference to the Market System/Team in the Posting Frequency. Will be cooordinated with the appropriate team in the design phase. | Punchlist - Coordinate with Other Teams Design
146 | Reliant | M. Wagner |  | FR 80, Under Notes: All items – data should be pushed to the QSE and available for random access? via web interface by all users. Data should also be available through user defined query (‘random query’).Retention period should be set based on further MP/ERCOT discussion. | response | MIS Team | Agreed data should be available for query. Retention periods should be negotiated with EDW, passed on via Punchlist | Punchlist - Coordinate with Other Teams
147 | Reliant | M. Wagner |  | FR 83, Under Notes: Reliant: This requires Business Process development by ERCOT Operations. Potential tracking assignment for ERCOT Readiness team. | Response | MIS Team | will pass on to IRT via Punchlist | Punchlist - Coordinate with Other Teams
148 | Reliant | M. Wagner |  | FR 84, Under Notes: Reliant: This requires Business Process development by ERCOT Operations. Potential tracking assignment for ERCOT Readiness team. | Response | MIS Team | will pass on to IRT via Punchlist | Punchlist - Coordinate with Other Teams
149 | Reliant | M. Wagner |  | FR 85, Under Posting Frequency: Within one day of change---with potential to occur daily Under Notes: Reliant: This requires Business Process development by ERCOT Operations. Potential tracking assignment for ERCOT Readiness team | Response | MIS Team | agreed to modify frequency, will pass on IRT issue via Punchlist | Punchlist - Coordinate with Other Teams
150 | Reliant | M. Wagner |  | FR 86, Under Notes: Reliant: This requires Business Process development by ERCOT Operations and Settlements with approval through the ERCOT Committee Process. Potential tracking assignment for ERCOT Readiness team. In addition to developing the objective criteria, BP must also have steps to ensure that changes trigger posting to the MIS. | Response | MIS Team | will pass on to IRT via Punchlist | Punchlist - Coordinate with Other Teams
151 | Reliant | M. Wagner |  | FR 87, Under Under Notes: Reliant: This requires Business Process development by ERCOT Operations and Settlements with approval through the ERCOT Committee Process. Potential tracking assignment for ERCOT Readiness team. In addition to developing the objective criteria, BP must also have steps to ensure that changes trigger posting to the MIS. | Response | MIS Team | will pass on to IRT via Punchlist | Punchlist - Coordinate with Other Teams
152 | Reliant | M. Wagner |  | FR 88, Under Notes: Reliant: This requires Business Process development by ERCOT Settlements to ensure that the data are posted on time and on a recurring basis. | Response | MIS Team | will pass on to IRT via Punchlist | Punchlist - Coordinate with Other Teams
154 | Reliant | M. Wagner |  | FR 89: Reliant: Admittedly….the time stated is the time in the table. If ERCOT chooses to post Shift Schedules on a forward basis, it is unlikely to get opposition from Market Participants. The expectation is that during the Adjustment Period and Real-Time ERCOT will provide a list of Operators on duty. And since each hour is both an Operating Hour and an Adjustment Period Hour, the requirement is effectively a constant one. | Response | MIS Team | Agreed | Answer Provided - Close ?
156 | Reliant | M. Wagner |  | FR 92, Added to the end of Protocol text: [Reliant: The language here is exactly as in the table, but there is nothing in 6.4.8 about posting….and review of subsequent sections didn’t yield required information. This needs clarification from TPTF. Exactly what do we want posted here?] | Response | MIS Team | Needs clarification from TPTF | * TPTF
157 | Reliant | M. Wagner |  | FR 93, Under Posting Frequency: Reliant: this requirement requires coordination from the Outage Scheduler Team (a)(i), Operations (a)(ii), (b), (d), and (e) and aggregated information from Market System (c). Is the MIS team working with the other teams to make sure that their posting obligations are covered in the requirements for the other systems? Or is the integration team doing this? | Response | MIS Team | These coordinations and recommendations are passed to the other teams via the Punchlist | Punchlist - Coordinate with Other Teams
158 | Reliant | M. Wagner |  | FR 96, In Description: Deleted Publish Ancillary Service quantities and inserted, "Communication of SASM Results" | Response | MIS Team | Changed to Post SASM Results | Answer Provided - Close ?
159 | Reliant | M. Wagner |  | FR 96, Under Protocol text: Reliant: Business Process needed for item (3) above. Potential tracking assignment for ERCOT Readiness Team. | Response | MIS Team | Communicated to IRT via Punchlist | Punchlist - Coordinate with Other Teams
160 | Reliant | M. Wagner |  | FR 98, Under Posting Frequency: Reliant: Same as FR 89—but citation here is better. Change citation in FR89 to be the one from this requirement and delete this requirement. It would be better to invalidate the requirement (and leave the number) as some parties have already started cross references to this document---meaning that if this requirement number is dropped, all other numbering changes cascade through documents based on this one. | Rejected | MIS Team | Different protocol, different requirement. If we have a duplicate it won't be hard to fulfill it twice (!) but definitely hard to track if we delete. | Answer Provided - Close ?
161 | Reliant | M. Wagner |  | FR 99, Under Protocol text: Reliant: This requires an ERCOT business process that employs information from TSPs and the Outage Scheduler System. May need an Operating procedure to ensure that all parties are working together. Potential assignment for ERCOT Readiness Team. MIS requirement is posting ‘location.’ | response | MIS Team | passed to IRT via Punchlist for evaluation | Punchlist - Coordinate with Other Teams
163 | Reliant | M. Wagner |  | FR 102, Reliant: ERCOT Operations business process--development by Operations, tracking by ERCOT Readiness. Step near conclusion of process is submission of report for posting. MIS requirement posting ‘location.’ | Response | MIS Team | Will pass to IRT team via Punchlist | Punchlist - Coordinate with Other Teams
165 | Reliant | M. Wagner |  | FR 106, In Protocol Text, Above (e) note from Reliant: Reliant: This will require a trigger condition (for posting) from Market System. Should be specified in Market System design document. | Response | MIS Team | A design issue | Design
167 | Reliant | M. Wagner |  | FR 110, Reliant: note that presentation of this information on dynamic page must be ‘eye catching’ as it is a very serious condition. | Response | MIS Team | Design issues - Hold that thought! | Design
169 | Reliant | M. Wagner |  | FR 113, Reliant: suggest cross checking with CRR team about functionality of CRR system. Their system may meet these requirements. | Response | MIS Team | Agreed. Will communicate via Punchlist with CRR | Punchlist - Coordinate with Other Teams
170 | Reliant | M. Wagner |  | FR 115, After Protocol text: Reliant: suggest cross checking with CRR team about functionality of CRR system. Their system may meet these requirements. | Response | MIS Team | Will communicate via Punchlist with CRR | Punchlist - Coordinate with Other Teams
171 | Reliant | M. Wagner |  | FR 119, Reliant: suggest cross checking with CRR team about functionality of CRR system. Their system may meet these requirements. | Response | MIS Team | Will communicate via Punchlist with CRR | Punchlist - Coordinate with Other Teams
172 | Reliant | M. Wagner |  | FR 122, After Protocol text: Reliant: need to coordinate with CRR team to get data for most of the CRR requirements—and thought needs to be given as to how the CRR Interface will work through the MIS…or if it will be a stand alone system with some things posted on MIS. | Response | MIS Team | Will communicate via Punchlist with CRR anad will further document this during Design | Punchlist - Coordinate with Other Teams Design
173 | Reliant | M. Wagner |  | FR 124, Under Protocol text: Reliant: need to coordinate with Settlements team to obtain this info | Response | MIS Team | Will communicate with Settlements via Punchlist | Punchlist - Coordinate with Other Teams
174 | Reliant | M. Wagner |  | FR 125, Under Protocol text: Reliant: need to coordinate with Settlements team to obtain this info | Response | MIS Team |  | Punchlist - Coordinate with Other Teams
175 | Reliant | M. Wagner |  | FR 127, After protocol text: Reliant: MIS requirement is a ‘location’ for the posting…nothing else | Response | MIS Team | Agreed | Answer Provided - Close ?
176 | Reliant | M. Wagner |  | FR 128, After protocol text: Reliant: MIS should have a Compliance Section | Response | MIS Team | Addressing through index by protocol section | Addressing through index by protocol section
177 | Reliant | M. Wagner |  | FR 147, After protocol text: Reliant: This is a business process. Ensuring compliance may fall to ERCOT readiness team.] [Reliant: Settlements team will likely produce this document. MIS requirement is to ensoure a posting ‘location.’ | Response | MIS Team | Will communicate with IRT via Punchlist | Punchlist - Coordinate with Other Teams
178 | Reliant | M. Wagner |  | FR 148, After protocol text: Reliant: Again, the MIS requirement is for posting, ERCOT business requirements for development of information for posting. | Response | MIS Team | Agreed | Answer Provided - Close ?
179 | Reliant | M. Wagner |  | FR 151 Protocol text: Added "Requirement: Design MIS system so that it is sufficiently flexible to accommodate new or revised posting requirements. " Deleted the "ERCOT shall post" paragraph. | Rejected | MIS Team | It is our intention to stay true to the Protocols; Afraid we can't just change the words … sorry! However, we will make every attempt to create the MIS flexible enough to accommodate new or revised posting requirements. | Answer Provided - Close ?
180 | Reliant | M. Wagner |  | FR 152, Protocol text: Added "Requirement: Design MIS system so that it is sufficiently flexible to accommodate new or revised posting requirements. " Deleted the "To the extent a request is reasonable" paragraph. | Rejected | MIS Team |  | Answer Provided - We cannot change protocol text. Close ?
181 | Reliant | M. Wagner |  | FR 155, Note after Protocol text: Reliant: Will ERCOT provide an inventory of the PUCT posting requirements to the MIS team so that they can be appropriately parsed and assigned to the correct areas of the MIS? If this is not to occur, how would we ensure that the requirements are met? | response | MIS Team | We will provide any and all information that we are able or allowed. It is our intention to act with all honesty. | Answer Provided - Close ?
182 | Reliant | M. Wagner |  | FR 156, Note after Protocol text: Reliant: MIS team to coordinate with COPS group. Requirment is to facilitate QSE shadow settlement. Suggest that ERCOT Settlements and COPs group work to gether to define a list of what’s needed to shadow settle—and once agreement is reached, that the list be incorporated herein as the requirement. | Response | MIS Team | We will track this issue by way of Punchlist | Punchlist - Coordinate with Other Teams
183 | Reliant | M. Wagner |  | FR 157, Note after Protocol text: Reliant: It would be useful to have the security and confidentiality specifically set forth for each type of data that is posted. If this doesn’t occur, how will the rolling data entering the public domain be tracked for posting? Moreover, versioning change management are integral parts of maintaining a document/data repository that is useful. Where will such issues be addressed? | Response | MIS Team | Definitely these issues will be researched, documented, and shared during the Design phase | Design
184 | Reliant | M. Wagner |  | FR 158, Note after Protocol text: Reliant: would be useful for MIS Team and TPTF to agree on the set of standards that is deemed to exist. | Response | MIS Team | We are in process now of documenting our standards, based on a best practices model as acknowledged throughout the industry. We will share these documetns with the TPTF and working Subgroup during Design Reviews | Design
185 | Reliant | M. Wagner |  | FR 160, Note after Protocol text: Reliant: this also requires document version control by ERCOT so that Market Participants can obtain historical copies of documents that have changed—for example, revisions to the Planning Charter, or various Operating Guides…this issue might be appropriate for the ERCOT readiness team] | Response | MIS Team | Agreed | Open
186 | Reliant | M. Wagner |  | FR 161, Protocol text: Deleted heading protocol text and (1). Inserted "Post" before list. Deleted (2) Added the following note at the end of protocol text: Reliant: the requirement is to post the forms | Rejected | MIS Team | We need the list of forms for specificity | Answer Provided - Close ?
187 | Reliant | M. Wagner |  | FR 162, Protocol text: ERCOT shall post on the MIS Public Area all registration procedures and applications necessary to complete registration for any function described in these Protocols. As part of its registration procedures, ERCOT may require one or more of the following: Reasonable tests of the ability of a Market Participant to communicate with ERCOT or perform as required under these Protocols; An application fee as determined by the ERCOT Board; and  Related agreements for specific purposes (such as agency designation, meter splitting, or network interconnection) that apply only to some Market Participants.[Reliant: MIS team to provide list of applications and procedures---suggest working with ERCOT legal.] | Response | MIS Team | We cannot change the Protocols because they don't 'read well', but we agree we should work with ERCOT legal and will do so. Noted on punchlist. | Answer Provided - Close ?
188 | Reliant | M. Wagner |  | FR 163, in Protocol text: Reliant: suggest parsing appropriate information from here and combining it with previous requirement. Requirements must be measurable. Without more specificity, it will be difficult to ensure that this requirement is met. | Response | MIS Team | point well taken, Requirements must be measurable. This, like many preceeding requirements, appears to be partly business process. We will review with IRT via Punchlist to ensure clear procedures are documented and results measurable. | Punchlist - Coordinate with Other Teams
189 | Reliant | M. Wagner |  | FR 164, in Protocol text: Reliant: again, the mix of business process and MIS requirements needs to be broken up and appropriately addressed | Response | MIS Team | Agreed, adding it to the Punchlist | Punchlist - Coordinate with Other Teams
190 | Reliant | M. Wagner |  | FR 166, in Protocol text: Any Entity providing electric service to Customers in ERCOT, or in Non-ERCOT portions of Texas in areas where Customer Choice is in effect, must submit to ERCOT a Load Serving Entity Application (“LSE application”). ERCOT shall post on the MIS Public Area the form in which LSE applications must be submitted, all materials that must be provided with the LSE application, and the fee schedule, if any, applicable to LSE applications.[Reliant: seems like this could be covered in FR161…… | Rejected | MIS Team |  | Answer Provided - Close ?
191 | Reliant | M. Wagner |  | FR 167, in Protocol text: To register as a Resource Entity, an applicant must submit to ERCOT a completed Resource Entity application and any applicable fee. ERCOT shall post on the MIS Public Area the form in which Resource Entity applications must be submitted, all materials that must be provided with the Resource Entity application. .[Reliant: seems like this could be covered in FR161…… | Rejected | MIS Team |  | Answer Provided - Close ?
192 | Reliant | M. Wagner |  | FR 168, Before Protocol text: Reliant: again, suggest coordinating with CRR team. Would be useful to separate posting requirements from business process requirements (from both ERCOT and QSE perspective). | Response | MIS Team | Agreed. Will track this with IRT thru punchlist | Punchlist - Coordinate with Other Teams
193 | Reliant | M. Wagner |  | FR 169, Added after Protocol text: Reliant: does this mean each number will be published separately, or is the intention to post the Creditworthiness Standards document? | Response | MIS Team | Agreed. Standards Document, unless otherwise instructed | Punchlist - Coordinate with Other Teams
194 | Reliant | M. Wagner |  | FR 170, Beginning of Protocol text: The posting of the variousPost weighting values will be posted to the MIS for the following CRR types: | Rejected | MIS Team |  | Answer Provided - Close ?
195 | Reliant | M. Wagner |  | Section 3.2, Requirements from Current Protocols Heading RELIANT: PERHAPS BETTER STATED AS PROTOCOLS NOT SPECIFICALLY ALTERED BY NODAL? ALSO, WILL ERCOT PROVIDE A LIST OF WHAT IS CURRENTLY REQUIRED BY EXISTING PROTOCOLS AS COMPARED WITH THE NODAL PROTOCOLS (THAT MAP TO THE CITATIONS HEREIN)? (THE REQUIRMENTS SHOULD BE PRETTY SIMILAR.) IT SEEMS LIKE THIS EFFORT IS REQIRED TO ENSURE THAT EXISTING DATA SOURCES ‘MAP OVER’ TO THE NEW MIS CORRECTLY. | Response | MIS Team | Agreed. We are in process of developing a Gap Analysis now, anad will be ready to review with TPTF as soon as past Requirements process. | Answer Provided - Close ?
196 | Reliant | M. Wagner |  | FR 172, (in brackets) Protocol text: ERCOT shall use the following process when considering applications for temporary exemptions from compliance with this Section and the SMOG. [define acronym, separate MIS requirement from business processes] |  | MIS Team |  | * TPTF
197 | Reliant | M. Wagner |  | FR 174 , Posting Category (bracketed note) [Where is it now?] |  | MIS Team |  | * TPTF
198 | Reliant | M. Wagner |  | FR 174, Protocol Text: Reliant: need to be specific about the report to be posted and assign responsibility for the business process to another team.] […] The weather responsiveness determination shall be performed annually between November 1st and November 15th. No later than November 20th, ERCOT shall produce a report that contains the ESI IDs that require profile code modifications as a result of the weather responsiveness test. This report shall be published to Market Participants in a data extract via the MIS by November 20th. | Rejected | MIS Team |  | Answer Provided - Close ?
199 | Reliant | M. Wagner |  | FR 175, Note in Protocol text: Reliant: need to be specific about the report to be posted and assign responsibility for the business process to another team.] | Response | MIS Team | Notify IRT thru Punchlist re:Business Process | Punchlist - Coordinate with Other Teams
200 | Reliant | M. Wagner |  | FR 176, Posting Category: added bracketed note [Where is it now?} | Response | MIS Team | to be determined during Design | Design
201 | Reliant | M. Wagner |  | FR 176, note In Protocol text: Reliant—again, this is a combination of other existing requirements for security and shadow settlements---should be combined with those. | Response | MIS Team | Will communicate the overlap of responsibilities with other project teams thru Punchlist
202 | Reliant | M. Wagner |  | FR 177, Posting Category: note Where it is now? | Response | MIS Team | Design | Design
203 | Reliant | M. Wagner |  | FR 177, note after (2) in Protocol text: Reliant: Nodal doesn’t have ‘congestion zones.’ It does have load zones…this requirement should be brought to TPTF for clarification. | Response | MIS Team | Agreed. | * TPTF
204 | Reliant | M. Wagner |  | FR 177, note in (3) Reliant: Nodal doesn’t have ‘congestion zones.’ It does have load zones…this requirement should be brought to TPTF for clarification | Response | MIS Team | Agreed.
205 | Reliant | M. Wagner |  | FR 178, Posting Category: note added, Where is it now? | Response | MIS Team | To be determined during Design | Design
206 | Reliant | M. Wagner |  | FR 178, Protocol text: note - Reliant: also, need to define ‘settlement run types’ to ensure that posting requirement is met. Will these data be with settlement data or under another category on the MIS? | Response | MIS Team | Agreed. To be determined during Design | Design
207 | Reliant | M. Wagner |  | FR 179, Posting Category: note added, Where is it now? | Response | MIS Team | To be determined during Design | Design
208 | Reliant | M. Wagner |  | FR 179, In Notes: note added, Reliant: does this mean that there is a compliance issue with the protocols at present? | Response | MIS Team | quite possibly; to be determined and documented during Design | Design
209 | Reliant | M. Wagner |  | FR 179, in Protocol text: Reliant: Is requirement (1) complete already given that December 31, 2002 passed? What is the current posting process for (2)? This should be defined and continued and the actual report name should be incorporated as the requirement here. | Response | MIS Team | quite possibly; to be determined and documented during Design | Design
210 | Reliant | M. Wagner | 111 | FR 179, in Protocol text: ERCOT will establish a UFE Analysis Team chaired by ERCOT and consisting of Market Participants and ERCOT personnel who report to the Technical Advisory Committee: The UFE Analysis Team will: (1) Analyze UFE data from January 01, 2002 to December 31, 2002 (2) Post findings to the MIS on a monthly basis | Rejected | MIS Team |  | Answer Provided - Close ?
211 | Reliant | M. Wagner | 111 | FR 180, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
212 | Reliant | M. Wagner | 111 | FR 180, In Notes: note added, Reliant: Does this mean that there is a current violation in the compliance with the protocols? What is the requirement and will it be met? | Response | MIS Team | possibly. Design issue | Design
213 | Reliant | M. Wagner | 112 | FR 181, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
214 | Reliant | M. Wagner | 112 | FR 181, in Protocol text: Reliant: Seems like some of this is covered in FR62. Please compare the requirements to determine if there is duplication and revise requirements accordingly. | Response | MIS Team | Thanks, we will do that | Answer Provided - Close ?
215 | Reliant | M. Wagner | 112 | FR 182, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
216 | Reliant | M. Wagner | 113 | FR 182, Before Protocol text: Reliant: Seems like some of this is covered in FR62. Please compare the requirements to determine if there is duplication and revise requirements accordingly. | Response | MIS Team | Thanks, we will do that | Answer Provided - Close ?
217 | Reliant | M. Wagner | 113 | FR 183, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
219 | Reliant | M. Wagner | 113 | FR 183, Before Protocol text: Reliant: Seems like some of this is covered in FR62. Please compare the requirements to determine if there is duplication and revise requirements accordingly. | Response | MIS Team | Thanks, we will do that | Answer Provided - Close ?
220 | Reliant | M. Wagner | 113 | FR 184, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
221 | Reliant | M. Wagner | 113 | FR 184, Before Protocol text: Reliant: does this differ from the other TLF and DLF posting requirements? Please include specific requirements that set it apart. | Response | MIS Team | Thanks, we will do that | Design
222 | Reliant | M. Wagner | 114 | FR 185, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
224 | Reliant | M. Wagner | 114 | FR 185, Before Protocol text: Reliant: seems like it would be useful to assign specific names to the reports so that compliance with the provision can be ensured. What are the names of the reports posted today? | Response | MIS Team | Agreed. This is happening now in Gap Analysis, and will be documented and shared during Design
225 | Reliant | M. Wagner | 114 | FR 186, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
226 | Reliant | M. Wagner | 115 | FR 187, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
229 | Reliant | M. Wagner | 115 | FR 188, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
230 | Reliant | M. Wagner | 115 | FR 188, Protocol text: ERCOT shall post on the MIS a table containing CO2, SO2, NOx, and particulate matter emissions data on an MWh basis for each certified REC generating Facility and REC offset generating Facility. ERCOT shall use generation data gathered for the REC trading program and the most recent annual emissions data provided by either the Texas Natural Resource Conservation Commission or the United States Environmental Protection Agency, as requested from those agencies by the PUCT, to calculate these numbers. ERCOT shall use the formulas provided by the PUCT for this posting. | Rejected | MIS Team |  | Answer Provided - Close ?
231 | Reliant | M. Wagner | 116 | FR 189, Protocol text note: Reliant: More specific definition of requirement needed. Eliminate the business process parts. | Response | MIS Team | Will document during Design | Design
232 | Reliant | M. Wagner | 117 | FR 191, Protocol text: (note added at the end) Reliant: wasn’t this covered in another requirement? | Response | MIS Team | possibly; we have included every Protocol for completeness | Answer Provided - Close ?
233 | Reliant | M. Wagner | 118 | FR 192, Posting Category: note added, Where is it now? | Response | MIS Team | To be documented during Design | Design
234 | Reliant | M. Wagner | 118 | FR 193, Posting Category: note added, Where is it now? | Response | MIS Team | To be documented during Design | Design
235 | Reliant | M. Wagner | 118 | FR 193, Protocol text: Competitive Retailers and Aggregators may obtain information from ERCOT to determine or to verify the ESI ID for a Service Delivery Point (SDP) using the Service Address. CRs or Aggregators may also obtain information from ERCOT to determine or to verify the Service Address for a SDP, using the ESI ID through a look-up function on the MIS. This look-up function will return the following information for a SDP: | Rejected | MIS Team
236 | Reliant | M. Wagner | 119 | FR 194, Before Protocol text: (note) Reliant: specific requirement needs to be developed and business process reqirements eliminated. This is the MIS requirements document… | Response | MIS Team | Agreed, but the part quoted speaks to posting on MIS the request. | Answer Provided - Close ?
237 | Reliant | M. Wagner | 119 | FR 195, Posting Category: note added, Where is it now? | Response | MIS Team | To be documented during Design | Design
238 | Reliant | M. Wagner | 119 | FR 195, Protocol text: ERCOT will make available the models used to produce the forecast and backcast profiles for the settlement process. The Load Profile for forecast and backcast profile models shall be accessible via the Market Information System in a downloadable format. | Rejected | MIS Team |  | Answer Provided - Close ?
239 | Reliant | M. Wagner | 120 | FR 196, Protocol text: ERCOT will publish Load Profile data from the profile creation process, in accordance with Section 18.2.7, Daily Profile Creation Process to the Market Information System and through the common API. [Reliant…..please list the requirements of 18.2.7 in requirements language.]Load Profile data will be made available to Market Participants for a period of two (2) years.[Reliant: what version control/time process management will insure that this standard is met? | Response | MIS Team | These are such good questions! We definitely have to define this in much greater detail once we get past this milestone. A design issue | Design - Discovery
240 | Reliant | M. Wagner | 120 | FR 197, note before Protocol text: Reliant: more specific definition of what is to be posted is required. | Response | MIS Team | We will document what is currently posted and verify that it meets the Protocol language | Design - Discovery
241 | Reliant | M. Wagner | 120 | FR 197, Protocol text: Details of all validation tests will be specified in the Load Profiling Guides. The validation test reports generated as exceptions are identified and shall be posted to the Market Information System. Competitive Retailers may dispute a Load Profile ID assignment through the ERCOT settlement dispute process, as described in Section 9.5, Settlement and Billing Process, in conjunction with the Load Profiling Guides.[Reliant: this is not an MIS requirement | Response | MIS Team | Agreed it may not be an MIS requirement; we kept it because we need to verify that something isn't implied here to be posted. | Answer Provided - Close ?
242 | Reliant | M. Wagner | 121 | FR 198, Posting Category: note added, Where is it now? | Response | MIS Team | Design phase will document this | Design
243 | Reliant | M. Wagner | 121 | FR 198, End of Protocol text: Reliant: this should exist already. Include report name or description of report as requirement. | Response | MIS Team | This is already being posted and we will post the same document as this requirement | Answer Provided - Close ?
244 | Reliant | M. Wagner | 121 | FR 199, Posting Category: note added, Where is it now? | Response | MIS Team | Design phase will document this. | Design
245 | Reliant | M. Wagner | 121 | FR 199, Protocol text: TDSPs will assign each ESI ID to a Weather Zone, based on service address zip code. ERCOT will post to MIS a mapping of a Weather Zone to appropriate Customer registration element used in assigning Weather Zones. | Rejected | MIS Team |  | Answer Provided - Close ?
246 | Reliant | M. Wagner | 122 | FR 200, Posting Category: note added, Where is it now? | Response | MIS Team | Design phase will document this | Design
247 | Reliant | M. Wagner | 122 | FR 200, Note before Protocol text: Reliant: please specifically define the posting requirement and eliminate the business process from this document. A lot of the language included in this document does not represent requirements for the MIS team. | Response | MIS Team | Included the Business process as a way to provide context for the MIS requirement.
248 | Reliant | M. Wagner | 122 | FR 201, Posting Category: note added, Where is it now? | Response | MIS Team | Design phase will document this | Design
249 | Reliant | M. Wagner | 122 | FR 201, Note before Protocol text: Reliant: please specifically define the posting requirement and eliminate the business process from this document. A lot of the language included in this document does not represent requirements for the MIS team. | Response | MIS Team | Included the Business process as a way to provide context for the MIS requirement.
250 | Reliant | M. Wagner | 123 | FR 202, Posting Category: note added, Where is it now? | Response | MIS Team | Design phase will document this | Design
251 | Reliant | M. Wagner | 123 | FR 202, Note before Protocol text: Reliant: please specifically define the posting requirement and eliminate the business process from this document. A lot of the language included in this document does not represent requirements for the MIS team. | Response | MIS Team | Included the Business process as a way to provide context for the MIS requirement. | Answer Provided - Close ?
252 | Reliant | M. Wagner | 124 | FR 203, Note before Protocol text: Reliant: please specifically define the posting requirement and eliminate the business process from this document. A lot of the language included in this document does not represent requirements for the MIS team. | Response | MIS Team | Included the Business process as a way to provide context for the MIS requirement. | Answer Provided - Close ?
253 | Reliant | M. Wagner | 124 | FR 204, Note before Protocol text: Reliant: What is the specific requirement? Is it to provide an interface to the dispute process? And what elements do we need for that. Please revise the requirement, ensure it is measurable, and ensure that it is not duplicative of other requirements. | Response | MIS Team | The specific requirement is to display the application that initiates and facilitates the dispute. Data elements are part of the 'how', which is Design | Answer Provided - Close ? Design?
254 | Reliant | M. Wagner | 125 | Reliant: Please refer to the global comments at the front, and apply as appropriate to the rest of this document---removing Protocol language, business process, etc. and refining requirements so that they are granular, unique and measurable | Response | MIS Team | Done | Close ?
255 | TXU | Rspangler | General | Reliant Resources has performed an extensive review of this document. TXU recognizes the Reliant comments as substantive and endorses their effort. | Response | MIS Team | See responses to Reliant issues. | Close ?
256 | TXU | Rspangler | General | As a general comment Posting Frequency entries such as “Not specified”, “As soon as practicable” or “On schedule” are not acceptable Business Requirements. Instances in which the protocols are vague with regard to Posting Frequency must be identified and resolved to a specific value. TXU has identified certain early instances of this issue in the following (see for example FR5) but the observation applies to the entire document. It may he helpful to define a default posting frequency, for example, 1 Business Day Following an identifiable event, which applies in the absence of a specific value from the protocol text. | Response | MIS Team | Where posting frequency is unavailable in the protocols, it will be provided during design. | Design
257 | TXU | Rspangler | General | At least one instance of an inaccurate posting requirement reference at FR23 is identified. While this may be an isolated case, the error does not lend confidence to the integrity of the entire 306 requirements. | Response | MIS Team | Noted.
259 | TXU | Rspangler | Page 10 | 1.3.3 Presenting the data to the Marketplace is one of the core requirements of the MIS. Agreed the MIS probably “creates” very little data and provides access to existing data generated by other systems. But one of the fundament requirements would be to make data available in a predefined format that could possibly be different that the way it is stored. For example, the data to be provided via the MIS may be the results of a query on a database, but the formatting and presentation of that data is critical. It may need to be available to view via a portal screen and/or an XML file provided via web services. | Response | MIS Team | This is all being considered and will be part of the Design phase. | Design
260 | TXU | Rspangler | General | The format and presentation of the data is a very important element in the MIS Portal, via screen or via the API. There doesn’t appear to be any requirements addressing the way in which the data is to be provided. This should be specified on each type of requirement. The format of a protocol document would be much different that a network model, a list of contingencies, equipment ratings, prices, settlement statements, etc. This detail should be worked out before hand to ensure the availability of the data is in a usable format for the marketplace. It may be that the upstream systems should provide a description of how they are making the data available to ERCOT internally, but the vendor for the MIS should be instructed on how to make that data available to the marketplace. Then the details design should include exact output specifications for how Market Participants can interact with ERCOT to send and receive, push and pull data. | Response | MIS Team | Agreed. MIS is responsible for presenting data as received from source systems. Details of data formatting will be worked our during design. | Design
261 | TXU | Rspangler | Page 16/FR5 | “Not specified” is inadequate for a Business Requirements Document. Each of the instances which do not contain a specific posting frequency must be identified and a posting frequency assigned. With regard to this particular instance, the reference protocol section 3.1.5.13 explicitly requires the posting of this information within 1 hour of receipt by ERCOT or disposition actin by ERCOT. | Accepted | MIS Team |  | Close ?
263 | TXU | Rspangler | Page 19/FR14 | As soon as practicable – “As soon as practicable” is not an acceptable Business Requirement. In this case the changes being described in the protocol text below are processed in accordance with the NOMCR process described in Section 3.10. Posting reqruiements for approved NOMCRS aare provided in section 3.10 and this posting requirement which relates to the update of a HUB price calculation should be consistent with the Section 3.10 posting provisions for NOMCRs and ERCOT’s update to the HUB price calculation algorithm. | Accepted | MIS Team | Jane - look up | Open
264 | TXU | Rspangler | Page 20/FR15 | As soon as practicable – “As soon as practicable” is not an acceptable Business Requirement. In this case the changes being described in the protocol text below are processed in accordance with the NOMCR process described in Section 3.10. Posting reqruiements for approved NOMCRS aare provided in section 3.10 and this posting requirement which relates to the update of a HUB price calculation should be consistent with the Section 3.10 posting provisions for NOMCRs and ERCOT’s update to the HUB price calculation algorithm. | Accepted | MIS Team | Jane - look up | Open
265 | TXU | Rspangler | Page 21/FR16 | As each hub is defined – More specificity is required here. Hub busses may be defined only through the Protocol Change Process. This posting must be coordinated with the PRR process to define the new Hub, An acceptable posting frequency might be 1 Business Day following final approval of the PRR. This gives rise to the idea that a default frequency should be adopted such as “1 Business Day “ whenever the protocols do not specify a specific value. While the Protocols may not say this, it also makes sense to identify as a market notice the first active date on which the new Hub’s settlement point prices will be published by ERCOT. | Response | MIS Team | Our source documents are the Nodal Protocols. The MIS Team will continue to clarify through PR change request where necessary. Posting frequencies will be negotiated with source Program Team. | Shared issue across MIS/IDA and MMS- Consider NPRR to specify approval and posting timeline for change in Hub definitions.
267 | TXU | Rspangler | Page 24/FR23 | The FR23 protocol text does not address interim updates. Interim updates are addressed in Protocol Section 3.10.4 (3) and specific posting frequency requirements are specified – not “On schedule”. | Accepted | MIS Team |  | Open
268 | TXU | Rspangler | Page 25/FR26 | Posting Frequency: On TAC approval of new standard – More specificity is required. Post within 1- Business Day of TAC approval. | Response | MIS Team | We can only follow protocol text. | Shared issue across MIS/IDA and source data program area
269 | TXU | Rspangler | Page 26/FR29 | Posting Frequency: On schedule – more specificity is required. What does “on schedule” mean? | Accepted | MIS Team |  | * TPTF
270 | Centerpoint | Mbailey | General | Not much information is provided regarding programmatic interfaces. There are various references to CIM, XML, and MP systems, but not much detail. We assume we will have an opportunity to review and provide comments to Conceptual Design phase as stated in Section 1.3.6. | Response | MIS Team | Correct. You will have the opportunity to provide comments during design. | Design
271 | Centerpoint | Mbailey | General | Transmission data is mostly designated to be posted in the Public area which is a security risk and a violation of CEII | Response | MIS Team | We only secure data based on protocol instructions. Ican you reference a specific FR ? | Pat Harris and Floyd to work together on refining in accordance with Section 3 and/or 12 via an NPRR as appropriate.
272 | Centerpoint | Mbailey | General | Need to have programmatic interface to the MIS Messaging System to enable MP to capture alerts, messages, and notifications and to programmatically distribute throughout MP’s internal systems | Response | MIS Team | This will be documented and addressed in design. This data will be available electronically as described in the Conceptual Design Document that TPTF will be able to approve. | Design
273 | Centerpoint | Mbailey | Page 11 | Section 1.3.3 state that “MIS will not develop user interfaces. Each application is responsible for developing and providing its own user interface according to the ERCOT Developers User Guide”. Further, Section 1.3.4 “Storage and Retention” states that “Application data will be retrieved from existing ERCOT business applications through the Enterprise Service Bus except where explicitly defined otherwise in the Requirements detail sections of this document. Application data retention and expiration is the responsibility of the data/business owners” - It appears that User and Application Interfaces to MIS data will be provided by application owners via the Enterprise Service Bus. - Who or what are the application owners that are responsible for developing and providing the user interfaces and, by extension, the programmatic interfaces? - Making a distinction between responsibilities for user interface is contrary to the expectation that MIS serves and the single point of access for market data. Shouldn’t MIS be the umbrella under which the various application owners are coordinated? | Response | MIS Team | MIS is coordinating with the other nodal project teams on user interface, a consistent look and feel based on ERCOT user guidelines will be provided. This will be further addressed in design. Yes, MIS will be responsible for coordinating wit hthe other nodal teams for all Uis during the design phase. | Design
274 | Centerpoint | Mbailey | Page 59/FR104 | “Needs clarification from TPTF, other than item h: Should ERCOT post (a) the latest SE solution, or (b) All SE solutions for the hour, or (c) other proposal. Also, should the SE solution(s) be exportable as CIM compliant database?” CNP supports option (b) -posting of ALL SE solutions for the last hour. Needs to be posted in a format that is manageable and allows programmatic extraction. | Response | MIS Team | MIS team believes this needs clarification from TPTF. | *TPTF Clarification
275 | Centerpoint | Mbailey | Page 59/FR104 | CIM format currently does not support posting of SE solution results. Moreover, the CIM file size for ERCOT system is expected to be over 200 Mbytes and therefore may not be the best mechanism for posting 12 SE solutions in an hour. | Response | MIS Team | This issue will be addressed in design. | Design
276 | Centerpoint | Mbailey | Page 10 | Section 1.3.3 “Data and Applications” states that “The business area that owns each application is responsible for data validation. All services presented by the MIS portal will adhere to the ERCOT Common Information Model”. . I can understand adherence to XML, but I'm not sure CIM will extend to all non- Transmission Model data required to be posted. Conversely, will a business service have to be CIM compliant to be hosted in the MIS? | Response | MIS Team | This issue will be addressed in design. | Design
277 | Centerpoint | Mbailey | Page 10 | • Section 1.3.1 “General Assumptions” states that “All data transactions will be processed by the Enterprise Service Bus, which has the capability to support the data load” Section 1.3.1 “General Assumptions” states that “MIS availability is dictated by the following minimum browser configuration: Microsoft © Internet Explorer, Version 6 with Javascript enabled” Why does MIS place this restriction even when Section 1.3.3. states “MIS will not develop user interfaces. Each application is responsible for developing and providing its own user interface according to the ERCOT Developers User Guide” | Response | MIS Team | ERCOT is attempting to describe minimum system configuration for optimal user experience. | Design Coordinate with integration/enterprise teams.
278 | Centerpoint | Mbailey | General | All data posted to the MIS ought to be categorized as secure by default. Data categorized as public and posted to the MIS accordingly ought to be by exception only. Transmission data is generally being categorized as public. Resource & Load data are generally being categorized as secure even contrary to protocol in some cases. We reiterate that ALL data (including CRR and Congestion data) should be treated as SECURED. | Response | MIS Team | Data categorization is dictated by protocol. | Pat Harris and Floyd to work together on refining in accordance with Section 3 and/or 12 via an NPRR as appropriate.

## Close_Items
# | Issuing Entity | Name | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason | Status --
176 | Reliant | M. Wagner |  | FR 128, After protocol text: Reliant: MIS should have a Compliance Section | Response | MIS Team | Addressing through index by protocol section | Addressing through index by protocol section Close?
46 | Reliant | M. Wagner | v | Eliminate all business process descriptions in this document. This document is about data availability through electronic interfaces. | Response | MIS Team | We are following a standard RUP methodology in these requirements and using an approved template. | Answer Provided - Close ?
53 | Reliant | M. Wagner | 8 | Fourth bullet, MIS Components: Dynamic-Update area Reliant: would the daily posting requirements be characterized as ‘dynamic’? | Response | MIS Team | Yes | Answer Provided - Close ?
54 | Reliant | M. Wagner | 8 | Last bullet, MIS Components: Dashboard Style Application Reliant: Is this dashboard similar to that discussed in TPTF? (i.e., eSuites? | Response | MIS Team | Yes | Answer Provided - Close ?
62 | Reliant | M. Wagner | 10 | Data and Applications, Sixth paragraph (MIS will not develop user interfaces): Reliant: Is there any intention to attempt to standardize the interfaces? (This might be handled by the “my page” type of access point. | Response | MIS Team | Yes. | Answer Provided - Close ?
63 | Reliant | M. Wagner | 10 | Storage and Retention, Second paragraph (data retention responsibilitiy) Reliant: Where is the activity of data management living? Is this under the umbrella of the EDW? It is unclear that the ‘business owners’ will be managing the data and managing the data expiration program. All data managed under the protocols is subject to data retention requirements and there should be a defined management plan to do this—and it should also include a discussion of version control. | Response | MIS Team | This issue has been turned over to the Data Warehouse. | Answer Provided - Close ?
67 | Reliant | M. Wagner | 13 | FR 1, Description: Deleted all but the first sentence Reliant: the crossed out information is not a function of the MIS Reliant: it would be useful to provide a description of what the ‘list’ would look like. For example, it would be useful to have the various types of documents grouped together---discussions may be required around whether the groupings should be by functionality (Operating Guides, Registration) or topic: for exmple---dividing registration forms by market participant type. Separate from this project ERCOT business processes are required to effect many other elements of these Protocol requirements—including things documented above (crossed out) such as how to format the first pages of the docs, and document expiration, email requirements, etc. | Description Text change accepted Rejected description of list | MIS Team | Other binding documents are defined in protocol language. | Answer Provided - Close ?
70 | Reliant | M. Wagner | 13 thru169 | FR 1 - 306, Protocol Text: Delete Reliant: it would be more consistent to reference the protocol language and not quote it in these documents in order to bring brevity to the documents and preparation and to avoid unintentional errors in transferring the protocol language. | Rejected | MIS Team | Protocol text is provided in every case to add clarity and specificity. This comment will not be responded to in every instance in this document. | Answer Provided - Close ?
154 | Reliant | M. Wagner |  | FR 89: Reliant: Admittedly….the time stated is the time in the table. If ERCOT chooses to post Shift Schedules on a forward basis, it is unlikely to get opposition from Market Participants. The expectation is that during the Adjustment Period and Real-Time ERCOT will provide a list of Operators on duty. And since each hour is both an Operating Hour and an Adjustment Period Hour, the requirement is effectively a constant one. | Response | MIS Team | Agreed | Answer Provided - Close ?
158 | Reliant | M. Wagner |  | FR 96, In Description: Deleted Publish Ancillary Service quantities and inserted, "Communication of SASM Results" | Response | MIS Team | Changed to Post SASM Results | Answer Provided - Close ?
160 | Reliant | M. Wagner |  | FR 98, Under Posting Frequency: Reliant: Same as FR 89—but citation here is better. Change citation in FR89 to be the one from this requirement and delete this requirement. It would be better to invalidate the requirement (and leave the number) as some parties have already started cross references to this document---meaning that if this requirement number is dropped, all other numbering changes cascade through documents based on this one. | Rejected | MIS Team | Different protocol, different requirement. If we have a duplicate it won't be hard to fulfill it twice (!) but definitely hard to track if we delete. | Answer Provided - Close ?
175 | Reliant | M. Wagner |  | FR 127, After protocol text: Reliant: MIS requirement is a ‘location’ for the posting…nothing else | Response | MIS Team | Agreed | Answer Provided - Close ?
178 | Reliant | M. Wagner |  | FR 148, After protocol text: Reliant: Again, the MIS requirement is for posting, ERCOT business requirements for development of information for posting. | Response | MIS Team | Agreed | Answer Provided - Close ?
179 | Reliant | M. Wagner |  | FR 151 Protocol text: Added "Requirement: Design MIS system so that it is sufficiently flexible to accommodate new or revised posting requirements. " Deleted the "ERCOT shall post" paragraph. | Rejected | MIS Team | It is our intention to stay true to the Protocols; Afraid we can't just change the words … sorry! However, we will make every attempt to create the MIS flexible enough to accommodate new or revised posting requirements. | Answer Provided - Close ?
181 | Reliant | M. Wagner |  | FR 155, Note after Protocol text: Reliant: Will ERCOT provide an inventory of the PUCT posting requirements to the MIS team so that they can be appropriately parsed and assigned to the correct areas of the MIS? If this is not to occur, how would we ensure that the requirements are met? | response | MIS Team | We will provide any and all information that we are able or allowed. It is our intention to act with all honesty. | Answer Provided - Close ?
186 | Reliant | M. Wagner |  | FR 161, Protocol text: Deleted heading protocol text and (1). Inserted "Post" before list. Deleted (2) Added the following note at the end of protocol text: Reliant: the requirement is to post the forms | Rejected | MIS Team | We need the list of forms for specificity | Answer Provided - Close ?
187 | Reliant | M. Wagner |  | FR 162, Protocol text: ERCOT shall post on the MIS Public Area all registration procedures and applications necessary to complete registration for any function described in these Protocols. As part of its registration procedures, ERCOT may require one or more of the following: Reasonable tests of the ability of a Market Participant to communicate with ERCOT or perform as required under these Protocols; An application fee as determined by the ERCOT Board; and  Related agreements for specific purposes (such as agency designation, meter splitting, or network interconnection) that apply only to some Market Participants.[Reliant: MIS team to provide list of applications and procedures---suggest working with ERCOT legal.] | Response | MIS Team | We cannot change the Protocols because they don't 'read well', but we agree we should work with ERCOT legal and will do so. Noted on punchlist. | Answer Provided - Close ?
190 | Reliant | M. Wagner |  | FR 166, in Protocol text: Any Entity providing electric service to Customers in ERCOT, or in Non-ERCOT portions of Texas in areas where Customer Choice is in effect, must submit to ERCOT a Load Serving Entity Application (“LSE application”). ERCOT shall post on the MIS Public Area the form in which LSE applications must be submitted, all materials that must be provided with the LSE application, and the fee schedule, if any, applicable to LSE applications.[Reliant: seems like this could be covered in FR161…… | Rejected | MIS Team |  | Answer Provided - Close ?
191 | Reliant | M. Wagner |  | FR 167, in Protocol text: To register as a Resource Entity, an applicant must submit to ERCOT a completed Resource Entity application and any applicable fee. ERCOT shall post on the MIS Public Area the form in which Resource Entity applications must be submitted, all materials that must be provided with the Resource Entity application. .[Reliant: seems like this could be covered in FR161…… | Rejected | MIS Team |  | Answer Provided - Close ?
194 | Reliant | M. Wagner |  | FR 170, Beginning of Protocol text: The posting of the variousPost weighting values will be posted to the MIS for the following CRR types: | Rejected | MIS Team |  | Answer Provided - Close ?
195 | Reliant | M. Wagner |  | Section 3.2, Requirements from Current Protocols Heading RELIANT: PERHAPS BETTER STATED AS PROTOCOLS NOT SPECIFICALLY ALTERED BY NODAL? ALSO, WILL ERCOT PROVIDE A LIST OF WHAT IS CURRENTLY REQUIRED BY EXISTING PROTOCOLS AS COMPARED WITH THE NODAL PROTOCOLS (THAT MAP TO THE CITATIONS HEREIN)? (THE REQUIRMENTS SHOULD BE PRETTY SIMILAR.) IT SEEMS LIKE THIS EFFORT IS REQIRED TO ENSURE THAT EXISTING DATA SOURCES ‘MAP OVER’ TO THE NEW MIS CORRECTLY. | Response | MIS Team | Agreed. We are in process of developing a Gap Analysis now, anad will be ready to review with TPTF as soon as past Requirements process. | Answer Provided - Close ?
198 | Reliant | M. Wagner |  | FR 174, Protocol Text: Reliant: need to be specific about the report to be posted and assign responsibility for the business process to another team.] […] The weather responsiveness determination shall be performed annually between November 1st and November 15th. No later than November 20th, ERCOT shall produce a report that contains the ESI IDs that require profile code modifications as a result of the weather responsiveness test. This report shall be published to Market Participants in a data extract via the MIS by November 20th. | Rejected | MIS Team |  | Answer Provided - Close ?
210 | Reliant | M. Wagner | 111 | FR 179, in Protocol text: ERCOT will establish a UFE Analysis Team chaired by ERCOT and consisting of Market Participants and ERCOT personnel who report to the Technical Advisory Committee: The UFE Analysis Team will: (1) Analyze UFE data from January 01, 2002 to December 31, 2002 (2) Post findings to the MIS on a monthly basis | Rejected | MIS Team |  | Answer Provided - Close ?
214 | Reliant | M. Wagner | 112 | FR 181, in Protocol text: Reliant: Seems like some of this is covered in FR62. Please compare the requirements to determine if there is duplication and revise requirements accordingly. | Response | MIS Team | Thanks, we will do that | Answer Provided - Close ?
216 | Reliant | M. Wagner | 113 | FR 182, Before Protocol text: Reliant: Seems like some of this is covered in FR62. Please compare the requirements to determine if there is duplication and revise requirements accordingly. | Response | MIS Team | Thanks, we will do that | Answer Provided - Close ?
219 | Reliant | M. Wagner | 113 | FR 183, Before Protocol text: Reliant: Seems like some of this is covered in FR62. Please compare the requirements to determine if there is duplication and revise requirements accordingly. | Response | MIS Team | Thanks, we will do that | Answer Provided - Close ?
230 | Reliant | M. Wagner | 115 | FR 188, Protocol text: ERCOT shall post on the MIS a table containing CO2, SO2, NOx, and particulate matter emissions data on an MWh basis for each certified REC generating Facility and REC offset generating Facility. ERCOT shall use generation data gathered for the REC trading program and the most recent annual emissions data provided by either the Texas Natural Resource Conservation Commission or the United States Environmental Protection Agency, as requested from those agencies by the PUCT, to calculate these numbers. ERCOT shall use the formulas provided by the PUCT for this posting. | Rejected | MIS Team |  | Answer Provided - Close ?
232 | Reliant | M. Wagner | 117 | FR 191, Protocol text: (note added at the end) Reliant: wasn’t this covered in another requirement? | Response | MIS Team | possibly; we have included every Protocol for completeness | Answer Provided - Close ?
236 | Reliant | M. Wagner | 119 | FR 194, Before Protocol text: (note) Reliant: specific requirement needs to be developed and business process reqirements eliminated. This is the MIS requirements document… | Response | MIS Team | Agreed, but the part quoted speaks to posting on MIS the request. | Answer Provided - Close ?
238 | Reliant | M. Wagner | 119 | FR 195, Protocol text: ERCOT will make available the models used to produce the forecast and backcast profiles for the settlement process. The Load Profile for forecast and backcast profile models shall be accessible via the Market Information System in a downloadable format. | Rejected | MIS Team |  | Answer Provided - Close ?
241 | Reliant | M. Wagner | 120 | FR 197, Protocol text: Details of all validation tests will be specified in the Load Profiling Guides. The validation test reports generated as exceptions are identified and shall be posted to the Market Information System. Competitive Retailers may dispute a Load Profile ID assignment through the ERCOT settlement dispute process, as described in Section 9.5, Settlement and Billing Process, in conjunction with the Load Profiling Guides.[Reliant: this is not an MIS requirement | Response | MIS Team | Agreed it may not be an MIS requirement; we kept it because we need to verify that something isn't implied here to be posted. | Answer Provided - Close ?
243 | Reliant | M. Wagner | 121 | FR 198, End of Protocol text: Reliant: this should exist already. Include report name or description of report as requirement. | Response | MIS Team | This is already being posted and we will post the same document as this requirement | Answer Provided - Close ?
245 | Reliant | M. Wagner | 121 | FR 199, Protocol text: TDSPs will assign each ESI ID to a Weather Zone, based on service address zip code. ERCOT will post to MIS a mapping of a Weather Zone to appropriate Customer registration element used in assigning Weather Zones. | Rejected | MIS Team |  | Answer Provided - Close ?
251 | Reliant | M. Wagner | 123 | FR 202, Note before Protocol text: Reliant: please specifically define the posting requirement and eliminate the business process from this document. A lot of the language included in this document does not represent requirements for the MIS team. | Response | MIS Team | Included the Business process as a way to provide context for the MIS requirement. | Answer Provided - Close ?
252 | Reliant | M. Wagner | 124 | FR 203, Note before Protocol text: Reliant: please specifically define the posting requirement and eliminate the business process from this document. A lot of the language included in this document does not represent requirements for the MIS team. | Response | MIS Team | Included the Business process as a way to provide context for the MIS requirement. | Answer Provided - Close ?
253 | Reliant | M. Wagner | 124 | FR 204, Note before Protocol text: Reliant: What is the specific requirement? Is it to provide an interface to the dispute process? And what elements do we need for that. Please revise the requirement, ensure it is measurable, and ensure that it is not duplicative of other requirements. | Response | MIS Team | The specific requirement is to display the application that initiates and facilitates the dispute. Data elements are part of the 'how', which is Design | Answer Provided - Close ? Design?
180 | Reliant | M. Wagner |  | FR 152, Protocol text: Added "Requirement: Design MIS system so that it is sufficiently flexible to accommodate new or revised posting requirements. " Deleted the "To the extent a request is reasonable" paragraph. | Rejected | MIS Team | We cannot change protocol text. | Answer Provided - Close ?
254 | Reliant | M. Wagner | 125 | Reliant: Please refer to the global comments at the front, and apply as appropriate to the rest of this document---removing Protocol language, business process, etc. and refining requirements so that they are granular, unique and measurable | Response | MIS Team | Done | Close ?
255 | TXU | Rspangler | General | Reliant Resources has performed an extensive review of this document. TXU recognizes the Reliant comments as substantive and endorses their effort. | Response | MIS Team | See responses to Reliant issues. | Close ?
261 | TXU | Rspangler | Page 16/FR5 | “Not specified” is inadequate for a Business Requirements Document. Each of the instances which do not contain a specific posting frequency must be identified and a posting frequency assigned. With regard to this particular instance, the reference protocol section 3.1.5.13 explicitly requires the posting of this information within 1 hour of receipt by ERCOT or disposition actin by ERCOT. | Accepted | MIS Team |  | Close ?

## Design
# | Issuing Entity | Name | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason | Status --
81 | Reliant | M. Wagner | 21 | FR 15, Under Posting Frequency: Reliant:: This requirement, is more ‘real time’ than a lot of the other posting requirements. The MIS team (mostly the market participants) need to give some thought to both the real time pages and the more static data presentation… | Response | MIS Team | Agreed. Adding "As soon as applicable with real -time implications". | (element of) Design
42 | Reliant | M. Wagner | iv | General Comment on MIS relationship to other systems: This document needs to be clear about whether ‘post on the MIS’ is happening through the MIS—or through an MIS access point to a window into various source system databases or source system UIs. Some of the source systems—Outage Scheduler and CRRs for example—will have user interfaces. And if information is posted on those UIs—should it be “mapped” to the MIS? Perhaps we could do a better job with a verbal discussion of the concern at the next TPTF. | Response | MIS Team | This will be documented and addressed in design. | Design
45 | Reliant | M. Wagner | v | Document where existing data are posted (on the current portal/MIS) and use this as a proposal for the “posting category” for all of the currently posted data for which the posting category is labeled as “Not Specified.” After categorization a list of the data elements and proposed categorization should be presented to TPTF and COPS for a final determination of the categorization level. For requirements that exist –but for which nothing is posted—these should be listed and provided to Market Rules or ERCOT Legal for follow up. | Response | MIS Team | All part of a future design phase. These requirements address part of current work. | Design
50 | Reliant | M. Wagner | 6 | #2 - content displayed in Extract category: Reliant: does ‘extract data’ include ad hoc query request functionality described below, or does this mean standard data extracts? | Response | MIS Team | Refers to extract data in general. | Design
51 | Reliant | M. Wagner | 7 | Last bullet of MIS Objectives: Develop a catalog of procedures for handling, securing and protecting information. Reliant: does this mean that each data report will be assigned to a category—and the categories posted—or somehow provided to the Market Participants—so that we can figure out which level of access is needed for different data? | Response | MIS Team | Yes all part of design (through roles definition) | Design
52 | Reliant | M. Wagner | 8 | First bullet, MIS Components: Configurable 'My Page' Reliant: TPTF previously discussed that a user would be able to choose from the catalog of reported data and determine if it he/she required access to the specific data report. Is this included in the configuration of “My Page”? | Response | MIS Team | Yes - all implementation of the My Page is part of design | Design
57 | Reliant | M. Wagner | 9 | Security, First paragraph: Reliant: it would be useful to have a diagram of the layers. | Response | MIS Team | That will come in design | Design
71 | Reliant | M. Wagner | 16 | FR 5, Description: [Reliant: Might be useful to coordinate with the Outage Scheduler team. This requirement might be accomplished by a link to a ‘window’ in the Outage Scheduler system—with appropriate security measures.] | Response | MIS Team | We will coordinate this during the design phase with the Outage team. | Design
79 | Reliant | M. Wagner | 20 | FR 13, Under Posting Frequency: Reliant: The list of names that comprise the hub will likely need to come from the NMMS team. The elements that comprise the Hubs are defined in the Protocols, but the names don’t conform to the CIM standard that is being developed for NMMS | Response | MIS Team | This issue will be addressed in design. | Design
107 | Reliant | M. Wagner | 35 | FR 41, Under Posting Frequency: Reliant: Needs coordination with Operations. Real time posting required. “Location” for posting applicable requirement for MIS team. Potentially discuss the dynamic vs. static page design requirements—and associated archiving procedures. | Response | MIS Team | Design Phase | Design
120 | Reliant | M. Wagner | 42 | FR 54, Under Posting Frequency: Reliant: This is a Real Time posting requirement and it should ‘live’ on the RT page when the need is announced---so there needs to be a way to populate the RT page with dynamic messages like this. | Response | MIS Team | Agreed. Will be addressed in Design. | Design
121 | Reliant | M. Wagner | 43 | FR 56, Under Posting Frequency: Reliant: Should be a link from the RT page. | Response | MIS Team | This is Design | Design
122 | Reliant | M. Wagner | 44 | FR 57, In Notes: Data should be pushed to the QSE and available for random access? [Reliant: what does this mean? Is random access referring to the public site or querying capability? We should also be able to query for historical values and download current information—if that is what is meant by random access.] via web interface by all users. Retention period should be set based on further MP/ERCOT discussion. Retention for this Data element could be based on the rolling 7-day COP [Reliant: Recommend that AS requirements be saved off in files with weather and load forecast information for each day and kept available (online) for 2 years.] Under Notes: Reliant: ERCOT Operations will develop daily AS Plans (for the next day—the Operating Day). The Plan is the Systemwide need. This information should be posted to the public page at 0600 each day. It might also be useful to have a link to this posting from the RT page.] | Response | MIS Team | New Requirement, and not in scope now. This could be added but may require an NPRR. Random access was added by someone from the subgroup working on the matrix, and was only in NOTES, not a clear requirement. It means available for download. Much of this recommendation can be addressed during Desgn, we've made some notes but please be sure and bring these up as we move forward. | Design
165 | Reliant | M. Wagner |  | FR 106, In Protocol Text, Above (e) note from Reliant: Reliant: This will require a trigger condition (for posting) from Market System. Should be specified in Market System design document. | Response | MIS Team | A design issue | Design
167 | Reliant | M. Wagner |  | FR 110, Reliant: note that presentation of this information on dynamic page must be ‘eye catching’ as it is a very serious condition. | Response | MIS Team | Design issues - Hold that thought! | Design
183 | Reliant | M. Wagner |  | FR 157, Note after Protocol text: Reliant: It would be useful to have the security and confidentiality specifically set forth for each type of data that is posted. If this doesn’t occur, how will the rolling data entering the public domain be tracked for posting? Moreover, versioning change management are integral parts of maintaining a document/data repository that is useful. Where will such issues be addressed? | Response | MIS Team | Definitely these issues will be researched, documented, and shared during the Design phase | Design
184 | Reliant | M. Wagner |  | FR 158, Note after Protocol text: Reliant: would be useful for MIS Team and TPTF to agree on the set of standards that is deemed to exist. | Response | MIS Team | We are in process now of documenting our standards, based on a best practices model as acknowledged throughout the industry. We will share these documetns with the TPTF and working Subgroup during Design Reviews | Design
200 | Reliant | M. Wagner |  | FR 176, Posting Category: added bracketed note [Where is it now?} | Response | MIS Team | to be determined during Design | Design
202 | Reliant | M. Wagner |  | FR 177, Posting Category: note Where it is now? | Response | MIS Team | Design | Design
205 | Reliant | M. Wagner |  | FR 178, Posting Category: note added, Where is it now? | Response | MIS Team | To be determined during Design | Design
206 | Reliant | M. Wagner |  | FR 178, Protocol text: note - Reliant: also, need to define ‘settlement run types’ to ensure that posting requirement is met. Will these data be with settlement data or under another category on the MIS? | Response | MIS Team | Agreed. To be determined during Design | Design
207 | Reliant | M. Wagner |  | FR 179, Posting Category: note added, Where is it now? | Response | MIS Team | To be determined during Design | Design
208 | Reliant | M. Wagner |  | FR 179, In Notes: note added, Reliant: does this mean that there is a compliance issue with the protocols at present? | Response | MIS Team | quite possibly; to be determined and documented during Design | Design
209 | Reliant | M. Wagner |  | FR 179, in Protocol text: Reliant: Is requirement (1) complete already given that December 31, 2002 passed? What is the current posting process for (2)? This should be defined and continued and the actual report name should be incorporated as the requirement here. | Response | MIS Team | quite possibly; to be determined and documented during Design | Design
211 | Reliant | M. Wagner | 111 | FR 180, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
212 | Reliant | M. Wagner | 111 | FR 180, In Notes: note added, Reliant: Does this mean that there is a current violation in the compliance with the protocols? What is the requirement and will it be met? | Response | MIS Team | possibly. Design issue | Design
213 | Reliant | M. Wagner | 112 | FR 181, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
215 | Reliant | M. Wagner | 112 | FR 182, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
217 | Reliant | M. Wagner | 113 | FR 183, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
220 | Reliant | M. Wagner | 113 | FR 184, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
221 | Reliant | M. Wagner | 113 | FR 184, Before Protocol text: Reliant: does this differ from the other TLF and DLF posting requirements? Please include specific requirements that set it apart. | Response | MIS Team | Thanks, we will do that | Design
222 | Reliant | M. Wagner | 114 | FR 185, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
225 | Reliant | M. Wagner | 114 | FR 186, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
226 | Reliant | M. Wagner | 115 | FR 187, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
229 | Reliant | M. Wagner | 115 | FR 188, Posting Category: note added, Where is it now? | Response | MIS Team | Design issue | Design
231 | Reliant | M. Wagner | 116 | FR 189, Protocol text note: Reliant: More specific definition of requirement needed. Eliminate the business process parts. | Response | MIS Team | Will document during Design | Design
233 | Reliant | M. Wagner | 118 | FR 192, Posting Category: note added, Where is it now? | Response | MIS Team | To be documented during Design | Design
234 | Reliant | M. Wagner | 118 | FR 193, Posting Category: note added, Where is it now? | Response | MIS Team | To be documented during Design | Design
237 | Reliant | M. Wagner | 119 | FR 195, Posting Category: note added, Where is it now? | Response | MIS Team | To be documented during Design | Design
242 | Reliant | M. Wagner | 121 | FR 198, Posting Category: note added, Where is it now? | Response | MIS Team | Design phase will document this | Design
244 | Reliant | M. Wagner | 121 | FR 199, Posting Category: note added, Where is it now? | Response | MIS Team | Design phase will document this. | Design
246 | Reliant | M. Wagner | 122 | FR 200, Posting Category: note added, Where is it now? | Response | MIS Team | Design phase will document this | Design
248 | Reliant | M. Wagner | 122 | FR 201, Posting Category: note added, Where is it now? | Response | MIS Team | Design phase will document this | Design
250 | Reliant | M. Wagner | 123 | FR 202, Posting Category: note added, Where is it now? | Response | MIS Team | Design phase will document this | Design
256 | TXU | Rspangler | General | As a general comment Posting Frequency entries such as “Not specified”, “As soon as practicable” or “On schedule” are not acceptable Business Requirements. Instances in which the protocols are vague with regard to Posting Frequency must be identified and resolved to a specific value. TXU has identified certain early instances of this issue in the following (see for example FR5) but the observation applies to the entire document. It may he helpful to define a default posting frequency, for example, 1 Business Day Following an identifiable event, which applies in the absence of a specific value from the protocol text. | Response | MIS Team | Where posting frequency is unavailable in the protocols, it will be provided during design. | Design
259 | TXU | Rspangler | Page 10 | 1.3.3 Presenting the data to the Marketplace is one of the core requirements of the MIS. Agreed the MIS probably “creates” very little data and provides access to existing data generated by other systems. But one of the fundament requirements would be to make data available in a predefined format that could possibly be different that the way it is stored. For example, the data to be provided via the MIS may be the results of a query on a database, but the formatting and presentation of that data is critical. It may need to be available to view via a portal screen and/or an XML file provided via web services. | Response | MIS Team | This is all being considered and will be part of the Design phase. | Design
260 | TXU | Rspangler | General | The format and presentation of the data is a very important element in the MIS Portal, via screen or via the API. There doesn’t appear to be any requirements addressing the way in which the data is to be provided. This should be specified on each type of requirement. The format of a protocol document would be much different that a network model, a list of contingencies, equipment ratings, prices, settlement statements, etc. This detail should be worked out before hand to ensure the availability of the data is in a usable format for the marketplace. It may be that the upstream systems should provide a description of how they are making the data available to ERCOT internally, but the vendor for the MIS should be instructed on how to make that data available to the marketplace. Then the details design should include exact output specifications for how Market Participants can interact with ERCOT to send and receive, push and pull data. | Response | MIS Team | Agreed. MIS is responsible for presenting data as received from source systems. Details of data formatting will be worked our during design. | Design
270 | Centerpoint | Mbailey | General | Not much information is provided regarding programmatic interfaces. There are various references to CIM, XML, and MP systems, but not much detail. We assume we will have an opportunity to review and provide comments to Conceptual Design phase as stated in Section 1.3.6. | Response | MIS Team | Correct. You will have the opportunity to provide comments during design. | Design
272 | Centerpoint | Mbailey | General | Need to have programmatic interface to the MIS Messaging System to enable MP to capture alerts, messages, and notifications and to programmatically distribute throughout MP’s internal systems | Response | MIS Team | This will be documented and addressed in design. This data will be available electronically as described in the Conceptual Design Document that TPTF will be able to approve. | Design
273 | Centerpoint | Mbailey | Page 11 | Section 1.3.3 state that “MIS will not develop user interfaces. Each application is responsible for developing and providing its own user interface according to the ERCOT Developers User Guide”. Further, Section 1.3.4 “Storage and Retention” states that “Application data will be retrieved from existing ERCOT business applications through the Enterprise Service Bus except where explicitly defined otherwise in the Requirements detail sections of this document. Application data retention and expiration is the responsibility of the data/business owners” - It appears that User and Application Interfaces to MIS data will be provided by application owners via the Enterprise Service Bus. - Who or what are the application owners that are responsible for developing and providing the user interfaces and, by extension, the programmatic interfaces? - Making a distinction between responsibilities for user interface is contrary to the expectation that MIS serves and the single point of access for market data. Shouldn’t MIS be the umbrella under which the various application owners are coordinated? | Response | MIS Team | MIS is coordinating with the other nodal project teams on user interface, a consistent look and feel based on ERCOT user guidelines will be provided. This will be further addressed in design. Yes, MIS will be responsible for coordinating wit hthe other nodal teams for all Uis during the design phase. | Design
275 | Centerpoint | Mbailey | Page 59/FR104 | CIM format currently does not support posting of SE solution results. Moreover, the CIM file size for ERCOT system is expected to be over 200 Mbytes and therefore may not be the best mechanism for posting 12 SE solutions in an hour. | Response | MIS Team | This issue will be addressed in design. | Design
276 | Centerpoint | Mbailey | Page 10 | Section 1.3.3 “Data and Applications” states that “The business area that owns each application is responsible for data validation. All services presented by the MIS portal will adhere to the ERCOT Common Information Model”. . I can understand adherence to XML, but I'm not sure CIM will extend to all non- Transmission Model data required to be posted. Conversely, will a business service have to be CIM compliant to be hosted in the MIS? | Response | MIS Team | This issue will be addressed in design. | Design
41 | Reliant | M. Wagner | iv | Global Comment on Data for the Market: Nearly everything that is posted on the dynamic content area will need to be accessible to Market Participants in real time. To avoid too much screen scraping—thought should be given to providing this information in an API format as well as posting it on the Dynamic section of the MIS. That said, if screen scraping is required, then displays should be designed where the browser just renders the html. If this is the plan, we encourage ERCOT to refrain from using javascript or other impediments to scraping. Alternatively, ERCOT could choose to provide Market Participants with access to the infrastructure that feeds the displays. OR, ERCOT could provide an API for everything on the dynamic site (every display with applicable market data) along with all of the other public/secure/certified data. OR, ERCOT could provide a set of CSV or XML files that contain the data in the displays in real time—providing Market Participants with a schedule of when to download the files (for SCED we may need a “push” given that it may not execute every 5 minutes under certain conditions). | Response | MIS Team | This will be documented and addressed in design. This data will be available electronically as described in the Conceptual Design Document that TPTF will be able to approve. | Design
44 | Reliant | M. Wagner | v | Define granular, specific, measurable (“Can we test it/track it to meet the requirement?”), unique (no overlap with other requirements) requirements. (This document appears to contain duplicate requirements—and this needs to be remedied.) | Rejected | MIS Team | We are required by the process to list every protocol, even if it is a duplicate. The granular, specific and measureable is something we don't know at this time- part of the design plan. | Design
239 | Reliant | M. Wagner | 120 | FR 196, Protocol text: ERCOT will publish Load Profile data from the profile creation process, in accordance with Section 18.2.7, Daily Profile Creation Process to the Market Information System and through the common API. [Reliant…..please list the requirements of 18.2.7 in requirements language.]Load Profile data will be made available to Market Participants for a period of two (2) years.[Reliant: what version control/time process management will insure that this standard is met? | Response | MIS Team | These are such good questions! We definitely have to define this in much greater detail once we get past this milestone. A design issue | Design - Discovery
240 | Reliant | M. Wagner | 120 | FR 197, note before Protocol text: Reliant: more specific definition of what is to be posted is required. | Response | MIS Team | We will document what is currently posted and verify that it meets the Protocol language | Design - Discovery
277 | Centerpoint | Mbailey | Page 10 | • Section 1.3.1 “General Assumptions” states that “All data transactions will be processed by the Enterprise Service Bus, which has the capability to support the data load” Section 1.3.1 “General Assumptions” states that “MIS availability is dictated by the following minimum browser configuration: Microsoft © Internet Explorer, Version 6 with Javascript enabled” Why does MIS place this restriction even when Section 1.3.3. states “MIS will not develop user interfaces. Each application is responsible for developing and providing its own user interface according to the ERCOT Developers User Guide” | Response | MIS Team | ERCOT is attempting to describe minimum system configuration for optimal user experience. | Design Coordinate with integration/enterprise teams.
123 | Reliant | M. Wagner | 44 | FR 58, In Notes: Data should be pushed to the QSE and available for random access? via web interface by all users. [Reliant: we take random access to mean that we can query for the historical information and that the current information will be posted.] Retention period should be set based on further MP/ERCOT discussion. This provision is an extension of (1) above and likely means that if ERCOT determines an Emergency condition, that it should notice that with the details when it makes the 0600 AS Plan posting discussed in (1) above. [Reliant: In general this value is not related to an emergency condition. It is the percent of RRS that can be supplied by load. It is a number determined by Operations and it should be posted with the daily AS Plan. BUT when ERCOT declares an emergency or determines that an “Emergency Condition may exist”, it can change the level of Load providing the Service and to that end, it would be posted on the Public page and potentially with any Emergency Notification. This reference envisions posting by 0600---so it isn’t as dynamic as posting other ‘emergency’ conditions.] | Response | MIS Team | there is no mention of historical data being available here other than in notes. If necessary for historical data to be available, and any requirements for data rentention periods, we will pass this along to EDW team via the Punchlist. | Design to determine Punchlist - Coordinate with Other Teams
47 | Reliant | M. Wagner | v | Coordinate with the other design teams (this is critical!) to make sure that requirements are synchronized and ownership lies with one team. (There should be an internal QA process that does this before these documents get issued!) | Response | MIS Team | This will be documented and addressed in design. | Design/Process

## NPRR
# | Issuing Entity | Name | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason | Status --
6 | LCRA | C. Bascom | 45 | FR 72 - Posting Frequency: Deleted "Not specified" & inserted "When an Ancillary Trade is reported to ERCOT" Added the following sentence to the end of the protocol text: "This includes purchases of Ancillary Services where ERCOT is the Supplier." | Response | MIS Team | The frequency is continuous. The last sentence is not in May 2006 protocols | NPRR.xls
43 | Reliant | M. Wagner | v | Cite the protocols (with date so that version is clear). Do not copy protocol language into the requirements docs as the requirement. Write a requirement that meets the statement in the Protocols. All requirements should map to Nodal protocols. | Rejected | MIS Team | All protocols refer to May 2006 as documented in Assumptions. The requirement that meets the protocol is documented in the Description field. | NPRR.xls
66 | Reliant | M. Wagner | 11 | Structure, protocol references Reliant: Please confirm that no posting changes have occurred due to the NPRRs that have passed since May. | Response | MIS Team | We are tracking all NPRRs and there will be an overall program strategy for dealing with these. | NPRR.xls
68 | Reliant | M. Wagner |  | FR 2, Posting Frequency: Reliant: Effectively this is a rolling requirement. Each day new data become eligible for posting. Also, need to review PUC Substantive Rule 25.504 – Is there an NPRR needed? | Response | MIS Team | Agreed this is a rolling requirement. NPRR noted and will be investigated. | NPRR.xls
94 | Reliant | M. Wagner | 28 | FR 28, Protocol Text: Reliant Added bracketed, non-italicized text: ...If an interim update is implemented, ERCOT shall report changes to the PUCT Market Oversight Division and the Independent Market Monitor [need clean up NPRR to change this to WEMM]. ERCOT shall provide Notice via electronic means to all Market Participants and post on the MIS Secure Area detailing the changed model information and the reason for the interim update within two Business Days following report to PUCT and WEIMM. [Need clean-up NPRR?]. | Response | MIS Team | We have noted this potential need for NPRR and language cleanup, will track this issue | NPRR.xls
10 | LCRA | C. Bascom | 71 | FR 125 - Inserted "INFO" into the PTP Option value formula: RTOPTPRINFO (j, k) | Response | MIS Team | We have kept to the May 2006 protocols in order to remain consistent | NPRR.xls synchronize with NPRR that modified formula (in August 2006 protocols)

## To_TPTF
# | Issuing Entity | Name | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason | Status --
156 | Reliant | M. Wagner |  | FR 92, Added to the end of Protocol text: [Reliant: The language here is exactly as in the table, but there is nothing in 6.4.8 about posting….and review of subsequent sections didn’t yield required information. This needs clarification from TPTF. Exactly what do we want posted here?] | Response | MIS Team | Needs clarification from TPTF | * TPTF
196 | Reliant | M. Wagner |  | FR 172, (in brackets) Protocol text: ERCOT shall use the following process when considering applications for temporary exemptions from compliance with this Section and the SMOG. [define acronym, separate MIS requirement from business processes] |  | MIS Team |  | * TPTF
197 | Reliant | M. Wagner |  | FR 174 , Posting Category (bracketed note) [Where is it now?] |  | MIS Team |  | * TPTF
203 | Reliant | M. Wagner |  | FR 177, note after (2) in Protocol text: Reliant: Nodal doesn’t have ‘congestion zones.’ It does have load zones…this requirement should be brought to TPTF for clarification. | Response | MIS Team | Agreed. | * TPTF
269 | TXU | Rspangler | Page 26/FR29 | Posting Frequency: On schedule – more specificity is required. What does “on schedule” mean? | Accepted | MIS Team |  | * TPTF
274 | Centerpoint | Mbailey | Page 59/FR104 | “Needs clarification from TPTF, other than item h: Should ERCOT post (a) the latest SE solution, or (b) All SE solutions for the hour, or (c) other proposal. Also, should the SE solution(s) be exportable as CIM compliant database?” CNP supports option (b) -posting of ALL SE solutions for the last hour. Needs to be posted in a format that is manageable and allows programmatic extraction. | Response | MIS Team | MIS team believes this needs clarification from TPTF. | *TPTF Clarification

## Open_Items
# | Issuing Entity | Name | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason | Status --
48 | Reliant | M. Wagner | 6 | Reliant General Question – In the specific post requirements, what is the process for resolving the “not specified” items under Posting Frequency? | Response | MIS Team | We are obtaining that information from the MIS subgroup -- ongoing. | ongoing
49 | Reliant | M. Wagner | 6 | First paragraph: The requirements in this document will provide a single point of access for Market Participants, the PUCT Reliant: does this mean that the Wholesale Electric Market Monitor (at the direction of PUCT) will access through the MIS? If not, perhaps the use of PUCT isn’t correct here. | Response | MIS Team | Investigating who this group is and what their access needs to be. | Open
61 | Reliant | M. Wagner | 10 | Data and Applications, Fifth paragraph (fail-over defined the Disaster Recovery): Reliant: a document reference for what the guidelines are is required for this to ensure that the guidelines are met and are able to be tested in the failover process. | Response | MIS Team | Guidelines are being developed. | Open
64 | Reliant | M. Wagner | 10 | Performance Reliant: will these be summarized in an appendix? Seems like it would be helpful to have a summary of the posting requirements/response times/data retention requirements in one document to facilitate data management and to ensure that statistics on meeting requirements can be developed from analysis of the function of the MIS. | Response | MIS Team | This is in process now in the form of our data inventory. | Open
65 | Reliant | M. Wagner | 10 | MIS Migration and Integration Reliant: will the plan include the existing ERCOT website or specifically portal applications (only)? Specificity is needed here to understand exactly what will be migrated? | Response | MIS Team | This is still under discussion with ERCOT. | Open
185 | Reliant | M. Wagner |  | FR 160, Note after Protocol text: Reliant: this also requires document version control by ERCOT so that Market Participants can obtain historical copies of documents that have changed—for example, revisions to the Planning Charter, or various Operating Guides…this issue might be appropriate for the ERCOT readiness team] | Response | MIS Team | Agreed | Open
263 | TXU | Rspangler | Page 19/FR14 | As soon as practicable – “As soon as practicable” is not an acceptable Business Requirement. In this case the changes being described in the protocol text below are processed in accordance with the NOMCR process described in Section 3.10. Posting reqruiements for approved NOMCRS aare provided in section 3.10 and this posting requirement which relates to the update of a HUB price calculation should be consistent with the Section 3.10 posting provisions for NOMCRs and ERCOT’s update to the HUB price calculation algorithm. | Accepted | MIS Team | Jane - look up | Open
264 | TXU | Rspangler | Page 20/FR15 | As soon as practicable – “As soon as practicable” is not an acceptable Business Requirement. In this case the changes being described in the protocol text below are processed in accordance with the NOMCR process described in Section 3.10. Posting reqruiements for approved NOMCRS aare provided in section 3.10 and this posting requirement which relates to the update of a HUB price calculation should be consistent with the Section 3.10 posting provisions for NOMCRs and ERCOT’s update to the HUB price calculation algorithm. | Accepted | MIS Team | Jane - look up | Open
267 | TXU | Rspangler | Page 24/FR23 | The FR23 protocol text does not address interim updates. Interim updates are addressed in Protocol Section 3.10.4 (3) and specific posting frequency requirements are specified – not “On schedule”. | Accepted | MIS Team |  | Open
271 | Centerpoint | Mbailey | General | Transmission data is mostly designated to be posted in the Public area which is a security risk and a violation of CEII | Response | MIS Team | We only secure data based on protocol instructions. Ican you reference a specific FR ? | Pat Harris and Floyd to work together on refining in accordance with Section 3 and/or 12 via an NPRR as appropriate.
278 | Centerpoint | Mbailey | General | All data posted to the MIS ought to be categorized as secure by default. Data categorized as public and posted to the MIS accordingly ought to be by exception only. Transmission data is generally being categorized as public. Resource & Load data are generally being categorized as secure even contrary to protocol in some cases. We reiterate that ALL data (including CRR and Congestion data) should be treated as SECURED. | Response | MIS Team | Data categorization is dictated by protocol. | Pat Harris and Floyd to work together on refining in accordance with Section 3 and/or 12 via an NPRR as appropriate.