## Slide 1: ERCOT Outage Evaluation & Resolution Phases I & II PR 60006_01 Project Update Retail Market Subcommittee November 8, 2006 Adam D. Martinez Mgr, Market Operations DPO

## Slide 2: Current Activities
Recent Activities
  Market Notice sent on Nov. 1 for PaperFree fileserver installation to Production
  Project team conducted planning meetings with TDTWG leadership to finalize Market cut-over plans for NAESB migration
    Only service providers will be required to test; however, all MPs are encouraged to test with ERCOT
    Test timeframes will be scheduled; ERCOT support available
Next Steps
  Conduct Market testing kick-off call week of 11/13/06
  Complete scheduling for Market Participants by 11/17/06
  Complete ERCOT production migration to new parallel environment by 11/21/06
  Page 2

## Slide 3: Change Impacts
Issue
  Availability of storage to support project resulted in a delay to the production dates originally planned
Scope
  No impact to scope
Schedule
  2-month delay (Oct. to Dec.) for test & production migration dates
  PaperFree fileserver migration to Prod – 11/11 (Nov. Retail Release)
  MP interoperability testing for new NAESB system – starts 11/27
    Primary Market testing scheduled through 1/12/07
    Secondary Market testing 1/15/07 – 1/26/07
Budget
  No change to total budget; $90K moved from 2006 to 2007
  Page 3

## Slide 4: Migration Timeline
Production Systems Ready
Migration Complete
  Page 4

## Slide 5: Market Impacts
Market Changes
  Will require Market Participant system changes; instructions and scripts available 11/21/06. Changes include:
    Change to new Production NAESB URL (NAESB.ercot.com)
    New User ID/Password
    New PGP key
    New SSL certificates (if necessary)
    IP address changes to firewalls (if necessary)
Cut-over
  ERCOT’s Production environment available for individual Market transitions upon completion of testing by that MP
  Existing NAESB in parallel production until all MPs are transitioned; target is 01/31/07
  Metrics will only be reported on new system beginning 01/31/07
  Page 5

## Slide 6: Questions / Contact
Adam D. Martinez
Mgr, MO DPO
ERCOT
(512) 248-3883
amartinez@ercot.com
  Page 6