## Slide 1: PR50121_07 Retail Business Processes (RBP) Project Update Retail Market Subcommittee November 8, 2006 Adam D. Martinez Mgr, Market Operations DPO

## Slide 2: Current Events
Project Status – Currently on target for Schedule, Scope, and budget
Project Phases
  Initiation – Completed 08/01/05
  Planning – Completed 05/08/06
  Execution
    Go-Live on 12/10/06 weekend; Stabilization through 02/09/07
  Closing – Target to complete February 2007
Recent Activities
  All Code has been delivered to iTEST
Next Steps
  Begin Siebel Data Conversion Staging in Production on 11/3/06 weekend (will continue each weekend until complete)
  Continue EIF Data Conversion every weekend until complete
  Begin Load Testing 11/03/06
  Continue UAT
  Page 2

## Slide 3
Project Milestones
Requirements (pens down) – Completed April 12, 2006
Design (internal document) – Completed July 14, 2006
Build – Completed July 28, 2006 for Core Components
Internal Testing – Target Completion Date of December 1, 2006
Internal Training – Target Completion of November 18, 2006
Production (Go live) – Weekend December 10, 2006
**Code Migration, Data Conversion, and Production Verification
  Page 3

## Slide 4: Testing Status
Testing Schedule
  Transaction Processing: started 08/28 – 87% complete (~ 600 scripts)
  Retail TML: started 10/02 – 63% (approx. 50 scripts)
  Reprocessing: started 10/02 – 5% (approx. 70 scripts)
  ETS Testing: started 10/02 – 67% (approx. 60 scripts)
  Load/Performance Testing: Starts 11/3 - 0% (Rescheduled)
  Monitoring Testing: Starts 11/13 – 0% (Rescheduled)
Defect Status
  134 total to date as of 11/01/06; only 49 of those have been TIBCO
  Breakdown
    Code – 63
    Configuration – 14
    Environment – 37
    Invalid – 16
    Unknown (Under Review) – 4
  Page 4

## Slide 5: Implementation Weekend
RMS approved SLA exception for Migration Weekend
DATE AFFECTED: From 7:00 AM Friday, December 8, 2006 to 11:30 PM Sunday, December 10, 2006 (accommodates Migration, Data Conversion, Verification, and avoid high-volume transaction weekends)
ADDITIONAL INFORMATION: During this outage the following functions will be affected:
  Market Participants utilizing NAESB WILL be able to send to ERCOT but will NOT be able to Receive from ERCOT during the outage.
    **NAESB will be offline between 8:00AM to 9:00AM Saturday, December 9, 2006 to for server reboot.
  867 Transactions will NOT be forwarded during the outage.
  997 Functional Acknowledgements will NOT be sent during the outage.
  Cancel/Notification batch exception in the event of a roll-back on December 10, 2006
  Retail components of the TML and API will NOT be available including
    Report Explorer / Search Reports
    Find ESI
    Find Transaction
    Submit Transactions
    USA Functionalities
  Page 5

## Slide 6: Implementation Weekend (cont)
Data Conversion Load Mitigation
  54 hours to complete
  Reduce the outage to the Market by launching Go-Live with 3-6 months of 2006 descending transactional data (previously stored in Seebeyond TCH Database)
  Phase in remaining years on following weekends. (Low to zero Risk)
    ETC by late December 31st, 2006 / January 7th, 2007
  Retail TML and API Find Transaction will be limited to Data Conversion Load
  Page 6

## Slide 7: Migration Weekend Timeline
  Page 7

## Slide 8: Questions / Contact
Adam D. Martinez
Mgr, Market Operations
Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Hope Parrish
Project Manager, Market Operations
Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com