## October 5, 2006
TDTWG - ERCOT Issue Log
July 26, 2006 - October 3, 2006
Issue Date | Notification Date | Start Time | End Time | Duration (mins) | Application | Issue Description | Identification Method | Impact | Root Cause | Resolution | Date Implemented | Notes | TDTWG Meeting Comments
2006-10-02 | 2006-10-03 | 7:46PM | 7:56PM | 18 | Paperfree | Paperfree File Server network outage | Monitoring | Outage | Hardware failure | Already included in another project | 2006-10-03 | SCR745 | Complete - SCR745 Phase 1 - implementation 11-11-06 - yellow status
2006-09-27 | 2006-09-27 | n/a | n/a | n/a | TIBCO | Delayed 867_03 IDR and NIDR Activity Reports | Monitoring | Report Delay | Data Exception | Already included in another project | 2006-09-28 | Increased Hawk monitoring to capture and correct exception immediately | Complete - Green status
2006-09-26 | 2006-09-29 | 12:02AM | 4:04PM | 242 | Paperfree | 997s not sent during outages | Market Notification / Daily Report | Transaction Loss | TBD | Not already included in another project | n/a | Result of Paperfree outage | Phase 1 of SCR745 - implementation date of 11-11-06
2006-09-25 | 2006-09-29 | 1:58AM | 3:47PM | 829 | Paperfree | 997s not sent during outages | Market Notification / Daily Report | Transaction Loss | TBD | Not already included in another project | n/a | Result of Paperfree outage | Phase 1 of SCR745 - implementation date of 11-11-06
2006-09-26 | 2006-09-26 | 12:02PM | 4:04PM | 242 | Paperfree | Paperfree File Server not responding | Monitoring | Outage | TBD | Not already included in another project | 2006-09-26 | ERCOT has engaged IBM and EMC to find root cause and resolution | Code implemented to reduce occurrences - Yellow status/monitoring in progress
2006-09-25 | 2006-09-25 | 1:58AM | 3:47PM | 829 | Paperfree | Paperfree File Server not responding | Market Notification / Monitoring | Outage | NIC driver error | Not already included in another project | 2006-09-25 | ERCOT has engaged IBM and EMC to find root cause and resolution | Code implemented to reduce occurrences - Yellow status/monitoring in progress
9/22/06 - 9/26/06 | 9/22/06 - 9/27/06 | n/a | n/a | n/a | Paperfree | 814 and 867 transactions duplicated | Monitoring | Transaction Duplication | TBD | Not already included in another project | n/a | ERCOT has engaged IBM and EMC to find root cause and resolution | Code implemented to reduce occurances - Yellow status/monitoring in progress
2006-09-20 | 2006-09-20 | n/a | n/a | n/a | TML API | Market Participants receiving the “No ESI ID found” message when using the API and to research | Market Notification | Information not available | Code issue | Already included in another project | 2006-09-28 |  | Complete - Green status
2006-09-21 | 2006-09-21 | ~2:00AM | ~4:00AM | 120 | Siebel | Siebel Batch continued following SBMI issue with future dated evaluation date | Market Notification | Order Cancellations | Incorrect date used | One time occurrence | 2006-09-21 | Process change and Training implemented | Complete - Green status
2006-09-21 | 2006-09-21 | 12:55AM | 1:03AM | 8 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
2006-09-19 | 2006-09-19 | n/a | n/a | n/a | Paperfree | Annual Validation backlog of 814_20 Maintains | Market Coordination / Monitoring | Backlog | Annual Validation and system limitations | Annual occurrence | n/a | current backlog is ~300K | Complete for 2006 - Green status - long term fix to be implemented in Feb 07
2006-09-11 | 2006-09-11 | 12:46AM | 12:49AM | 3 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
8/15/06 - 9/8/06 | 2006-09-08 | n/a | n/a | n/a | Siebel | ESIID address deleted from database | Exception Processing | Rejected Transactions | Software Bug | Already included in another project | n/a | Implementation date to be determined | In progress - yellow status - fix to be in place Feb 07
2006-09-05 | 2006-09-05 | n/a | n/a | n/a | TIBCO | Posting delay for extracts and reports | Market Notification / Monitoring | Report Delay | Component Nonresponsive | Already included in another project | 2006-09-06 | Redifined Hawk monitoring agent rules | Complete - Architecture change in place - Green Status
2006-08-30 | 2006-08-31 | 9:17PM | 9:28PM | 11 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
2006-08-24 | 2006-08-24 | n/a | n/a | n/a | TIBCO | Posting delay for extracts and reports | Market Notification / Monitoring | Report Delay | Component Nonresponsive | Already included in another project | 2006-08-24 | Implementation of Hawk monitoring agent | Complete - Architecture change in place - Green Status
2006-08-08 | 2006-08-08 | n/a | n/a | n/a | TIBCO | Delayed TDSP ESIID Report | Monitoring | Report Delay | Code issue with implementation | Already included in another project | TBD |  | Complete - Architecture change in place - Green Status
2006-08-02 | 2006-08-02 | 1:10AM | 1:13AM | 3 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
2006-07-27 | 2006-07-27 | 1:00AM | 9:30AM | 510 | Paperfree | 814 and 867 transactions duplicated | Monitoring | Transaction Duplication | TBD | Not already included in another project | n/a | ERCOT has engaged IBM and EMC to find root cause and resolution | Code implemented to reduce occurrences - Yellow status/monitoring in progress