## Slide 1: Flight Testing Update

## Slide 2: Flight 1006
Details
Flight Kick-Off Conference Call: 10/06/06
Flight began with Day 1 transactions flowing: 10/09/06
Flight 1006 scheduled to conclude: 11/21/06
  Contingency testing scheduled to conclude: 12/12/06

## Slide 3: Flight 1006
Flight Manifest
6 TDSPs
4 New REPs – 18 New Relationships
5 New Umbrella DUNs
2 Existing REPs testing in a new territory – 2 New Relationships
2 Existing REP testing new functionality
3 Existing REPs testing Change of Service Provider
1 Existing REP (New Umbrella DUNs) changing Banks
5595 Total Tasks (68 of 5595 Total MarkeTrak API tasks)

## Slide 4: Flight 1006
Progress
Connectivity complete
Flight started on time
As of 11/07/06 at 9:00 AM
  Day 22
    72.59% complete
    81.56% by end of day

## Slide 5: Flight 1006
Progress (continued)
0 outstanding transactions for Week 1
  0 Inbound to ERCOT
  0 Outbound from ERCOT
  0 Point-to-Point
11 outstanding transactions for Week 2
  2 Inbound to ERCOT
  2 Outbound from ERCOT
  7 Point-to-Point

## Slide 6: Flight 1006
Progress (continued)
15 outstanding transactions for Week 3
  1 Inbound to ERCOT
  2 Outbound from ERCOT
  12 Point-to-Point
91 outstanding transactions for Week 4
  27 Inbound to ERCOT
  12 Outbound from ERCOT
  52 Point-to-Point

## Slide 7: Flight 1006
Progress (continued)
301 outstanding transactions for Week 5 (Test Days 21 & 22 only)
  212 Inbound to ERCOT
  63 Outbound from ERCOT
  26 Point-to-Point

## Slide 8: MarkeTrak API Certification
MarkeTrak
Flight 1006 was the first Flight to Market test and certify for MarkeTrak API
Testing Participants – 4 (3 TDSPs, 1 CR)
8 scripts utilized for MarkeTrak API testing / certification
  Originally, a total of 4 MarkeTrak scripts were created
  Now, 3 scripts broken out/ created for TDSPs & 3 scripts broken out/ created for CRs
  Plus 1 ERCOT/CR Connectivity script (CON57) and 1 ERCOT/TDSP Connectivity script (CON58)

## Slide 9: MarkeTrak API Certification
MarkeTrak API certification testing completed successfully with all four parties as of Wednesday, 11/01/06
Future MarkeTrak API Certification may be completed ad-hoc, as long as the testing is not during a scheduled black-out period.

## Slide 10: Questions
Notes: <number>
<footer>
<header>
<date/time>