## Slide 1: Enhancements to FasTrak PR 50007 Project Update Retail Market Subcommittee November 8, 2006 Adam Martinez Mgr, Market Operations DPO

## Slide 2: Current Activities
Go live – only 5 days from today!!
Recent Accomplishments
  ERCOT completed UAT and regression testing (October 20th)
    Identified 2 additional deferred defects
    Total of 6 deferred defects
  Successfully migrated to CERT environment (October 27th)
  Successfully migrated to Production environment (November 1st)
Ongoing / Upcoming Activities
  Started API CERT testing with MPs (October 30th)
  Production verification (start on November 3rd)
  API production verification with MPs (November 8th & 9th)
Market Test Activities
  3 out of 4 MPs involved in Market Test are completed with their CERT Testing (as of November 1st)
  Page 2

## Slide 3: User Pre-loading Status
User Setups Performed by ERCOT
  Deadline for MPs to send information to ERCOT for mass pre-loading has passed (10/13/2006)
  To date only 60% of CRs have submitted their User Profile Spreadsheets to ERCOT for preloading of users prior to go-live date
  Any CR who has not submitted a spreadsheet and who is planning to use MarkeTrak, must follow steps below
User Setups performed by MP
  For CRs not requesting pre-load
  Must contact ERCOT to create your MarkeTrak Administrator
  After administrator role is created, MP will have to create its users in MarkeTrak
  Detailed instructions are posted to the project website
  Page 3

## Slide 4: Schedule Status
Project Activity | Duration | Dates | Status
ITest Environment Migration | 1 week | 9/18 – 9/24 | Complete
ERCOT UAT GUI & API Regression Test | 4 weeks | 9/25 – 10/20 | Complete
GUI Sandbox | Approx. 4 weeks | 9/27 – 10/20 | Complete
Market Training | 2 days | 10/12 – 10/16 | Complete
Migration to CERT Environment | 1 week | 10/23 – 10/29 | Complete
Market CERT Test – API | 2 weeks | 10/30 – 11/10 | In Progress
Production Migration & Stabilization Prior to Market Release | 2 weeks | 10/30 – 11/10 | In Progress
Go Live (Market Release) | 1 Day | 11/13 | Not Started
  Page 4

## Slide 5: UAT Results Review
MarkeTrak testing completed on October 20th
A total of 282 UAT and 1634 Regression test scripts were successfully executed
There were a total of 16 defects logged with this testing effort
Defect Count | Defect Status | Root Cause
3 | Closed | Code
5 | Closed | Configuration
4 | Closed | Documentation
1 | Closed | Environment
1 | Invalid | Script Errors, Data, etc.
2 | Deferred | For Future Enhancement
  Page 5

## Slide 6: Deferred Business Requirements
# | Defect # / Description | Reason to Defer | Workaround | Status / Date for implementation
1 | (1897) TML to MarkeTrak Link prompts for Digital Cert twice | The business requirement states that users will only have to enter their digital certificate once. | Current work-around is for users to create “Favorites” link directly to MarkeTrak to avoid additional prompt for certificate. | OPEN - Will need to work with Verisign - Date TBD
2 | (1905) While there are 3 concurrent users (same dig cert) the MarkeTrak system does not properly display the error messages for invalid data | ERCOT has repeatedly educated the Market during this effort that all users need to have their own digital certificate | This is not an issue impacting requirements as ERCOT has required that all users be assigned individual digital certificates. | CLOSED - Will not be fixed - each user at each MP will need to have own digital certificate.
3 | (1926) Inadvertent Switch Issues – The Siebel call is not populating all of the necessary data | The business requirement states that MarkeTrak will interface with Siebel to auto-populate information associated with Inadvertent Switch issues after it is submitted to ERCOT | ERCOT has already agreed to continue to support Siebel data population via manual steps as done today. ERCOT will monitor volumes of Inadvertant Switch Issues and will escalate issue resolution if volumes become unmanageable. | OPEN - SIR # 10909 and #10689 are targeted for Feb 2007 release
4 | (2210) Bulk Insert Performance – The requirement states that each issue submitted via Bulk Insert must be submitted in three seconds or less | In the testing environment, issues submitted via Bulk Insert consistently are submitted in 4.5 seconds | ERCOT will monitor results to ensure optimal performance and minimal impact to user experience. | OPEN - Need to review production stats after go live - Date TBD
5 | (2530) Problems with display of new report 'Number of issues submitted by Month' | The business requirement asked for fields that were not valid. | ERCOT will review the requirements for reports and determine what changes need to be made to meet market expecations | OPEN - Need to review reporting needs / feedback from market after go live - Date TBD
6 | (2553) API permissions for Query only | The business requirement is the permission for a Query only MP is they are unable to submit. The request failed, however the response error message referenced the wrong UserID. | The submit does fail, wrong error message will need to be ignored. ERCOT has issue open with software vendor for resolution. | OPEN - Need resolution identfied by software vendor. Date TBD
  Page 6

## Slide 7: MarkeTrak Migration Plan Review
November
8th & 9th
Saturday
11/11/06
Sunday
11/12/06
Monday
11/13/06
Continue to be able to enter new issues
New entry disabled
FasTrak New Issues
90 days

FasTrak In Progress
Continue to be able to work ‘in progress’ issues
MarkeTrak Prod Ver
ERCOT staff conducting Prod Ver
API Prod Ver
MarkeTrak–GO LIVE
New issues in MarkeTrak
ERCOT will keep the FasTrak tool online (with entry of new issues disabled) for a period of ninety (90) calendar days after the implementation of MarkeTrak to production. This is in support of the current timelines in the market for the working of DEV issues.
MP / ERCOT
  Page 7

## Slide 8: Questions / Contacts
Adam D. Martinez
Mgr, MO DPO
ERCOT
(512) 248-3883
amartinez@ercot.com
Scott Egger
Business Analyst, MO DPO
ERCOT
(512) 248-3162
segger@ercot.com
  Page 8