## Slide 1: Market Coordination Team Update Retail Market Subcommittee November 8, 2006 Susan Munson Retail Market Liaison

## Slide 2: Project Schedule
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 3: Risks / Issues
Issue | Mitigation | Owner
PR50121_07 RBP – Stabilization necessary for successful implementation | Schedule management Milestone completion | ERCOT
PUCT Mandate of 07/01/2007 poses tight timeline | Schedule and resource management Milestone completion | All
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 4
PR40038_01 Status
Status:
  On target for schedule, budget, and scope
Project Phases:
  Initiation – Completed
  Planning – Target completion date 12/22/2006 (Original = 12/9/2006)
  Execution – Mandated completion date July 1, 2007; Go-Live 06/24/2007
  Closing – Target completion is post go-live
Recent Activity:
  ERCOT Conceptual Design Reviews Completed for TIBCO, Paperfree/NAESB, Siebel
  TML Requirements Review Completed
  MCT Initial review of Draft Scope of Production Implementation
Next Steps for ERCOT:
  Complete Exception Handling Requirements (ETS, Reprocessing, ODS, other Tools)
  Complete Core Detail Designs (TIBCO, Siebel, Paperfree/NAESB, TML, ODS)
Next Steps for MCT:
  Continue to monitor Market issues and progress
  Begin Market progress reporting in January, 2007
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 5: Texas SET 3.0 Progress Reporting: What will be reported?
All Market Participants will be required to provide their progress on Design, Development, and Internal Testing of Texas SET V3.0 and identify any risks that may delay Flight 0407 or Implementation of Version 3.0
Progress will be reported as % complete
Non-response will default to previous month’s status

## Slide 6: Texas SET 3.0 Progress Reporting: Who will report?
All CRs and TDSPs currently active in the Market and ERCOT
Primary business contacts for all active CRs and TDSPs will be notified by end of November 2006 to provide a reporting contact person, phone number, and email address
If the primary business contact requests their EDI service provider to be their reporting contact, this must be stated in an email to the MCT lead, Susan Munson (smunson@ercot.com)

## Slide 7: Texas SET 3.0 Progress Reporting: When will reports be given?
The Market Coordination Team lead will report project status
throughout the project lifecycle to RMS each month
Progress will be reported starting at January, 2007 RMS meeting and concluding at the May, 2007 RMS meeting
Progress report is due 10 days prior to the RMS meeting each month via email
Due to the holidays, progress reports for January RMS status are due by COB January 3, 2006
Reminder emails will be sent one week prior to the status due date each month

## Slide 8: Texas SET 3.0 Progress Reporting: What is the reporting format?
Progress report will be similar to previous market releases
(MIMO, V2.1)

## Slide 9: Example of RMS Presentation - CRs

## Slide 10: Example of RMS Presentation - TDSPs and ERCOT

## Slide 11: Texas SET 3.0 Progress Reporting: Summary
The Market Coordination Team lead will report project status throughout the project lifecycle to RMS each month. This will include the percentage complete by each Market Participant through the design, development, and internal testing phases of the project, and any additions to the original design or process. The lead will be responsible for gathering this information from the Market Participants each month.

## Slide 12
Meeting Dates and Locations through 2006
  December – CenterPoint in Houston (12/11)
(Note: all meetings are held in conjunction with TX SET meetings)
Future Meetings/Market Communications
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 13: ERCOT Contacts
ERCOT Project Manager ERCOT SR. Business Analyst
Hope Parrish Jennifer Frederick
hparrish@ercot.com jfrederick@ercot.com
512-248-6522 (w) 512-248-6733 (w)
512-771-9582 (c) 512-413-0815 (c)
ERCOT Market Liaison
Susan Munson
smunson@ercot.com
512-248-3881 (w)
512-826-0564 (c)
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO

## Slide 14: Questions?
Project: PR40038_01 Current Phase: Planning
2006 PPL Source: Market/PUCT Priority: 2.1 Rank: 54 Budget: $3-$5 MM Program Area: RO