## Open MCT Action Items
Date Opened | Action Item | Resolution | Status | Date Last Updated
October, 2006 | Write TX SET Issue for 814_03 and 814_14 gray box language for N1 Customer name segment to be considered after Texas SET 3.0. This would be to remove the phrase "in the absence of current Rep of Record's customer information" | 11/6 - Rob Bevill to draft TX SET issue | Pending | 2006-11-06
October, 2006 | Clean up Retail Market Guide to revise processes that will be changed or deleted after Texas SET 3.0 goes into production | Consider the governance process timeline and add to MCT agenda accordingly - 11/6 - add to December MCT meeting to begin work | Pending | 2006-11-06
November, 2006 | Modify RMG and/or Protocols to document proposed process of ERCOT sending ESI ID, Customer Name, and phone number to TDSPs in the event of Mass Transition. This process will be implemented in Retail Release following TX SET 3.0 Implementation via SIR. | Jennifer Garcia will check Protocols & RMG to initiate process of writing PRR &/or RMGRR | Pending | 2006-11-06
November, 2006 | TX SET issue needed to revise grayboxes on 650_04 for use of BGN06 on reconnect for denial of access. In addition, this issue will contain changes for Disconnect for Non-pay BGN matching discussed at previous meeting. | Cary Reed to write TX SET issue for future implementation (after Texas SET 3.0) | Pending | 2006-11-06
November, 2006 | 867_03 Problematic scenario is cancelling an estimated read that occurred prior to Texas SET 3.0 Implementation on 7/1/07 because the original will not contain the REF~5I but the cancel is required to in Version 3.0 Proposed solution to send REF~5I on the cancel with "D10" as the code in REF02, reason of 'Prior to V3.0", and estimation counters of "0". | TDSPs and CRs to review if they can handle the proposed solution of REF~5I estimates. Can CRs handle a REF~5I after REF~5I on cancel of original prior to 7/1/07? All MPs send concerns and issues to TX SET listserve prior to December meeting. This item will be discussed @ Dec. MCT. Also bring up at TX SET. | Pending | 2006-11-06

## Closed Action Items
Date Opened | Action Item | Resolution | Status | Date Last Updated
August, 2006 | Email box for MCT questions/issues – Post FAQs to MCT website. | Susan Munson to have mailbox set up for MCT questions/issues; Post FAQs to MCT page of ERCOT.com | Closed | 2006-10-03
August, 2006 | Impacts to TML for TX SET 3.0? | ERCOT will report back on TML Changes at next MCT meeting. | Closed | 2006-09-11
September, 2006 | Update Market Requirements document with ERCOT solutions to POLR Rule requirements | ERCOT to redline Market Requirements document; October 3 MCT meeting to review | Closed | 2006-10-03
September, 2006 | Review Test Script Brainstorm list; add new script ideas | All MCT bring ideas to October 3 MCT meeting | Closed | 2006-10-03
September, 2006 | CRs & TDSPs come up with ideas for solution to 650_01 reconnect issue (CR submits standard; CR submits Priority; CR cancels standard; TDSP rejects Priority and cancels standard - how to handle?) | Revisit this issue at October 3 MCT meeting; discuss ideas and "pain points" for all MPs; Discussed at 10/3 meeting - CRs to review their processes; CRs will not get reconnects done faster by submitting priorities; no change control at this time | Closed | 2006-10-03
September, 2006 | Determine acceptable error threshold on Customer Billing Information file validation by ERCOT | Decision at October 3 MCT meeting; decided to set no threshold - ERCOT will handle "one-off situations with CRs" as needed; ERCOT will report to PUCT what was sent by CRs | Closed | 2006-10-03
September, 2006 | Update MCT Issues Log | Susan Munson to update and bring to October 3 MCT meeting | Closed | 2006-10-24
October, 2006 | What does "dummy data" on Customer Billing Contact Information File for new CRs look like? Who will provide? Add clarification to Market Requirements Document | New CRs will create their own mock data for this file; This information will be explained in the test script and at Flight Orientation. | Closed | 2006-10-24
August, 2006 | Safety Net Reject Code from TDSP to ERCOT on 814_04 – Change control needed for 814_11? | Catherine Meiners to write TX SET Issue. | Closed | 2006-11-06
October, 2006 | Discuss F2, F3, F4 (RMG) - File layouts for Mass Transition ESI ID spreadsheets to POLR CRs. Add POLR Customer Class and Voluntary/Non-Voluntary CR Status | Reviewed the spreadsheets and will submit RMGRR on urgent status through Texas SET for F2, F3, and F5; 11/6 - RMGRR046 granted urgent status by RMS and will be voted on at 11/8 RMS | Closed | 2006-11-06
October, 2006 | TDSPs and CRs to bring back their answers to the question: On 650_04 reconnects (RC004) for Denial of Access, should they send the BGN02 from the Disconnect in the BGN06? | Discuss at 11/6 meeting; 11/6 - not required, but graybox in Implementation Guide needs clarification. Cary Reed to write TX SET issue for future implementation (after Texas SET 3.0) | Closed | 2006-11-06
October, 2006 | ERCOT to review possibility of sending limited customer billing contact info file to TDSPs during mass transition (i.e. customer name and phone number) | Discuss at 11/6 meeting; 11/6 - market agreed with ERCOT sending file containing ESI ID, customer name, and primary phone number to TDSPs. ERCOT will go through SIR process in retail release following Texas SET 3.0 Implementation 7/1/07. Jennifer Garcia will check Protocols & RMG to initiate process of writing PRR &/or RMGRR | Closed | 2006-11-06
October, 2006 | Confirm how TXU ED is responding to the 814_04 in the N1 Customer Name field (ie.using 'Mass Transition Customer' or substituting actual Customer name; Gray boxes on 814_14 may need to be changed as a result (and change control). | Discuss at 11/6 meeting; 11/6 - TXU ED is echoing back 'Mass Transition Customer' in 814_04. No updates to 814_14 gray box necessary | Closed | 2006-11-06

## Parking Lot Items
Date Opened | Parking Lot Item | Resolution | Status | Date Last Updated