## Open TX SET Action Items
Date Opened | Action Item | Resolution | Status | Date Last Updated
2006-10-06 | MPs to take Texas SET transaction checklist back to their shops; review necessity for negative response transactions | Kathy Scott to send out; To be discussed at 10/25-26 meetings and RMGRR filed. 10/26/2006 - May require additional discussion at a later time - Need to evaluate the benefit of changing the current process. | Pending | 2006-10-05
2006-10-06 | Swimlane Sub-team to meet and determine new strategy for creating and maintaining swimlanes | Team to meet on 10/12/06 chaired by Kyle Patrick 10/26/06 - Sub-team will present to TX SET their changes at the November meeting | Pending | 2006-10-04
2006-10-06 | Protocol Revision Request is necessary for re-try queue for the 814_20 Maintenance Transction when the maintenance request is rejected for A76 - ESI ID Invalid | 11/07/06 - ERCOT will review and provide comments back to TX SET at the 12/06 meeting | Pending
2006-10-06 | PUCT has issued a proposal for publication - Project 33025 which among other things proposes to eliminate "Drop to AREP" Process - once the project is approved and adopted by the PUCT TX SET will need to review to determine what needs to be done with the 814_10 Drop to AREP transaction | 11/07/06 TX SET will monitor rulemaking process | Pending

## Closed Action Items
Date Opened | Action Item | Resolution | Status | Date Last Updated
2006-02-28 | TX SET Leadership (Kathy Scott ) will take updated TX SET Procedures Document to RMS for approval. | Approved at RMS on 4/12/06 and will be discussed at TAC in May for their approval | Closed | 2006-04-26
2006-02-28 | SIR 10528 – Backdating Transactions – ERCOT will implement validation to reject any transaction received that backdated prior to 01/01/1999. | This action item has been resolved with the implementation of SIR 10528 by ERCOT on April 22, 2006 | Closed | 2006-04-26
2006-02-28 | Multiple DTM~140s on the 867_04 transaction received from TDSP. Bill Reily will bring an example of when TXU ED has provided multiple meter information in the 867_04 to enable TX SET to fully discuss the appropriate transactional process. | Discussion on 4/25/06 at TX SET identified that issue has been resolved | Closed | 2006-04-26
2006-03-06 | TX Leadership to develop language to specify that the Change Control Form is for use by TX SET after the approval of an Issue | Leadership had discussed with Jennifer Fredrick to update the Change Control Form on the web for TX SET Use only, however that information had not been posted at the time of this meeting - Susan Munson will work with Jennifer to get this updated. | Closed | 2006-06-07
2006-03-06 | Market Participants and ERCOT to go back to their shops and determine what they need to implement changes in their systems. Provide feedback at the April 5th meeting. | Market Participants provided the necessary feedback at the April 5, 2006 meeting concerning Mass Transition changes and implementation schedule | Closed | 2006-04-26
2006-03-06 | Each Market Participant has been asked to evaluate cost estimates of what it would cost to implement Mass Transistion Long Term Transactional Solution. Provide feedback at the April 5th meeting. | Market Participants provided the necessary feedback at the April 5, 2006 meeting concerning Mass Transition changes and implementation schedule | Closed | 2006-04-26
2006-05-06 | Ts Cs - POLR Rule Reference 4.3.4 - Is a new reject code necessary to reject off cycle fee. CRs will evaluate need for new reject code prior to TX SET meeting. | Assigned to Rob Bevill; No reject code needed; handle through dispute process | Closed | 2006-06-07
2006-05-06 | Ts Cs - POLR Rule Reference 4.4.3 - Do we need a reject code when a re-bill comes in greater than 150 days? Note: 5 day reject rule applies. | Assigned to Rob Bevill; No reject code needed; handle through dispute process | Closed | 2006-06-07
2006-02-28 | TX SET membership was assigned to review and propose revision changes to TX SET Implementation Guides to support Mass Transition Project and high level design at March Meeting. | Discussed at March TX SET Meeting - 04/26/06 - This is a work in progress. 6/7/06 - Still pending until change controls and documents are agreed upon. 06/27/06 - Defer closing this item until POLR rule is approved to ensure all changes have been identified and incorporated into Implementation Guides 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-02-28 | TX SET Leadership (Kathy Scott) will develop an RMGRR to incorporate MCT Roles and Responsibilities Document into the Retail Market Guide. | Glen Wingerd and Sonja Mingo do not think this should be a part of the Retail Market Guide. Recommend adding MCT Roles and Responsibilities document to RMS Agenda for discussion with a vote if needed. 07/28/06- Decision by RMS Leadership that this should not be a RMGRR Change only post the Roles and Responsibilites to the Website under MCT reporting to RMS | Closed | 2006-07-28
2006-02-28 | Revise the 867_04 Implementation Guide to remove invalid example. TX SET discussed example 2 of 5 found on page 19 of this Implementation Guide. | Need and issue created to remove the incorrect or correct the examples on this transaction - Johnny Robertson will draft issue 06/27/06 - Change control still needs to be done to correct example 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-02-28 | Revise grey boxes in transactions to clarify that only 5 or 9 digit zip codes are allowed all others would be rejected by ERCOT. | Catherine Meiners drafted issue. Change control must be written 06/27/06 - Catherine Meiners will write change control for implemented change 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-05-06 | Ts Cs - POLR Rule Reference 4.3.7 - will look at the Implementation Guide for potential transaction flow and grey box changes for the 814_PC process. | Assigned to Johnny Robertson. (Gray box change only.) 6/7/06 - This will be part of the change control for Ts Cs 06/27/06 - The 814_PC Implementation Guide has been redline waiting change control conference call on 7/28 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-05-06 | Ts Cs - POLR Rule Reference 4.4.5 - Review the 820 Implementation guide for conformity with the rule. | Assigned to Kathy Scott, Cary Reed, Bill Reily (regarding clarity between 820/810 pairs). 6/7/06 - Cleaned up verbiage in Implementation Guide; this will be part of the change control for Ts Cs 06/27/06 - The 814_PC Implementation Guide has been redline waiting change control conference call on 7/28 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-05-06 | Ts Cs - POLR Rule Reference 4.8.3 - Modify 810_02 existing “05” replacement code to allow for a new provision. | Will look at 867 monthly and final and 810 for "05" replacement code. Assigned to Diana Rehfeldt, Johnny Robertson 06/27/06 Still a work in progress- need redlined changes completed in implementation guide 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-06-06 | Estimated Meter Reads | Diana Rehfeldt, Bill Reily, and Johnny Robertson will create a strawman 867 redline for this. TDSPs need to figure out the codes. 06/27/06 Still a work in progress- need redlined changes completed in implementation guide 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-06-06 | New Codes in the 650s for Denial of Access | Cary Reed, Rob Bevill, Kyle Patrick, and Suzette Sondag to work on these codes. Reason codes for estimated reads will be assigned to Bill Reily, Kathy Scott, and Alan Burke. 06/27/06 - Need to include redlined changes with Change control document to be scheduled for 7/28/06 Change Control Conference Call 07/28/06- Change Control written and approved for 3.0 implmenentation | Closed | 2006-07-28
2006-07-06 | Post Implementation Guides and SEF files to ERCOT.com for Texas SET 3.0 | Susan Munson to send out redlined Guides to volunteer reviewers - 8/8/2006. Reviewers to return corrected redlined Guides by 8/18/2006. TX SET to review complete set of Guides on 8/22 - 8/24/2006. Susan Munson to post Draft Version 3.0 Implementation Guides to ERCOT.com on 9/1/2006. SEF Files to be posted and distributed by 9/15/2006. | Closed | 2006-08-30
2006-08-06 | TDSPs to provide priority codes for inclusion in Version 3.0 Market Requirements document |  | Closed | 2006-09-12
2006-08-06 | ERCOT will investigate communications protocol options for CSV Customer Billing Information file (i.e. Secure FTP vs. FTP with PGP). (RMGRR042) | ERCOT filed comments to RMGRR042 with their recommendations on 10/4/06. To be discussed at 10/5 TDTWG and considered at RMS on 10/11/06. | Closed | 2006-10-26
2006-08-06 | 814_20 Mass Volumes will be addressed by the PRR672 task force | This has been sent back to Texas SET for discussion. Still collaborating. 10/26/2006 - 2- SIRs will be implemented by ERCOT to address short term recommendation | Closed | 2006-10-26
2006-10-06 | Rob Bevill to take Appendices F3, F4 of the Retail Market Guide for ESI ID spreadsheets for Mass Transition and modify based on Market needs. TDSPs to review Appendix F2. | To be discussed at 10/25-26 meetings and RMGRR filed. | Closed | 2006-10-26
2006-10-06 | Susan Munson to work with Cary Reed to write up the 650_01 priority reconnect issue and send out to TX SET listserve - communicate to CRs to review process |  | Closed | 2006-10-26
2006-10-06 | ERCOT to find security response to this question: If ERCOT does adopt Secure FTP for the process of sending Customer Billing Information to CRs during mass transition event, before the CR opens the file, where does the file physically exist? | Relates to the question of liability in the event of 'hacking' | Closed | 2006-10-26
2006-10-06 | CRs to find out if they can handle receiving maximum of 100K 814_20s per day. Can their systems handle? | To be discussed at 10/25-26 meetings and RMGRR filed. 10/26/2006 CRs felt that their system design would be able to manage a large volume received at one time. | Closed | 2006-10-26

## Parking Lot Items
Date Opened | Parking Lot Item | Resolution | Status | Date Last Updated
2006-02-28 | Update RMGRR to make sure there is a way to drop the Customer Information to the TDSP as well as the CR for updates. | Due to issues and POLR rulemaking has not been settled this may not be an issue for TX SET. Can re-open if needed at a later date when all issues have been resolved. | Closed | 2006-04-26
2006-02-28 | (Chuck Moore) Look at RMGRR Long Term language to see if ERCOT will still send a list of pending transactions to the Gaining CRs. This request is for when the current CR is defaulting the new gaining CR receives a spreadsheet that notifies them of pending transactions to see if the gaining CR has an opportunity to gain (Switch) the Retail Customer earlier preventing them from going to POLR. | ERCOT will investigate if this functionality or process can be added to the Mass Transition requirements document. TX SET Leadership will also add this item to the agenda for May 22/23 meetings to discuss what needs to be added and to document the requirement needs for ERCOT. | Closed | 2006-08-24
2006-02-28 | Possibly look at ERCOT dropping a 814_03 for ESI IDs with pending MVIs that are on day 1, 2, or 3. Might need to look at a priority code and/or code to let the TDSP know that this is a MVI and the lights are not on so that they know it will not be processed as a Switch. | Per TX SET discussion the cost of building this logic would be more than the benefit because of the volume that would apply for this situation. | Closed | 2006-04-26
2006-02-28 | (Kyle Patrick) Need a way for CRs to submit a Switch on customers that are with them as the POLR but have requested Non-POLR service. | This issue may be resolved through the adopted POLR Rule and the selection criteria for POLRs that are within the Rule. | Closed | 2006-04-26
2006-02-28 | Work to consolidate implementation materials for Retail Releases. Work to make sure that information provided concerning releases is consistent across all documentation involved in the project and/or release. | TX SET in conjuction with MCT will work to creating this as our goal | Pending | 2006-04-26