## October 5, 2006
TDTWG - ERCOT Instance Log
July 26, 2006 - November 13, 2006
Issue Date | Notification Date | Start Time | End Time | Duration (mins) | Application | Issue Description | Identification Method | Impact | Root Cause | Resolution | Date (to be) Implemented | Notes | TDTWG Meeting Comments
2006-11-11 | 10/30/06, 11/11/06 | 12:00PM | 10:49PM | 649 | Retail | Planned Maintenance Retail Release | n/a | Planned Outage | n/a | n/a | n/a |  | Complete - Green status
2006-11-09 | N/A | 12:34PM | 1:17PM | 43 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP, Temporary fix implemented in October | Complete - Green status
2006-10-26 | 2006-10-26 | 1:23AM | 1:25AM | 2 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP, Temporary fix implemented in October | Complete - Green status
2006-10-18 | 2006-10-18 | 3:21PM | 4:46PM | 85 | Paperfree | Paperfree application lost connectivity to the Paperfree File Sever. | Monitoring | Unplanned Outage | Configuration issue | Already included in another project | 2006-10-18 | During this time ERCOT was receiving transactions into NAESB and holding in Paperfree. | Complete - SCR745 Phase 2 - implementation 11-11-06 - yellow status
2006-10-17 | 2006-10-17 | 10:39AM | 10:57AM | 18 | Paperfree | The NAESB application locked up and required a reboot. All processing suspended. | Monitoring | Unplanned Outage | Application frozen | Already included in another project | 2006-10-17 | System rebooted. | Complete - SCR745 Phase 1 would have handled this issue - Implementation 11-27-06 - yellow status
2006-10-15 | 10/4/06, 10/9/06, 10/13/06 | 8:00AM | 8:00PM | 720 | Retail | Planned Maintenance Outage | n/a | Planned Outage | n/a | n/a | n/a |  | Complete - Green status
2016-10-14 | 2006-10-16 | 10/14 7:40AM | 10/15 7:10AM | 690 | Paperfree | Outbound processing of 814 and 824 transactions suspended | Manual Troubleshooting | Degradation | Process hung | Already included in another project | 2006-10-15 | Process restarted. | Complete - SCR745 Phase 2 - implementation 11-11-06 - yellow status
2006-10-11 | 2006-10-11 | 5:08PM | 6:10PM | 62 | Retail | Critical memory issue on a Retail Database Server | Monitoring | Unplanned Outage | Hardware failure | Already included in another project | 2006-10-11 | Conversion to the IBM P series server will allow for hot swap capabilities for this type of issue. | Complete - Green status
2006-10-10 | 2006-10-10 | n/a | n/a | n/a | MIR Report Explorer | ERCOT was unable to successfully create and post all Siebel Service Order Full Extracts | Market Notification | Report Delay | Disk full on storage device | One time occurrence | 2006-10-10 |  | Complete - Green status
2006-10-09 | 2006-10-09 | n/a | n/a | n/a | MIR Report Explorer | Errors when downloading Settlement Statements and the following extracts: ESIID Service History and Usage, Settlement & Billing, Load, Generation | Market Notification / Monitoring | Settlements and Extracts | Unknown | One time occurrence | n/a |  | Complete - Green status
2006-10-05 | 2006-10-05 14:49 | 12:36AM | 12:42AM | 6 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP, Temporary fix implemented in October | Complete - Green status
2006-10-02 | 2006-10-03 | 7:46PM | 7:56PM | 18 | Paperfree | Paperfree File Server network outage | Monitoring | Unplanned Outage | Hardware failure | Already included in another project | 2006-10-03 | SCR745 | Complete - SCR745 Phase 2 - implementation 11-11-06 - yellow status
2006-09-27 | 2006-09-27 | n/a | n/a | n/a | TIBCO | Delayed 867_03 IDR and NIDR Activity Reports | Monitoring | Report Delay | Data Exception | Already included in another project | 2006-09-28 | Increased Hawk monitoring to capture and correct exception immediately | Complete - Green status
2006-09-26 | 2006-09-29 | 12:02AM | 4:04PM | 242 | Paperfree | 997s not sent during outages | Market Notification / Daily Report | Transaction Loss | TBD | Not already included in another project | n/a | Result of Paperfree outage | Phase 2 of SCR745 - implementation date of 11-11-06 - yellow status
2006-09-25 | 2006-09-29 | 1:58AM | 3:47PM | 829 | Paperfree | 997s not sent during outages | Market Notification / Daily Report | Transaction Loss | TBD | Not already included in another project | n/a | Result of Paperfree outage | Phase 2 of SCR745 - implementation date of 11-11-06 - yellow status
2006-09-26 | 2006-09-26 | 12:02PM | 4:04PM | 242 | Paperfree | Paperfree File Server not responding | Monitoring | Unplanned Outage | TBD | Not already included in another project | 2006-09-26 | ERCOT has engaged IBM and EMC to find root cause and resolution | Code implemented to reduce occurrences - Yellow status/monitoring in progress
2006-09-25 | 2006-09-25 | 1:58AM | 3:47PM | 829 | Paperfree | Paperfree File Server not responding | Market Notification / Monitoring | Unplanned Outage | NIC driver error | Not already included in another project | 2006-09-25 | ERCOT has engaged IBM and EMC to find root cause and resolution | Code implemented to reduce occurrences - Yellow status/monitoring in progress
9/22/06 - 9/26/06 | 9/22/06 - 9/27/06 | n/a | n/a | n/a | Paperfree | 814 and 867 transactions duplicated | Monitoring | Transaction Duplication | TBD | Not already included in another project | n/a | ERCOT has engaged IBM and EMC to find root cause and resolution | Code implemented to reduce occurances - Yellow status/monitoring in progress
2006-09-20 | 2006-09-20 | n/a | n/a | n/a | TML API | Market Participants receiving the “No ESI ID found” message when using the API and to research | Market Notification | Information not available | Code issue | Already included in another project | 2006-09-28 |  | Complete - Green status
2006-09-21 | 2006-09-21 | ~2:00AM | ~4:00AM | 120 | Siebel | Siebel Batch continued following SBMI issue with future dated evaluation date | Market Notification | Order Cancellations | Incorrect date used | One time occurrence | 2006-09-21 | Process change and Training implemented | Complete - Green status
2006-09-21 | 2006-09-21 | 12:55AM | 1:03AM | 8 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
2006-09-19 | 2006-09-19 | n/a | n/a | n/a | Paperfree | Annual Validation backlog of 814_20 Maintains | Market Coordination / Monitoring | Backlog | Annual Validation and system limitations | Annual occurrence | n/a | current backlog is ~300K | Complete for 2006 - Green status - long term fix to be implemented in Feb 07
2006-09-11 | 2006-09-11 | 12:46AM | 12:49AM | 3 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
8/15/06 - 9/8/06 | 2006-09-08 | n/a | n/a | n/a | Siebel | ESIID address deleted from database | Exception Processing | Rejected Transactions | Software Bug | Already included in another project | n/a | Implementation date to be determined | In progress - yellow status - fix to be in place Feb 07
2006-09-05 | 2006-09-05 | n/a | n/a | n/a | TIBCO | Posting delay for extracts and reports | Market Notification / Monitoring | Report Delay | Component Nonresponsive | Already included in another project | 2006-09-06 | Redifined Hawk monitoring agent rules | Complete - Architecture change in place - Green Status
2006-08-30 | 2006-08-31 | 9:17PM | 9:28PM | 11 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
2006-08-24 | 2006-08-24 | n/a | n/a | n/a | TIBCO | Posting delay for extracts and reports | Market Notification / Monitoring | Report Delay | Component Nonresponsive | Already included in another project | 2006-08-24 | Implementation of Hawk monitoring agent | Complete - Architecture change in place - Green Status
2006-08-08 | 2006-08-08 | n/a | n/a | n/a | TIBCO | Delayed TDSP ESIID Report | Monitoring | Report Delay | Code issue with implementation | Already included in another project | TBD |  | Complete - Architecture change in place - Green Status
2006-08-02 | 2006-08-02 | 1:10AM | 1:13AM | 3 | Siebel | SBMI, SBMO, SBSW transaction duplication | Monitoring | Transaction ID Duplication | TBD | Already included in another project | 2006-12-09 | Fix to be implemented with RBP | Complete - Green status
2006-07-27 | 2006-07-27 | 1:00AM | 9:30AM | 510 | Paperfree | 814 and 867 transactions duplicated | Monitoring | Transaction Duplication | TBD | Not already included in another project | n/a | ERCOT has engaged IBM and EMC to find root cause and resolution | Code implemented to reduce occurrences - Yellow status/monitoring in progress

## Service Availability
Month | Service | Gross Available Minutes | Planned Outage Minutes | Net Available Minutes | Unplanned Outage Minutes | Percent Availability
January | Retail Transaction Processing | 44640 | 1620 | 43020 | 105 | 99.76%
February | Retail Transaction Processing | 40320 | 990 | 39330 | 556 | 98.59%
March | Retail Transaction Processing | 44640 | 960 | 43680 | 0 | 100%
April | Retail Transaction Processing | 43200 | 715 | 42485 | 0 | 100%
May | Retail Transaction Processing | 44640 | 3255 | 41385 | 402 | 99.03%
June | Retail Transaction Processing | 43200 | 0 | 43200 | 0 | 100%
July | Retail Transaction Processing | 44640 | 390 | 44250 | 304 | 99.31%
August | Retail Transaction Processing | 44640 | 885 | 43755 | 0 | 100%
September | Retail Transaction Processing | 43200 | 0 | 43200 | 1071 | 97.52%
October | Retail Transaction Processing | 44640 | 720 | 43920 | 183 | 99.58%
Year to Date | Retail Transaction Processing | 437760 | 9535 | 428225 | 2621 | 99.39%
(to Oct 31)