Texas Nodal

DRAFT EDS Market Trials Approach

Version 0.6

November 21, 2006

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 10/10/06 | 0.1 | Initial Draft. | John Hall |
| 10/30/06 | 0.2 | Revise document title to Market Trials Approach. Refine document scope to include approach and transfer detailed testing data to the Market Trials Detailed Plan | John Hall |
| 11/13/06 | 0.3 | Refined SCADA schematic and added overall market trials approach. | John Hall |
| 11/15/06 | 0.4 | Restructured and updated the document based on a document review walkthrough. | John Hall, Ken Kasparian |
| 11/20/06 | 0.5 | Comments from Jeyant Tamby and Raj Chudgar added. | John Hall, Ken Kasparian |
| 11/21/06 | 0.6 | Updates based on feedback from Steve G and improved alignment with the Nodal Transition Plan. | Ken Kasparian |

Document Sign-off

| Package | Name | Signature | Date |
| --- | --- | --- | --- |
| Document Author | John Hall |  |  |
| ERCOT Integrated Readiness & Transition | Steve Grendel |  |  |
| Integration & Design Authority | Jeyant Tamby |  |  |
| EMS / MMS | Al Hirsch |  |  |
| Commercial Systems | Raj Chudgar |  |  |
| NMMS | Raj Chudgar |  |  |
| MIS | Pat Harris |  |  |
| MER | Trip Doggett |  |  |
| EDW | Sylvia Shiroyama |  |  |
| EIP | Daryl Shing |  |  |
| Infrastructure | David Forfia |  |  |
| ITP | Glen Wingerd |  |  |
| CRR | Shawna Jirasek |  |  |
| Director, Systems Operation | Kent Saathoff |  |  |
| Director, Commercial Operations | Betty Day |  |  |
| Director, Market Services | Richard Gruber |  |  |

Table of Contents

1	Executive Summary	6

2	Market Trials Overview	8

2.1	Market Trials Requirements	8

2.2	Market Trials Phases	9

2.3	Testing Cycles and Market Participant Segmentation	9

2.4	Market Trials Testing Week	9

2.5	Market Trials Reporting	9

2.6	Market Trials Data	10

2.7	Market Trials Sandbox	10

2.8	Market Trials Documentation	10

2.9	Market Trials Planning Next Steps	10

3	EDS 1 – Data and Telemetry Market Trials	11

3.1	Objectives	11

3.2	System Functionality	12

3.3	Entrance Criteria	13

3.4	Exit Criteria	13

4	EDS 2 – State Estimator, Real-time Security Analysis Market Trials	14

4.1	Objectives	14

4.2	System Functionality	15

4.3	Entrance Criteria	15

4.4	Exit Criteria	15

5	EDS 3 – Real Time Market Trials	16

5.1	Objectives	16

5.2	System Functionality	16

5.3	Entrance Criteria	17

5.4	Exit Criteria	17

6	EDS 4 – Day-Ahead Market Trials	18

6.1	Objectives	18

6.2	System Functionality	19

6.3	Entrance Criteria	19

6.4	Exit Criteria	20

7	Summary	20

8	Appendices	21

8.1	Texas Nodal High-level Inputs & Outputs	21

8.2	Texas Nodal High-level Schedule	22

8.3	Market Trials High-level Timeline	23

8.4	Detailed Market Trials Plan (Illustrative Example)	24

# Executive Summary

The objective of market trials is to confirm through a series of structure and unstructured tests that “stable and accurate operations of the SCADA, Network Security Analysis, Transmission Constraint Management, SCED, LFC, DAM, RUC, and real time settlement system can be declared” as outlined in the Nodal Transition Plan.

Nodal Program Work streams (packages) have been tasked with providing this functionality with the following documents defining the necessary detail. All design documentation and plans will be guided by these documents.

- Texas Nodal Protocols revised with all approved Nodal Protocol Revision Requests (NPRRs) approved by Nodal Program Change Control.

- ERCOT Nodal Transition Plan

The market trials plan has been compiled based on the Nodal Timeline, as shown in Figure 1 below. For ease of reference, each phase of the market trials is defined in the following categories:

- Objectives

- System functionality

- Entry criteria

Each phase of the market trials honors the ERCOT Nodal Transition Plan, except where noted, with appropriate references to the Nodal Protocols and also defines the SoSA operations (processes) to be tested in each phase.

This approach document defines the framework against which the Market Trials Detailed Plan will describe the phases in sufficient detail to execute the trials.

Many exhibits in the approach are sample formats which will be expanded in the detailed plan.

The following diagram illustrates the four phases of market trials. Following the illustration is more detail about each phase.

Figure 1 - Market Trials Plans align with the Nodal timeline

# Market Trials Overview

This document provides a high level market trials approach. This approach will guide detailed planning of the Early Delivery System phases (EDS) for the Texas Nodal project and outlines the key objectives, functionality, and beginning entrance criteria for each phase of the market trials. The approach aligns with the Nodal schedule agreed by TPTF in September 2006. In this document, “Paragraph #” references refer to the ERCOT Nodal Transition Plan.

Note that these areas provide an overview of the approach and will be further detailed over time in the EDS Market Trials Detailed Test Plan and Market Trials Handbook.

## Market Trials Requirements

The ERCOT Nodal Transition Plan, Reference Protocols (October 2006) and SoSA procedures will be used as guiding documents for market trials planning. These requirements will be tied to specific criteria and EDS phase tasks to ensure a traceable and comprehensive process. The detailed market trials planning documentation will document the specific requirements and traceability matrices. This table is an example of the plan.

| EDS | Description | Transition Plan Requirement | Operations / SoSA | Market Trials tasks | MP Interventions | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Telemetry & ICCP Validation | 5.4.1(2) ERCOT shall develop procedures for setup and data implementation requirements applicable to TSP’s and QSE’s. ERCOT shall with the assistance of TSP’s and QSE’s: (a) Verify that all data and telemetry requirements Specified in the nodal Protocols Section 3.10, Network Operations Modeling and Telemetry, Have been met and that all Data submittals are complete and represent an accurate model of the ERCOT System; | EDS 1 - Assumption: only testing data coming in FROM the field ICCP-related operations I can think of: - S.UC1.OP1: Update Frequency (EMS operation) - S.UC1.OP3: Update Generation Levels (EMS Operation) - S.UC1.OP5: Update Responsiveness Information (EMS Operation) | All telemetry (SCADA/ICCP) points checked out (programmatically or manually). Status Report at the end of this activity must indicate that all points have been tested and verified Require Professional Engineers Seal from Entities to assure accuracy of data. Can be required from QSE’s/TSP’s due to issues of public safety and public interest Alarm Functionality Validated | 12-31-06 – Preliminary MP Interface Specs 3-30-07 – Final Interface Specs | This is a joint ERCOT and Market Participant task. Will require a EDS type functionality from TSP/QSE QSE/TSP personnel can SIMULATE analog/digital changes on their EDS and ERCOT EDS will be able to accomplish point-to-point check out with ERCOT operators Explore programmatic way to validate – this approach can be used later for periodic verification. |
| 2 | Network model validation |  |  |  |  |  |
| 3 | Real-time Operations |  |  |  |  |  |
| 4 | Day ahead Operations |  |  |  |  |  |

## Market Trials Phases

The Market Trials will be implemented in four different phases with each phase testing critical functionality and progressively increasing in scope and complexity. The phases and high level focus areas are:

- EDS 1 – Data and Telemetry

- EDS 2 – State Estimator, Real Time Security Analysis

- EDS 3 – Real Time Market Operations

- EDS 4 – Day Ahead Market Operations

Based on a comprehensive release schedule, each successive EDS phase will provide additional operational capabilities to be tested, building up to the complete set of Texas Nodal systems and functionality.

## Testing Cycles and Market Participant Segmentation

To help optimize the trials schedule and reduce resource constraints for both Market Participants and ERCOT, each of the EDS phases will be further broken down into test cycles. The cycles will be targeted to meet specific objectives that support the overall EDS phase.

Market Participant involvement may be segmented into different cycles to allow the team to focus on certain areas and benefit from both a smaller testing pool and common characteristics of the segments. Some example segments could be:

| - Size | - Entity type/classification |
| --- | --- |
| - Type of EMS/GMS | - Readiness to connect with ERCOT |

Each segment will be defined and communicated with each Market Participant and a list will be included in the Market Trials detailed plan.

## Market Trials Testing Week

To provide strong communication and focus on testing activities, the Market Trials schedule will revolve around a standard weekly testing schedule. During any Trials week specific activities and communication points will be defined. This will include a minimum of two conference calls with participants to start off and closeout the week. Testing cycles will be defined that may include multiple cycles during a given week or a single cycle for the week cycle based functionality and complexity. Activities within the trials will be documented within the Market Trials Handbook and posted externally to avoid surprises and to ensure maximum value to both Market Participants and ERCOT.

## Market Trials Reporting

During each of the EDS phases, a defined set of reporting criteria and system outputs will be posted to provide Market Participants with appropriate data. During the Market Trials planning phase, the specific reporting requirements, output data, and periodicity will be detailed in the EDS Market Trials Detailed Test Plan.

## Market Trials Data

The Market Trials will utilize a combination of live ICCP data feeds and production quality simulated data feeds to support trial scenarios. When specific data feeds are not realistic for the specific trial scenarios (i.e. zonal RT telemetry, outages, operating date, operating load, etc.) the data will be simulated. Details of data elements, source and method of simulation will be defined within the Market Trials Detailed Plan.

## Market Trials Sandbox

The market trials sandbox environment will provide a means for Market Participants to test communication with the Nodal ERCOT systems. This environment provides the interfaces for Market Participant testing of data submission prior to the start of EDS. This environment will be available ahead of the EDS implementation and is provided for Market Participant system testing. The details of specific interfaces, functionality, and timelines will be outlined in the EDS Market Trials Detailed Test Plan. Participation in the Sandbox may be required prior to Market Trials.

## Market Trials Documentation

Market trials will be defined and managed using a suite of documents which build in detail on the overall EDS Strategy defined in the ERCOT Nodal Transition Plan. These documents are listed and defined below:

- EDS Market Trials Approach (This document) – Provides a high level market trials approach for each of the EDS phases.

- ERCOT Nodal Transition Plan – TPTF-created definition of the Nodal System components and transition considerations

- EDS Release Strategy – Definition of the EDS phases and release management process, entry and exit criteria for each release.

- EDS Market Trials Detailed Test Plan –Details the test plan for each of the EDS phases defining specific entry and exit criteria, system functionality, test environments, data management plans, staffing, detailed schedules, Market Participant requirements and trial cycles, test scripts and use cases. This is the most detailed document in the suite of EDS documents

- Market Trials Handbook - A document containing a compilation of relevant material from all of the above documents with the focus of providing detailed guidelines for Market Participants during market trials.

## Market Trials Planning Next Steps

The ideas and concepts outlined in this approach document will be further detailed in the EDS Market Trials Detailed Plan. In order to ensure that ERCOT and Market Participant expectations remain in alignment while the implementation details continue to be documented, the team has requested setting up a working group to provide draft versions of the EDS Market Trials Detailed Test Plan sections for comment prior to completing a final draft for signoff. The target milestones for completion are outlined below, interim drafts will be sent on a periodic basis.

- EDS 1 to 4 Detailed Plan – Drafts for comment		To be defined

- EDS 1 Detailed Plan – Final Signoff			To be defined

- EDS 2 Detailed Plan – Final Signoff			To be defined

- EDS 3 Detailed Plan – Final Signoff			March 30, 2007

- EDS 3 Market Trials Handbook – Final Signoff		June 29, 2007

- EDS 4 Detailed Plan – Final Signoff			September 28, 2007

- EDS 4 Market Trials Handbook – Final Signoff		December 31, 2007

# EDS 1 – Data and Telemetry Market Trials

## Objectives

The Data and Telemetry Market Trials phase will verify the following:

- data and telemetry requirements and data submittals are complete and represent an accurate model of the ERCOT System

- accuracy of all constraints on transmission elements

- TSP calculations on likely binding transmission constraints in the SCED

- redundant telemetry communications paths between ERCOT and QSE’s/TSP’s

- all telemetry meets update performance requirements and recovery capabilities

- alarm processors operate properly per requirements

- outage detection functionality (including scheduled vs. forced outages)

- real-time weather information acquisition requirements

- the ability to process stale telemetry at ERCOT, QSE’s and TSP’s

## System Functionality

The following Texas Nodal systems and capabilities listed below will be utilized for the EDS 1 phase of Market Trials.

- Nodal Energy Management System (SCADA)

- ICCP Links

The table and the SCADA schematic below indicate testing points and data validation required by professional engineers’ seal.

| Segment | Certification Requirement | Notes |
| --- | --- | --- |
| A to H | To be certified by MPs by PE Seal | See NP Section 8 |
| H to I | To be certified by TBD (3rd Party ?) | See NP Section 8 |
| I to N | To be certified by ERCOT – PE Seal and by System Operators | See NP Section 8 |

Figure 2 - ERCOT SCADA Schematic Data Flow Configuration

EDS 1 key issues:

- NMMS naming convention is different from current model and a mapping table will need to be created

- Provide Real Time data from QSE’s/TSP’s as described in the schematic above.

Market Participants will verify and validate the accuracy of their data and

## Entrance Criteria

To begin the EDS 1 phase of Market Trials, a defined set of entrance criteria must be completed to ensure readiness. Specific criteria will need to be defined for both ERCOT and the Market Participants to help ensure that the test phase will be productive. During the market trials planning phase the team will be working with Market Participants to finalize a set of measurable criteria.

Below are some example areas that will be expanded and documented in the EDS Market Trials Detailed Test Plan and Market Trials Handbook.

| Criteria | Measurement | Pass (Y/N) |
| --- | --- | --- |
| ERCOT CRITERIA |  |  |
| EMS system stability | EMS ITEST complete based on exit criteria |  |
| SCADA interfaces tested |  |  |
| ICCP Link setup |  |  |
| Independent Readiness Critieria - TBD |  |  |
| MP CRITERIA |  |  |
| EDS1 required system development complete |  |  |

## Exit Criteria

Exit criteria for each EDS phase is defined to ensure that the deliverables from each phase are of the required quality and completeness to allow each successive phase, which builds on the previous phase, to proceed as planned.

Exit criteria will be defined together with Market Participants to finalize a set of measurable criteria.

# EDS 2 – State Estimator, Real-time Security Analysis Market Trials

## Objectives

To further validate telemetry by introducing the Nodal Network Model and Network Security Analysis the State Estimator and Real-time Security Analysis Market Trials phase will verify the following:

- State Estimator performance and availability requirements

- State Estimator utilizing live data acquisition processes and calculated data

- Continuous Telemetry of the Status of Breakers and Switches

- Network Security Analysis sequence

- Network Security Analysis results against real-time computations

- Transmission Constraint Management process

## System Functionality

The following Texas Nodal systems and capabilities listed below will be utilized for the EDS 2 phase of Market Trials.

- EDS 1 Components - Nodal Energy Management System (SCADA)

- State Estimator

- Nodal Network Model

- Network Topology Builder

- Topology Consistency Analyzer

- Bus Load Forecast functions

- Network Security Analysis functionality

- Contingency Screening application

## Entrance Criteria

To begin the EDS 2 phase of Market Trials, a defined set of entrance criteria must be completed to ensure readiness. Specific criteria will need to be defined for both ERCOT and the Market Participants to help ensure that the test phase will be productive. During the market trials planning phase the team will be working with Market Participants to finalize a set of measurable criteria.

Below are some example areas that will be expanded and documented in the EDS Market Trials Detailed Test Plan and Market Trials Handbook.

| Criteria | Measurement | Pass (Y/N) |
| --- | --- | --- |
| ERCOT CRITERIA |  |  |
| ICCP data input tested | 100% validation of telemetry data points H to I | (See Figure 2) |
| SCADA interfaces tested |  |  |
| ICCP Link setup |  |  |
| Network Model complete |  |  |
| MP CRITERIA |  |  |
| MP Network Model Transparency Tool (Viewer) & Registration and Qualification |  |  |

## Exit Criteria

Exit criteria for each EDS phase are defined to ensure that the deliverables from each phase are of the required quality and completeness to allow each successive phase, which builds on the previous phase, to proceed as planned.

Exit criteria will be defined together with Market Participants to finalize a set of measurable criteria.

# EDS 3 – Real Time Market Trials

## Objectives

The third phase of market trials will build on EDS 1 & 2 to demonstrate the Real-Time system integration with the EMS components of the system. The phase will verify the following:

- that QSE’s/TSP’s can successfully submit resource offer curves into SCED

- RT SCED functionality and market results

- the reasonableness of the LMPs calculated by SCED

- the RUC functionality and market results

- RT settlement statements including RUC commitments

- Supplemental Ancillary Services Market procedures

- Load Frequency Control functionality

- Area Control Error (ACE) accuracy

## System Functionality

The following Texas Nodal systems and capabilities listed below will be utilized for the EDS 3 phase of Market Trials.

| - NMMS (without Planning model) | - Nodal EMS (live feeds) |
| --- | --- |
| - Outage Scheduler | - SCED |
| - RUC | - SASM |
| - COP | - Emergency Operations |
| - Trades | - 3 Part Offers |
| - Schedules | - CMM |
| - MIS (RT components) | - Commercial operations (RT components) |
| - EDW (RT components) | - Integration (RT components) |
| - 8*5 Market Trials support in place | - LMPs calculated and deemed reasonable by ERCOT |

## Entrance Criteria

To begin the EDS 3 phase of Market Trials, a defined set of entrance criteria must be defined to ensure readiness. Specific criteria will need to be defined for both ERCOT and the Market Participants to help ensure that the test phase will be productive. During the market trials planning phase, the team will be working with Market Participants to finalize a set of measurable criteria.

Below are some example areas that will be expanded and documented in the EDS Market Trials Detailed Test Plan and Market Trials Handbook.

| Criteria | Measurement | Pass (Y/N) |
| --- | --- | --- |
| ERCOT CRITERIA |  |  |
| MMS system stability | MMS ITEST complete based on exit criteria |  |
| Commercial operations system stability | COMS ITEST complete based on exit criteria |  |
| MIS system stability | MIS ITEST complete based on exit criteria |  |
| EMS system stability | EDS 1, 2 complete based on exit criteria |  |
| - MP CRITERIA |  |  |
| - MP specific EDS 3 development completed |  |  |
| MP EDS 3 interfaces completed per ERCOT published requirements |  |  |
| Sandbox connectivity tested |  |  |
| MP ability to generate and submit offers via API or MIS Portal |  |  |
| Have signed up for a SCED cycle [Methodology to follow] |  |  |
| Registration | EDS 3 specific Asset Registration complete |  |

## Exit Criteria

Exit criteria for each EDS phase are defined to ensure that the deliverables from each phase are of the required quality and completeness to allow each successive phase, which builds on the previous phase, to proceed as planned.

Exit criteria will be defined together with Market Participants to finalize a set of measurable criteria.

# EDS 4 – Day-Ahead Market Trials

## Objectives

The fourth phase of market trials will continue to build on EDS 1, 2, and 3 to demonstrate the Day-Ahead market system integration with the overall Nodal systems. This phase will verify the following:

- that QSE’s/TSP’s can successfully create and submit DAM offers

- the operation of DAM to procure Ancillary Services

- DAM settlement statements using LMPs and MCPCs

- all Real Time components integrate with Day Ahead

- the overall system stability through a 168 hour test

- Settlement Statements for each operating day of the 168 hour test

## System Functionality

The following Texas Nodal systems and capabilities listed below will be utilized for the EDS 4 phase of Market Trials.

| - NMMS (full) | - Nodal EMS (live feeds) |
| --- | --- |
| - DAM (full) | - SCED (full) |
| - RUC | - COP |
| - CRR (full) | - SASM (full) |
| - Credit Monitoring & Management (full) | - Emergency Operations |
| - MIS (full) | - 3 Part Offers |
| - Trades | - Schedules |
| - Full back-end (x4) | - EDS (full) |
| - 8*5 support (24*7 for MP SAT) | - Commercial operations (full) |
| - Integration (full) |  |

## Entrance Criteria

To begin the EDS 4 phase of Market Trials, a defined set of entrance criteria must be defined to ensure readiness. Specific criteria will need to be defined for both ERCOT and the Market Participants to help ensure that the test phase will be productive. During the market trials planning phase, the team will be working with Market Participants to finalize a set of measurable criteria.

Below are some example areas that will be expanded and documented in the EDS Market Trials Detailed Test Plan and Market Trials Handbook.

| Criteria | Measurement | Pass (Y/N) |
| --- | --- | --- |
| ERCOT CRITERIA |  |  |
| NMMS Planning Model completed ITEST | Exit criteria to be defined |  |
| DAM system completed ITEST | Exit criteria to be defined |  |
| CRR DAM components completed ITEST | Exit criteria to be defined |  |
| CMM DAM components completed ITEST | Exit criteria to be defined |  |
| - MP CRITERIA |  |  |
| - MP specific EDS 4 development completed |  |  |
| MP EDS 4 interfaces completed per ERCOT published requirements |  |  |
| Connection to Sandbox, MP Network Model Transparency Tool (Viewer) & Registration and Qualification |  |  |
| MP ability to generate and submit DAM offers via API or MIS Portal |  |  |

## Exit Criteria

Exit criteria for each EDS phase are defined to ensure that the deliverables from each phase are of the required quality and completeness to allow each successive phase, which builds on the previous phase, to proceed as planned.

Exit criteria will be defined together with Market Participants to finalize a set of measurable criteria.

# Summary

The Market Trials Approach defines how the market trials detailed plans will be developed by ERCOT together with the market Participants. This purposely ensures the definition of future TPTF checkpoints for reporting back on the products which will drive effective market trials. The overarching intent is that all products and any detailed plans will be developed by ERCOT with the market participants.

# Appendices

## Texas Nodal High-level Inputs & Outputs

## Texas Nodal High-level Schedule

See Appendix 7.3 for detail

## Market Trials High-level Timeline

## Detailed Market Trials Plan (Illustrative Example)

| EDS | Description | Transition Plan Requirement | Operations / SoSA | Market Trials tasks | MP Interventions | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Telemetry & ICCP Validation | 5.4.1(2) ERCOT shall develop procedures for setup and data implementation requirements applicable to TSP’s and QSE’s. ERCOT shall with the assistance of TSP’s and QSE’s: (a) Verify that all data and telemetry requirements Specified in the nodal Protocols Section 3.10, Network Operations Modeling and Telemetry, Have been met and that all Data submittals are complete and represent an accurate model of the ERCOT System; | EDS 1 - Assumption: only testing data coming in FROM the field ICCP-related operations I can think of: - S.UC1.OP1: Update Frequency (EMS operation) - S.UC1.OP3: Update Generation Levels (EMS Operation) - S.UC1.OP5: Update Responsiveness Information (EMS Operation) - S.UC1.OP6: Update QSE Provider Information (EMS Operation) - S.UC1.OP7: Use Revised Data (EMS Operation) - S.UC1.OP8: Use Telemetry Data (EMS Operation) - S.UC2.OP1: Update RT Generation/Transmission Data (EMS Operation) - S.UC2.OP2: Update Transmission Ratings (EMS Operation) ICCP information TO the field (external): - S.UC2.OP4: Send Base Points - M.UC12.OP1: Clear RT Market (I know Base Points are communicated to QSE’s via ICCP, will need to check which other ones do) | - All telemetry (SCADA/ICCP) points checked out (programmatically or manually) 100 % - Status Report at the end of this activity must indicate that 100 % of all points have been tested and verified - Require Professional Engineers Seal from Entities to assure accuracy of data. Can be required from QSE’s/TSP’s due to issues of public safety and public interest - Alarm Functionality Revalidated - SCADA/ICCP enhancement to detect Forced Outage of equipment - Real Time Weather Telemetry revalidated - Dynamic Rating telemetry - Validate all Transmission Element Limits and Constraints - Check TSP’s calculation Transmission Element Ratings that are likely to be active in SCED - Telemetry Criteria Developed (protocol 3.10.7.4) - Define and implement business processes to repair errors. | - 12-31-06 – Preliminary MP Interface Specs - 3-30-07 – Final Interface Specs | - This is a joint ERCOT and Market Participant task. - Will require a EDS type functionality from TSP/QSE - QSE/TSP personnel can SIMULATE analog/digital changes on their EDS and ERCOT EDS will be able to accomplish point-to-point check out with ERCOT operators - Explore programmatic way to validate – this approach can be used later for periodic verification. |
| 2 | Network Model Validation SE Solution |  |  |  |  |  |
| 3 | Real-time Operations |  |  |  |  |  |
| 4 | Day ahead Operations |  |  |  |  |  |