| Texas Nodal Market Implementation Program - Overview |  |  |  |
| --- | --- | --- | --- |
| Project Manager | Tim Pare (interim) | Reporting Period | Status at 11/27/06 |

Confidence in delivery – RAG Status

| Dimension | This week | Trend | Commentary |
| --- | --- | --- | --- |
| Scope/baseline |  |  | Assessing impact of NPRRs on May protocol baseline |
| Resources |  |  | Program Executive Director selected In negotiations with preferred Integration Project Manager |
| Costs |  | = | Seeking budget baseline BOD approval. First re-forecast scheduled for December |
| Timescales |  | = | Seeking PMs’ commitments to 12/31 commitments to CSD & initial Interface spec submission |
| Critical dependencies |  | = | Confirming vendors’ delivery schedules to permit adequate integration, testing and EDS trials per program schedule |
| Vendors |  | = | Satisfactory completion & approval of vendor development contracts |
| Stakeholders |  | = | Accepted CSD 12/31 delivery “challenge” from TPTF |

Issues for escalation

- EMS Requirements to be presented to TPTF 12/5

- Requirements for, and impact of, January fee filing on project teams

- Lack of available business resources to identify requirements for Protocol 8: Compliance and EMS/MMS project areas.

Key achievements and expectations

| Project | Achievements this Period | Outlook for next period |
| --- | --- | --- |
| PMO | - New Executive Director selected, expected start date mid-December - Nodal budget baselined. | - Initiate regular cost reporting following BOD budget baseline - 2nd IBM program Control audit scheduled for December |
| IDA | - powERUP site published for internal review. - Domain model published - Interface specification draft published | - Release Market Participant Identity Management Guide. - Review functional and supplementary requirements for – EMS Dynamics Ratings, EMS System, LFC, Outage Evaluation, Outage Scheduler, State Estimator, Contingency Analysis, Voltage Scheduler and SCADA. |
| NMMS | - Successfully conducted Nodal Modeling Forum - NMMS – detailed use cases 90% complete & integration model template 50% complete - NMT – 603 issues closed (overall 26% complete of 4,252 identified data issues) | - NMMS – Generate NMMS interface document and review & distribute data dictionary - NMT – Prepare presentation on Private Networks and consolidate market participants justification into their master critical measurements list. |
| EMS | - Required Zonal “customs” requirements evaluation complete | - Finish EMS Requirements preparation for TPTF submission 12/5 |
| MMS | - Excellent feedback received from TPTF on MMS Requirements Documentation. | - Integrate MMS comments from TPTF - Continue CSD & Activity Map work |
| CRR | - BA on-boarded - TPTF CSD comments received and incorporated - Updated detailed design documents | - Send Detailed Design documents to stakeholders for review - Update actuals - Conduct further discussions with other ISOs about team organization |
| COMS | - Joint COMS/Testing kickoff for elaboration phase - Necessary re-execution of prototype and functional tests completed. - Database modifications (necessitating tests) have increased processing time by approximately 50% for most processes. - NPRR impact analysis completed | - Finalize guidelines and help tips for COMS. - ITEST PERL migration - TIBCO installation, testing, and training. |
| MER & MIS | - MIS - Conceptual Design delivered to IDA for review - MIS Vendor - Phase 2 SOW completed and reviewed with Purchasing & Project Stakeholder group - Training classes for rest of year and into 2007 are posted on the web and available for registration | - Review protocol changes to assess any MIS impacts - Continue developing QSE Basic Training, LSE 201, NMMS and Transition to Nodal Markets and Start-up courses |
| EDW | - EDW usage criteria approved by IDA | - Conduct requirements gathering sessions with project teams |
| Infrastructure | - Power Recovery – Austin Storage Migration: All 120 servers migrated - Stand up services complete for ABB MMS/OS Remote Development Environment | - Complete SOW for IBM Long Term Lab & Oracle Services, Monitoring & Reporting Analysis, and IBM Professional Services extension (PM/EA) |
| Integration | - POC Environment Final Test Report with Hawk Rules completed - Common Services Final Test Report completed | - Develop repeatable process to load and delete data required for demo) - Finalize development of utility to load and extract test data - Carry out End to End Test - Conduct Proof of Concept demo |
| Integration Testing | - Joint COMS/Testing kickoff for elaboration phase - Established test team for NMMS | - Start test cases for COMS, CRR and NMMS - Test Learning Management System (LMS) |
| ERCOT Readiness & Transition | - Completed input to Registration Requirements - Organization Design workshop conducted with IRT Team - Communication and Awareness Approach conducted with IRT Team - System Development Awareness Workshop conducted with IRT Team | - Complete internal review of Market Trials Approach and send to TPTF - Distribute QSE Qualification Approach for internal review - Continue work on MISO Readiness Criteria and Process Case Study |

Key Milestone Status

| Control Milestone | Baseline | Actual/F’cast | Comment |
| --- | --- | --- | --- |
| Requirements approval | 10/31/2006 | 1/24/2007 | Slippage to key reqts (EMS, MMS & EDW) & holidays impacting on TPTF schedule |
| Key CSD submission | 12/31/2006 | 12/31/2006 | There will be a few non-critical exceptions |
| Key CSD approval | 2/28/2007 | 2/28/2007 | Depends on 12/31 achievement |
| Vendor SOW BOD approval | 12/10/2006 | 12/10/2006 | All required packets scheduled for BOD |
| Interface specs – draft | 12/31/2006 | 12/31/2006 |  |
| Interface specs – final | 3/31/2007 | 3/31/2007 |  |

Top 3 Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Failure to deliver ERCOT/MP interface specs impacts MPs’ system developments | M | H | - Assigned to Integration project as #1 priority |
| Failure to deliver CSDs by 12/31 undermines MP confidence in ERCOT’s ability to recover time lost in Requirements | M | M | - Projects focused on delivering CSDs by 12/31 as a priority after Requirements. Seeking commitments to this date |
| EDS trials disrupted by inability of upstream projects to deliver product in time to enable proper integration testing sequence | H | H | - Upstream PMs confirming vendors’ ability to achieve required delivery schedule. - Developing integration sequence & revised critical path |