| Texas Nodal Market Implementation Program - Overview |
| --- |
| Project Manager | Tim Pare (interim) | Reporting Period | Status at 11/27/06 |

Confidence in delivery – RAG Status

| Dimension | Status | Trend | Commentary |
| --- | --- | --- | --- |
| Scope/baseline |  | = | Assessing impact of NPRRs on May protocol baseline |
| Resources |  | ( | Program Executive Director selected In negotiations with preferred Integration Project Manager |
| Costs |  | = | Budget baselined. First cost report scheduled for December |
| Timescales |  | = | Seeking PMs’ commitments to 12/31 delivery of CSD & initial Interface specs |
| Critical dependencies |  | = | Confirming vendors’ delivery schedules to permit adequate integration, testing and EDS trials per program schedule |
| Vendors |  | = | Driving to timely approval and completion of vendor development contracts |
| Stakeholders |  | = | Accepted CSD 12/31 delivery “challenge” from TPTF |

( - Worse, ( - Better, =  - Same

Issues for escalation

- EMS Requirements to be presented to TPTF 12/5

- Requirements for, and impact of, January fee filing on project teams

- Lack of available business resources to identify requirements for Protocol 8: Compliance and EMS/MMS project areas.

Key achievements and expectations

| Project | Achievements this Period | Outlook for next period |
| --- | --- | --- |
| PMO | New Executive Director selected, expected start date mid-December Nodal budget baselined. | Initiate regular cost reporting following BOD budget baseline 2nd IBM program Control audit scheduled for December |
| IDA | powERUP site published for internal review. Domain model published Interface specification draft published | Release Market Participant Identity Management Guide. Review functional and supplementary requirements for – EMS Dynamics Ratings, EMS System, LFC, Outage Evaluation, Outage Scheduler, State Estimator, Contingency Analysis, Voltage Scheduler and SCADA. |
| NMMS | Successfully conducted Nodal Modeling Forum NMMS – detailed use cases 90% complete & integration model template 50% complete NMT – 603 issues closed (overall 26% complete of 4,252 identified data issues) | NMMS – Generate NMMS interface document and review & distribute data dictionary NMT – Prepare presentation on Private Networks and consolidate market participants justification into their master critical measurements list. |
| EMS | Required Zonal “customs” requirements evaluation complete | Finish EMS Requirements preparation for TPTF submission 12/5 |
| MMS | Excellent feedback received from TPTF on MMS Requirements Documentation. | Integrate MMS comments from TPTF Continue CSD & Activity Map work |
| CRR | BA on-boarded TPTF CSD comments received and incorporated Updated detailed design documents | Send Detailed Design documents to stakeholders for review Update actuals Conduct further discussions with other ISOs about team organization |
| COMS | Joint COMS/Testing kickoff for elaboration phase Necessary re-execution of prototype and functional tests completed. Database modifications (necessitating tests) have increased processing time by approximately 50% for most processes. NPRR impact analysis completed | Finalize guidelines and help tips for COMS. ITEST PERL migration TIBCO installation, testing, and training. |
| MER & MIS | MIS - Conceptual Design delivered to IDA for review MIS Vendor - Phase 2 SOW completed and reviewed with Purchasing & Project Stakeholder group Training classes for rest of year and into 2007 are posted on the web and available for registration | Review protocol changes to assess any MIS impacts Continue developing QSE Basic Training, LSE 201, NMMS and Transition to Nodal Markets and Start-up courses |
| EDW | EDW usage criteria approved by IDA | Conduct requirements gathering sessions with project teams |
| Infrastructure | Power Recovery – Austin Storage Migration: All 120 servers migrated Stand up services complete for ABB MMS/OS Remote Development Environment | Complete SOW for IBM Long Term Lab & Oracle Services, Monitoring & Reporting Analysis, and IBM Professional Services extension (PM/EA) |
| Integration | POC Environment Final Test Report with Hawk Rules completed Common Services Final Test Report completed | Develop repeatable process to load and delete data required for demo) Finalize development of utility to load and extract test data Carry out End to End Test Conduct Proof of Concept demo |
| Integration Testing | Joint COMS/Testing kickoff for elaboration phase Established test team for NMMS | Start test cases for COMS, CRR and NMMS Test Learning Management System (LMS) |
| ERCOT Readiness & Transition | Completed input to Registration Requirements Organization Design workshop conducted with IRT Team Communication and Awareness Approach conducted with IRT Team System Development Awareness Workshop conducted with IRT Team | Complete internal review of Market Trials Approach and send to TPTF Distribute QSE Qualification Approach for internal review Continue work on MISO Readiness Criteria and Process Case Study |

Key Milestone Status

| Control Milestone | Baseline | Actual/F’cast | Comment |
| --- | --- | --- | --- |
| Requirements approval | 10/31/2006 | 1/24/2007 | Slippage to key reqts (EMS, MMS & EDW) & holidays impacting on TPTF schedule |
| Key CSD submission | 12/31/2006 | 12/31/2006 | There will be a few non-critical exceptions |
| Key CSD approval | 2/28/2007 | 2/28/2007 | Depends on 12/31 achievement |
| Vendor SOW BOD approval | 12/10/2006 | 12/10/2006 | All required packets scheduled for BOD |
| Interface specs – draft | 12/31/2006 | 12/31/2006 |  |
| Interface specs – final | 3/31/2007 | 3/31/2007 |  |

Top 3 Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Failure to deliver ERCOT/MP interface specs impacts MPs’ system developments | M | H | Assigned to Integration project as #1 priority |
| Failure to deliver CSDs by 12/31 undermines MP confidence in ERCOT’s ability to recover time lost in Requirements | M | M | Projects focused on delivering CSDs by 12/31 as a priority after Requirements. Seeking commitments to this date |
| EDS trials disrupted by inability of upstream projects to deliver product in time to enable proper integration testing sequence | H | H | Upstream PMs confirming vendors’ ability to achieve required delivery schedule. Developing integration sequence & revised critical path |