## Slide 1: Texas Nodal Network Modeling and Telemetry TAC Meeting By Raj Chudgar, ERCOT Friday, 12/01/2006

## Slide 2: NMT – Network Operations Modeling & Telemetry - Project
Agenda
  Network Model Data Issues
    Overview
    Automated Data Query Results by Market Participant
    Process
    Summary of issues to date
    Progress by Market Participant to date
  Critical Measurements Update
    Overview
    Counts by Market Participant
    Critical Measurement Definitions
  Summary
  ERCOT TDSP Road Show Update

## Slide 3: NMT – Network Operations Modeling & Telemetry - Project
  Network Model Data Issues

## Slide 4: NMT – Network Operations Modeling & Telemetry - Project
Determining Model Data Issues Process
  Developed a series of queries looking for plausibility issues concerning:
    Modeling Issues
    ICCP Mapping Issues
  Queries run every 2 weeks after each Genesys EMS database load
  Queries generate issues which are loaded into an Access database
  Issues are assigned to NMT project team members to investigate and resolve internally within ERCOT as a first step
    Procedures have been documented on how to investigate and resolve issues
  Remaining unsolved issues are discussed with individual Market Participants to resolve

## Slide 5: NMT – Network Operations Modeling & Telemetry - Project
Model Data Issue Process

## Slide 6: NMT – Network Operations Modeling & Telemetry - Project
Model Data Issues Query Result Set – as of 11/17/2006

## Slide 7: NMT – Network Operations Modeling & Telemetry - Project
Model Data Issues Progress by MP – as of 11/17/2006
Note 1: Blank TDSP indicates ones that ERCOT has not contacted to date
Note 2: NMT inherited ~400 legacy model issues

## Slide 8: NMT – Network Operations Modeling & Telemetry - Project
  Critical Measurements Telemetry Analysis

## Slide 9: NMT – Network Operations Modeling & Telemetry - Project
Critical Measurements Update
  Identify possible new Telemetry as required by Nodal Protocols and Criteria
    Input based on ERCOT snapshots – normal & peak loads
    Processed using GEN-SE tool by Nexant
    NMT provided spreadsheets to each MP
    MPs must provide new telemetry (schedule) or justifications, (e.g. why not needed) for each point
  NMT is working with each MP when there are questions
  MPs submit Service Requests when issues are identified
  Next Steps (on-going)
    NMT / Nexant will rerun analysis after Service Requests are implemented
    NMT will provide results back to MPs
    NMT will have final schedules for new telemetry or documented justifications

## Slide 10: NMT – Network Operations Modeling & Telemetry - Project
Critical Measurement Counts by MP

## Slide 11: NMT – Network Operations Modeling & Telemetry - Project
Critical Measurement Definitions
  Critical Measurements
    Measurements pairs (Mw and Mvar) whose loss will result in unobservability of one or more buses are called critical measurements. SE will not be able to detect errors in critical measurements due to lack of redundancy and hence errors in critical measurements will significantly affect the SE solution and hence the security assessment.
  Unobservable Buses
    Buses lacking sufficient measurements around them to make them observable are called unobservable buses. SE runs in this area of network using distributed load schedules. So the solution around these buses (Thermal and voltage violations) is not fully reliable.
  Weakly Observable Buses
    A weakly observable bus does not have any injection measurements or measurements on connected branches. It is observable due to injections at adjacent buses. As the name implies, these buses are weakly observable.

## Slide 12: NMT – Network Operations Modeling & Telemetry - Project
Summary
  Major Model clean-up underway
    Target to complete by 3/31/2007
  Major Telemetry effort underway
    Target to have all justifications and schedules for new implementations by 3/31/2007
    Implementation schedule will be published end of 1Q2007
  ERCOT will continue to provide progress reports to TPTF, TAC, and ROS on a regular basis

## Slide 13: ERCOT / TDSP Road Show
  Progress Update

## Slide 14: ERCOT / TDSP Road Show Update
ERCOT started the Road show in August 2006 to work with TDSPs to “jump start” their Nodal efforts
  TDSPs are critical for EDS 1 and EDS 2 as defined by the Nodal Transition Plan
  TDSPs are on the critical path for Nodal to be successful
ERCOT has met with 7 of the 18 TDSPs
  ERCOT Wholesale Client Services is attempting to schedule time with all remaining TDSPs by 1Q2007
  All remaining have been contacted, and 4 have been scheduled for Dec 2006 or Jan 2007.
  ERCOT presented Nodal information at LCRA “Storm Team” meeting for many smaller TDSPs that are within LCRA jurisdiction

## Slide 15: ERCOT / TDSP Road Show Details
TSP Name | Road Show Status
AEP TEXAS CENTRAL COMPANY | Complete
BRAZOS ELECTRIC POWER CO OP INC (TDSP) | In Planning – Jan 07
BROWNSVILLE PUBLIC UTILITY BOARD (TDSP) | Contacted
BRYAN TEXAS UTILITIES (TDSP) | Contacted
CENTERPOINT ENERGY HOUSTON ELECTRIC LLC (TDSP) | Complete
CITY OF AUSTIN DBA AUSTIN ENERGY (TDSP) | Complete
CITY OF COLLEGE STATION (TDSP) | Contacted
CITY OF GARLAND (TDSP) | Complete
CITY OF SAN ANTONIO CITY PUBLIC SERVICE (TDSP) | Complete
DENTON MUNICIPAL ELECTRIC (TDSP) | Contacted
GEUS (TDSP) | Contacted
LCRA TRANSMISSION SERVICES CORPORATION | Complete
MAGIC VALLEY ELECTRIC CO OP INC (TDSP) | Joint with STEC (Scheduled Dec 6th)
RAYBURN COUNTRY CO OP DBA RAYBURN ELECTRIC (TDSP) | Contacted
SOUTH TEXAS ELECTRIC CO OP INC | Scheduled Dec 6th
TEXAS MUNICIPAL POWER AGENCY | Contacted
TEXAS-NEW MEXICO POWER CO (TDSP) | In Planning
TXU ELECTRIC DELIVERY (TDSP) | Complete