| PRR Number | 672 | PRR Title | Retail Market Timing Necessary for PUCT Project 29637 – Phase 2 & Phase 3 – Implement Results of Collaborative Analysis |
| --- | --- | --- | --- |
| Impact Analysis Date |  | 12/01/06 |  |
| Cost/Budgetary Impact |  | $250K - $500K |  |
| Estimated Project Time Requirements* *Unless otherwise indicated, project time requirements begin upon project initiation. |  | 4 – 6 Months Assumes implementation of PR-40038_01 TX SET 3.0 on 7/1/2007 prior to PRR672 Phase 2 & Phase 3 initiation. Assumes implementation of processing changes recommended by Collaborative Analysis for 814_20 Creates and 814_20 Changes prior to PRR672 Phase 2 & Phase 3 initiation: SIRs 10999 and 11000. |  |
| ERCOT Staffing Impacts (across all areas) |  | PRR672 Phase 2 & Phase 3 has the potential to temporarily impact existing ERCOT staff for development of the functionality proposed by this PRR in the following groups: - Retail Customer Choice - Commercial Operations - Retail Client Services - Commercial Services - Enterprise Integration - Market Operations Testing - Market Operations DPO - Retail Market Analysis - Commercial Ops Data Integrity & Admin Ongoing support for PRR672 Phase 2 & Phase 3 has staff impact, in addition to Phase 1 staff impact, to the following group: - Retail Customer Choice – 2 FTE |  |
| ERCOT Computer System Impacts |  | Implementation of PRR672 Phase 2 & Phase 3 includes modifications to the following transaction timings : Level 1 - to be processed within 1 Retail Business Hour - Priority Move-ins Level 2 - to be processed within 2 Retail Business Hours - Standard Move-ins - Move-outs Implementation of PRR672 Phase 2 & Phase 3 would impact the following system/process areas: - Paperfree - NAESB and peripherals - TIBCO - Siebel - Lodestar - ETS - protocol calculation / reporting changes. - Cross-system architectural changes to support volumes and timings - Monitoring of systems to support required volumes and timings Assumptions for PRR672 Phase 2 & Phase 3: - Exclusion of transaction volumes submitted during annual validation period and "large" volume transactions. - "Large" volumes to be defined following stabilization of PR-50121_07 – Retail Business Processes. For the purpose of this Impact Analysis, assumptions (see above) have been made regarding the business requirements of this PRR. These assumptions and other requirements are to be confirmed or corrected as part of the project planning process. Any modification of assumptions or requirements during the project planning process will be reflected in the estimates of project time, cost, etc. |  |
| ERCOT Business Function Impacts |  | Implementation of PRR672 Phase 2 & Phase 3 would impact the following business process areas: - Retail Customer Choice - Commercial Operations - Retail Market Analysis - Commercial Ops Data Integrity & Admin |  |
| Grid Operations & Practices Impacts |  | None. |  |

Alternatives for a More Efficient Implementation (include explanation of impacts)

NA

Evaluation of Interim Solutions (e.g., manual workarounds)

NA

Feasibility of Implementation

Impact on Resource Availability: - PR-40038 – TX SET 3.0, including Mass Transition and Terms and Conditions - PR-50088 – ETS Transition to EDW (Enterprise Data Warehouse) - PR-50061 – EDW EAI (Enterprise Application Integration) Transition - PR-60015 – ESI ID Account Table Split - PR-70005 - EIS Siebel to L* Data Comparison - PR-70007 - MarkeTrak Enhancements - PR-70009 - Systematic Exception Reprocessing Functionality - PR-70008 – Exception Reporting / Monitoring Enhancements - Regular Retail Releases - Nodal Projects - Integration - Network Model Management Systems (NMMS) - Market Management System (MMS) - Energy Management System (EMS) - Commercial Systems Impact to Other Projects – All Phases: Technical dependency on other projects: - PR- 50121_07 Retail Business Processes. Changes to the Retail Transactions applications in support of the TIBCO framework are currently in progress. Risk is high that resolution for testing and stability issues related to RBP will impact design and development work on PRR672. - 50088 - ETS (ESIID Tracking System) Transition to EDW - 50061 - EDW EAI Transition (inc. PaperFree & NAESB) Scheduling dependency on other projects: - PR-40038 – TX SET 3.0, including Mass Transition and Terms and Conditions

Comments

Estimates in this Impact Analysis should be revisited following completion of projects with technical impacts to PRR672 Phase 2 and 3: - PR- 50121_07 Retail Business Processes Excluded from the estimates in this impact analysis are the following transaction timing changes: Level 1 - 814_20 changes (i.e. maintains) - Findings by ERCOT support alternative to changing transaction timing for 814_20 Creates (adds) – near term approach - changing transaction flow process for 814_20s (Two SIRs to be in Feb 2007 release) - Automate the 814_20s throttling capabilities within current processing pipe (all 814s) - Building a separate processing pipe for 814_20/814_21 processing - ERCOT requests the market to review the production results from the near-term before adding system changes to PR-60008for the 814_20s Level 2 - Off-cycle Switches - ERCOT does not believe the analysis supports the timing changes for the following: - Market behavior of sending >15 days from date requested – changing the timing does not change the result for the end use customer - Protocol language for First Available Switch Date (FASD) - Off-cycle Drop to AREP - ERCOT plans to file a PRR to move these to Level 4 Level 3 - 814_20 changes (i.e. maintains) - ERCOT recommends near term approach – changing transaction flow process for 814_20s (Two SIRs 10999 and 11000 to be in Feb 2007 release) - Automate the 814_20s throttling capabilities within current processing pipe (all 814s) - Building a separate processing pipe for 814_20/814_21 processing. - ERCOT requests the market to review the production results from the near-term SIRs 10999 and 11000 before adding system changes to PR60008 for the 814_20s - Historical Usage – Collaborative Analysis findings indicate that ERCOT already meets the 4 hour turn for historical usage (867_02).