## Slide 1: Texas Nodal Energy & Market Management System EMS/MMS Projects Revision Request Discussion for PRS December 14, 2006 Al Hirsch EMS/MMS Project Manager

## Slide 2
EMS/MMS Agenda – EMS & MMS Project Status Update
MMS Phase 1 & Phase 2 Accelerated SCED Milestones
Notes: <number>
<footer>
<header>
<date/time>

## Slide 3
EMS/MMS Agenda – EMS & MMS Project Status Update
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4: EMS/MMS Agenda – EMS & MMS Project Status Update
MMS Phase 2 Milestones
SCED FAT
MMS FAT

## Slide 5: EMS/MMS Agenda – EMS & MMS Project Status Update
MMS Phase 2 – Accelerated SCED Delivery

## Slide 6: EMS/MMS Agenda – EMS & MMS Project Status Update
MMS Phase 2 – MMS Delivery

## Slide 7: EMS/MMS Agenda – EMS & MMS Project Status Update
MMS Phase 2 – Original Integrated MMS Delivery

## Slide 8: Impact of Changes – Key Points
MMS – Off-The-Shelf System Customized for Nodal Protocols
Original Integrated MMS Delivery Split for Early Real Time Delivery Resulted in Increased Development Complexity
MMS Schedule Already Compressed to Recover 6 Week Delay of Vendor Selection & Start
Development Already in Progress; Testing Phase Begins Soon
MMS June 2007 – Deliverable is on Critical Path for Nodal
Milestones in Other Projects. Successor Schedules Not Purported to Be Able To Absorb Slippage.
Result: Impact of Revision Requests are Chained Across Split MMS delivery; Case in point: 018NPRR

## Slide 9: EMS/MMS Agenda – Conclusion
Wrap-Up
Next Steps