## Sheet1
MCT Issue Log Texas SET 3.0
Issue # | Issue Type | Affected Txn | Change Control Affected | Issue Statement | Issue Status | Date added | Date of Status Change | Source
1.1 | Implementation Guide Gray Box | 814_04 | Emergency CC 2006_703 | Clarification required that 'SNP' shall only be used by the TDSP when 814_03 is for Mass Transition and a Safety Net Request is pending for the ESI ID. Update REF~7G 'SNP' gray box | Closed | 2006-08-23 | Adopted 8/24/2006
1.2 | Implementation Guide Gray Box | 814_08 | Emergency CC 2006_703 | Correct 'MTC' Mass Transition Cancel gray box to restrict use to 'ERCOT Use Only' in the REF~1P (Status Reason) | Closed | 2006-08-23 | Adopted 8/24/2006
1.3 | Implementation Guide Gray Box | 814_09 | Emergency CC 2006_703 | Correct 'EFR' Evaluate for Resubmission to remove 'For ERCOT Use Only' since this is a respons from TDSP in the REF~1P | Closed | 2006-08-23 | Adopted 8/24/2006
1.4 | Implementation Guide Gray Box | 814_14 | Emergency CC 2006_703 | Correct DTM~376 header gray box to be clear that segment is only required when Mass Transitin and Move-out date is needed to be communicated to the gaining CR from ERCOT | Closed | 2006-08-23 | Adopted 8/24/2006
1.5 | Implementation Guide Change | 814_15 | Emergency CC 2006_703 | Correct ASI to remove the 'RL' data element from this segment, which is not necessary since 'Accept' will accomplish the same thing. | Closed | 2006-08-23 | Adopted 8/24/2006
1.6 | Implementation Guide Gray Box; Updated Market Requirements | 814_02 | Emergency CC 2006_700 | Add two new MSC Codes to the SAC04 of the 814_02 Transaction to meet a regulatory requirement identified by TXU ED | Closed | 2006-08-23 | Adopted 8/24/2006
1.7 | Implementation Guide Change | 650_01 | Emergency CC 2006-701 | Add new 'YNQ Yes/No Friday Overdue Authorization for Disconnects for Non-Payment' segment; recommendation from Terms and Conditions Task Force | Closed | 2006-08-23 | Adopted 8/24/2006
1.8 | Implementation Guide Change | 650_04 | Emergency CC 2006-702 | Provides the TDSP with the mechanism to correctly communicate the action (BGN08) taken when services have been Reconnected due to Denial of Access (RC004) by the TDSP | Closed | 2006-08-23 | Adopted 8/24/2006
1.9 | Updated Change Control document | 814-25 | Corrected CC 2006-694 | Removed 814_25 from Affected TX SET Transaction(s) section of Change Control form since it does not contain the N1 Service Address loop | Closed | 2006-08-23 | Adopted 8/24/2006
1.1 | Updated Change Control document | 650_02 | Corrected CC 2006- 698 | Corrected typo in 650_02 transactions in Detailed Description and Reason for Proposed Change(s) section of Change Control Form to state transaction 650_02 instead of 650_01 | Closed | 2006-08-23 | Adopted 8/24/2006
2.1 | Updated Change Control document | 814_19 | Corrected CC 2006-692 | Added 814_10 to 'Affected EDI Transaction Set' section | Closed | 2006-09-11 | Adopted 9/11/2006
2.2 | Implementation Guide Gray Box; Updated Market Requirements | 814_08, 814_09 | Corrected CC 2006-692 | Added 814_08, 814_09 to first bullet ('TS' indicator on BGN segment) | Closed | 2006-09-11 | Adopted 9/11/2006
2.3 | Updated Change Control document | 814_09 | Corrected CC 2006-692 | Added to New Cancellation Code 'MTC' bullet | Closed | 2006-09-11 | Adopted 9/11/2006
3.1 | ERCOT Coding Change | 814_05 | CC 2006-692 | Missing from section to use existing REF~7G segment with new code of '017' to represent service terminated because service provider went out of business. Decision was made for ERCOT to change the '017' reject code to A13 on the outbound 814_05 and put '017' into the REF03 | Closed | 2006-10-03 | Adopted 10/3/2006
3.2 | Updated Change Control document | 814_14 | CC 2006-692 | Add description to Change Control to state: Need new REF~ACD segment on 814_14 for POLR Customer Class designation (Implementation Guides are correct); updated change control | Closed | 2006-10-03 | Adopted 10/3/2006
3.3 | Market Requirements Document Change | n/a | n/a | Removed Appendix C: File Layout for Reporting of POLR Customer Class and modified Section 1.A Reporting of POLR Customer Class to clarify that this will be done through TML | Closed | 2006-10-03 | Adopted 10/3/2006
3.4 | Market Requirements Document Change | n/a | n/a | Modified Appendix B: File Layout for Customer Billing Contact Information to include all record types and file types used for sending and receiving Customer Billing Contact Information Files | Closed | 2006-10-03 | Adopted 10/3/2006
3.5 | Market Requirements Document Change | n/a | n/a | Added Appendix C: TDSP Priority Code tables for use in prioritizing Move-ins (Protocol Revision (PRR672) | Closed | 2006-09-11 | Adopted 10/3/2006
4.1 | Requirements/Implementation Guide Clarifications; Market Requirements Document Change | n/a | n/a | Clarification on use of "Mass Transition Customer" in 814_03. ERCOT will place "Mass Transition Customer" in the Customer Name field on the 814_03. TXU ED requested ERCOT to send a file containing ESI ID, Customer Name, and Primary Phone number to the TDSPs during a mass transition. This will not be included in scope of Texas SET 3.0, but will be included in a SIR during a retail release following Texas SET 3.0 implementation. RMGRR will be written to detail this process. TDSPs requested 814_PCs from CRs for every 814_04 they send the POLR CR during a mass transition. POLR CRs to review internally to see if this is possible. | Closed | 2006-10-24 | Discussed 10/24/2006; Resolved 11/6/2006
4.2 | Requirements Clarification | n/a | n/a | Allocation of ESI IDs in a mass transition - what is the source of the load-share data used as a basis for the allocation? POLRs provide the MWH information to the PUCT. PUCT confirmed the percentages will be sent to ERCOT for use in the ESI ID allocation. | Closed | 2006-10-24 | Resolved 10/24/2006
4.3 | Testing Clarification | n/a | n/a | New CRs must send a test Customer Billing Contact Information (CBCI) file containing mock data to ERCOT during flight test. TTPT Script Sub-team asked if ERCOT will provide the mock data. Answer from ERCOT testing team: No, file layouts will be provided to new MPs at Market Orientation; however, new CRs need to understand how to format their files and must create their own mock data. | Closed | 2006-10-24 | Resolved 10/24/2006
4.4 | Testing Clarification | n/a | n/a | In testing Mass Transition scripts specific to POLRs during Flight test, TTPT Script Sub-team asked if all CRs must test this functionality? Answer from MCT: All eligible POLRs and designated POLRs must test the POLR Scripts. | Closed | 2006-10-24 | Resolved 10/24/2006
5.1 | Requirements Clarification; Market Requirements Document Change | n/a | n/a | Will CRs need to send an initial load production Customer Billing Contact Information (CBCI) to ERCOT after go-live of Version 3.0 on 7/1/07? Answer: Yes, this will be done during the last two weeks of July, 2007. As a reminder, the CBCI file sent during Flight 0407 by all CRs is a test file and cannot be considered production. Market Requirements | Closed | 2006-11-07 | Discussed 11/7/2006; Resolved 12/11/2006 | Question from 11/08 RMS meeting
5.2 | Requirements Clarification | 650_04 | n/a | On 650_04 reconnects (RC004) for Denial of Access, should market participants sent the BGN02 from the Disconnect in the BGN06? Answer: No, this is not required. Texas SET Issue for changes to gray box will be written for future implementation. In addition, this issue will include BGN matching for Disconnect for Non-pay discussed at a previous meeting. | Closed | 2006-11-06 | Resolved 11/6/2006 | Question from 10/24 MCT meeting
5.3 | Requirements Clarification | 867_03, 810_02 | n/a | Request for clarification on the addition of the new replacement code on the 810_02 and 867_03 (Terms & Conditions Requirement 3 in the Texas SET 3.0 Market Requirements document). AEP & CNP must send cancel/rebills for all months unless its an IDR. For IDRs, they only send cancel/rebill for month impacted. TXUED - only sending the impacted month. No word on procedure of other TDSPs. | Closed | 2006-11-06 | Resolved 11/6/2006 | JG Email
5.4 | Requirements Clarification | 867_03 | n/a | How to handle 867_03 cancel/rebills that occur after Version 3.0 is in production but are for billing periods prior to Version 3.0 and the months being cancelled were estimated? The REF~5I segment for Estimates was added to the 867_03 transaction in Version 3.0 and does not exist in Version 2.1. AEP submitted proposed solution for TDSPs to send 867_03s with a "D10" reason code (Other) in the REF02, the reason explanation of "Before V3.0", and Estimation counters of "0". It was determined to use this proposed solution at 12/11/2006 MCT meeting and the Market Requirements document have been redlined documenting these changes. | Closed | 2006-11-06 | Discussed 11/6/2006; Resolved 12/11/2006 | CR Email
6.1 | TML Requirements Clarification | 814_14 | n/a | Question: How will TML be updated to distinguish 814_14 Drops to AREP from 814_14 Drops to POLR? Answer: TML is being updated to reflect if transactions are related to a Mass Transition so the 814_14 will have an indicator that it is a Mass Transition Drop. You will be able to distinguish between the two. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.2 | Requirements Clarification | 814_15 | n/a | Question: Is ERCOT prepared to receive 814_15 rejects for ANSI errors? Answer: Nothing is changing with Texas SET 3.0 that would change the way an 814_15 reject is handled | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.3 | Requirements Clarification | n/a | n/a | Customer Billing Contact Information File. When ERCOT sends a response file identifying the records that have failed, does ERCOT expect the CR to fix the file and re-submit a new file? The CR has until the 15th of the corresponding month to re-submit a corrected file. Is there a naming convention for the ERROR file? MTCRCustomerInformationERCOTResponse. Or will there even be an error file sent to the originating CR of the April and October customer billing contact information file? Yes. Can an "umbrella" CR with multiple DUNS numbers send one production file for all of their entities' ESI IDs and can one DUNS number be included for all recores in the file? No, CRs that have more than one DUNs number must submit separate files for each DUNs number. | Closed | 2006-11-21 | 2006-12-11 | JR Email
6.4 | Requirements Clarification | n/a | n/a | What happens if a customer calls in for a MVI/MVO during a Mass Transition? How does this affect the data we have in the system and the ERCOT process? MIMO rules will continue to handle the processes. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.5 | Requirements Clarification | n/a | n/a | How will first notice of the ESI IDs be provided (to POLR CRs) and what data will we get? This is prior to receiving the 814_14? Lists of ESI IDs will be generated during the ESI ID allocation process and at the time the 814_03s are sent out. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.6 | Requirements Clarification | 810, 867 | n/a | Can the TDSP continue to send us (CR) 810 transactions even after the 867 is estimated for the 3rd time? Yes. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.7 | Requirements Clarification | n/a | n/a | Will the TDSP disconnect Special Needs customers or will they be estimated like critical load customers? All TDSPs will follow their processes for Special Needs Customers; no changes. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.8 | Requirements Clarification | n/a | n/a | If TDSP installs a new meter, what do the transactions look like? Does CR get an exchange? Yes. Is there a gap in consumption? No. No changes to existing processes. | Closed | 2006-11-21 | 2006-12-11 | KP Email
6.9 | Requirements/Implementation Guide Clarifications | 810 | n/a | How will charges show on the 810 for meter changes made as a result of TDSP Action following Denial Of Service, e.g. if a remote Reading Meter is installed or Service is disconnected and subsequently reconnected? What codes will be used? Using existing SAC04 codes; see TX SET 810 Implementation Guide. Will the charge reference a service order number if applicable? Yes. | Closed | 2006-12-11 | 2006-12-11 | KC email