## Sheet1
161 | ERCOT, Settlement (Hong Xiao) | p. 55, Sec. 3.6.1, SFT | To deternime the deration factor of each oversold element, the total of the positive flows resulted from all outstanding CRRs prior to the DAM execution needs to be calculated in addition to the oversold quantity. | Response | Moved to IDA Punch List. Current requirement does not cover the calculation for positive flows from all outstanding CRRs, However, MMS can provide all information to calculated this flow.

## DAM & SASM
| Document Name: | MMS Requirement Specification For DAM and SASM Ver.0.9.2
| Issuing Entity (Name) | Page Number | Description | Response | Reviewer | Reason / Comment | Updated Reason / Comment
34 | Reliant (M.Wagner) | p. 06, Sec. 1 | The primary authority directing the operational characteristics and behavior of the Market Management System is the Texas Nodal Protocols. This requirements document set is provided as a supplement to assist in the implementation of this system which includes all processes, tools (hardware and software), and operations and constraints necessary for full compliance withto the Texas Nodal Protocols. | Accepted | J.Gilbertson
35 | Reliant (M.Wagner) | p. 09, Sec. 2.1 | Network Security Monitor (NSM): Evaluates network security given the energy and CRR dispatches from either IUC or NCUC. [Reliant: What is meant by “CRR Dispatches?” Are you talking about CRRs carried to Real-Time? Is this to determine the oversold level?] Generates network constraint equations describing the changes required to the energy and CRR dispatches to remove transmission constraint violations. | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc.
144 | ERCOT | p.12,Sec.2.2 | SASM is an acronym for Supplemental Ancillary Service Market, not Supplemental Ancillary Service Management | Accepted |  | Requirements document will be updated accordingly for all occurances.
36 | Reliant (M.Wagner) | p. 13, Sec. 2.3 |  | Clarification Provided | J.Gilbertson | See document Pricing Issues with Fixed Quantity Block Offers and Bids in DAM.doc.
110 | LCRA (S.Siddiqi) | p. 13, Sec. 2.3 | In certain cases LMPs produced by the DAM clearing process could be lower than cleared fixed quantity offer prices and/or higher than cleared quantity bid prices [Does this imply that block bids and offers could lose money? Can the system reject bids/offers that are not supported by final LMPs and MCPCs?] | Clarification Provided | J.Gilbertson | See document Pricing Issues with Fixed Quantity Block Offers and Bids in DAM.doc.
154 | ERCOT | p.18, Sec. 2.4 | It may be useful to state the UOM associated with the input/output data elements to be sure that it is correct (now rather than later.) | Response |  | Moved to IDA Punch List. Unit of measure will be addressed during detailed design.
155 | ERCOT | p.18, Sec.2.4 | Things specified as outputs for Settlements (in the input/output section) are not necessarily in-synch with the elements listed as outputs in later process requirements. For instance, the outputs from DAM to the Post Processor seem to include what Settlements needs, but are not listed as an output for Settlements. The outputs from the Post Processor do not appear to be at the appropriate level for settlements or include everything that settlements needs. | Response |  | Moved to IDA Punch List. MMS will provide available data to other systems. Transformation of data for a particular system will be done in the integration layer.
153 | ERCOT | p. 18, Sec. 2.4 | Input and Output Data Settlement will also need the Three Part Supply Offer data associated with an awarded Three Part Supply Offer (for instance, Settlements needs the startup price, min energy price, % FIP, %FOP, etc) – we need access to more than just the award Does settlements really need Capacity Trades and Energy Trades resulting form the DAM? I think that we need them, as they exist in a snapshot taken for a RUC process and the final as reflected by 1430 in the day after the Operating Day… I don’t think we need them as they exist as a result from the DAM (assuming that they can change between completion of DAM and start of DRUC, therefore want it from the snapshot at DRUC.) Does settlements really need the Self-Schedules out of the DAM? These can be updated through the end of the Adjustment Period for the Operating Hour for which they apply. Therefore, I think that settlements would want that “final” value for the Operating Hour that exists at the end of the Adjustment Period for that Operating Hour – not a preliminary value out of DAM. Same type of comment for DC Tie schedules. If these can change between DAM and the end of the Adj Prd for the Operating Hour, then settlements wants the final value that exists at the end of the Operating Hour’s Adjustment Period. Generic Caps (documented as an input to MMS from Settlements) - settlements can provide the data but Operations will need to calculation with the appropriate FIP and FOP. The back up data can come from settlements but does not have to since the back up data comes from a table in the Nodal Protocols, Section 4.4.9.2.3, Startup Offer and Minimum-Energy Offer Generic Caps (same comment made on RUC requirements document) Verifiable Costs (documented as an input to MMS from Settlements: (same comment made on RUC requirements document) Verifiable Startup data available from the settlement system will include: AFCRS – Actual Fuel Consumption Rate per start for each start type VOMS – Verifiable O&M Expenses per start for each start type GASPERSU – Percent GAS used for a start for each start type OILPERSU – Percent OIL used for a start for each start type SFPERSU – Percent Solid Fuel used for a start for each start type Verifiable Minimum-Energy data available from the settlement system will include: VFCLSL – Verified Fuel Consumption at LSL VOMLSL – Variable O&M Expenses at LSL GASPERME – Percent GAS used to operate at minimum OILPERME – Percent OIL used to operate at minimum SFPERME – Percent Solid Fuel used to operate at minimum Settlements will provide the data but Operations must perform a calculation for both Verifiable Startup and Minimum-Energy using the appropriate FIP and FOP Anything stated with settlements as the destination will be stored and available in the MI database, right? | Response |  | Moved to IDA Punch List. Interface/integration issue. Snapshot timing needs to be finalized. MMS snapshots are configurable. This Three-Part Offer data will be provided to settlements. There are no Capacity/Energy Trades/Self-Schedules "that result from DAM." The reason Trade/Self-Schedule submission requirements are in the DAM document is because the other Market Participant submissions are in this document. Taking a snapshot at the submission cut-off time is appropriate as you described.
111 | LCRA (S.Siddiqi) | p. 16, Sec. 2.4.1, Table 2-1 |  | Clarification Provided | J.Gilbertson | QSE submission for AS Offer does not include any link information. DAM can determine (using resource id) if resource has corresponding 3 part energy offer for the as offer. See document Ancillary Service Offer Modeling.doc.
1 | TXU | p. 17, Sec. 2.4.1, Table 2-1 |  | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
2 | TXU | p. 17, Sec. 2.4.1, Table 2-1 |  | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
3 | TXU | p. 17, Sec. 2.4.1, Table 2-1 |  | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
145 | ERCOT | p.18, Sec.2.4.1, Table 2-1 | The Input and Outputs in the System Scope need to have a lot more definition surrounding them. Specifically, how is MMS anticipating receiving the calculated Ancillary Service Load Ratio Share from the Settlement System. | Response |  | Moved to IDA Punch List. Interface details need to be worked out. The requirements document is not meant to describe inputs/ouputs in detail. The LRS needed is specified in more detail in PD1.
146 | ERCOT | p.18, Sec.2.4.1, Table 2-1 | The Functional Requirements Input and Output need to provide some detail around how the data will look. | Response |  | Detailed design will provide more details.
147 | ERCOT | p.22,Sec.2.4.2, Table 2-2 | The Functional Requirements Input and Output need to provide some detail around how the data will look. | Response |  | Detailed design will provide more details.
156 | ERCOT | p.23, Sec.2.4.2, Outputs | Section 2.4.2 Outputs: a) Following data are listed as outputs to settlements but may not be actually needed: · Derated CRR Offers (NOIE PTP Options Declared to be Settled in RT) - Name of CRR Account Holder - CRR ID - Operating Date/Hour - Derated Quantity - Minimum Reservation Price · Awarded PTP Obligation Bids - Not to Exceed Price - Clearing Price b) “Day-Ahead Show Price” is needed for settlements’ purposes but not listed: c) Which system is going to calculate the “Dearation Factor” for oversold CRRs? The MMS outputs may be sufficient to calculate this value but which system is going to define and perform the calculation? | Response |  | Moved to IDA Punch List. This is an interface/integration issue. MMS will provide available data for other systems. A) Need to work out what Settlements need as we work on the interface specifications. B) "Day-Ahead Shadow Price" will be added as an output. C) MMS applications (e.g. SCED) have to be highly available. As a general rule if the results of the computation are not used by a MMS application then the approach is to push the calculation to the integration layer or another system.
112 | LCRA (S.Siddiqi) | p. 25, Sec. 2.4.2, Table 2-2 Settlement, CRR Account Holder |  | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc.
37 | Reliant (M.Wagner) | p. 24, Sec. 2.4.2, Table 2-2 DRUC | · Reduced Ancillary Services Plan [Reliant: what is a “Reduced” AS Plan? If ERCOT reduces its plan, do the QSE obligations change?] | Clarification Provided | J.Gilbertson | The reduced plan is used by DAM when submitted AS Offers are not enough to cover the total AS Plan. QSE obligations do not change. DRUC computes how much AS is still needed after the DAM by subtracting the reduced AS Plan from the actual AS Plan.
38 | Reliant (M.Wagner) | p. 24, Sec. 2.4.2, Table 2-2 QSE | · Awarded Combined Cycles Offers | Accepted | J.Gilbertson
113 | LCRA (S.Siddiqi) | p. 27, Sec. 2.4.2, Table 2-2 |  | Accepted | J.Gilbertson | OK except will output the "contingency ID" instead of "Contingency element". See similar item response on CE9 "Shadow prices"
150 | ERCOT | p.27,Sec.2.4.2,Table 2-2 | The outputs for many of the requirements do not explicitly indicate that it is necessary as an output for Settlements. | Response |  | Moved to IDA Punch List. This is an interface/integration issue. MMS will provide data to other systems as available. The integration project will perform necessary transformation.
39 | Reliant (M.Wagner) | p. 28, Sec. 3.1.2, PD2 | e. The results of the bid/offer processing are then relayed back to the QSE. [Reliant: is this validation part of the ACK?] | Clarification Provided | J.Gilbertson | Yes, assuming that the ACK pertains to the bid response.
40 | Reliant (M.Wagner) | p. 29, Sec. 3.1.2, PD2 | 2. QSEs shall be notified with the results of the validation (pass/fail) along with a transaction ID for tracking purposes. In case of failed submissions, the QSE shall also be notified of the validation errors. Please refer to Business requirement section: PD3 (General Validation Process of QSE Input) for more details. [Reliant: what is a transaction ID and who generates it—ERCOT or the QSE?] | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
4 | TXU (R.Spangler) | p. 28, Sec. 3.1.2, PD2 | 3. QSEs shall have the ability to view and query all of their valid submissions on the MIS at any time. The MMS system shall permit the QSEs to view input data for seven days in the past, the present operating day and future. The time period of seven days in the past is provided for the QSEs to view data for similar days of the week.TXU: If this transaction is via the Query, please identify it as such. | Accepted | J.Gilbertson | Yes, viewing submissions involves querying the database. DAM Requirements document will be updated accordingly.
41 | Reliant (M.Wagner) | p. 29, Sec. 3.1.2, PD2 | 3. QSEs shall have the ability to view all of their valid submissions on the MIS at any time. [We should be able to query the system for valid submissions at any point in time.] The MMS system shall permit the QSEs to view input data for seven days in the past, the present operating day and future. The time period of seven days in the past is provided for the QSEs to view data for similar days of the week. | Clarification Provided | J.Gilbertson | Yes
135 | GP&L (R.Hoeinghaus) | p. 29, Sec. 3.1.2, PD2 |  | Accepted | J.Gilbertson | See document Explanation of Market Submission Items.doc. Revise 1c to state "c. If the data is already present, then the information from the new submission is used to update the data in the operational database, except for AS Offers from a resource and Three-Part Supply Offers. "
5 | TXU (R.Spangler) | p. 28, Sec. 3.1.2, PD2 | 6. Submissions of all DAM Offers and Bids shall have the same start date and end date. TXU: This requirement is unclear with regard to its expected impact on QSEs. When and how does this restriction apply. Is it Resource/Load specific? Can a QSE submit multiple offers and bids for different blocks of hours in the DAM. If so, can they overlap. What if 1 QSE is representing multiple fleets and is offering from each fleet’s resource? How does this requirement relate to requirement 9 below? and etc | Clarification Provided* | J.Gilbertson | Since there is date information included in the start time and end time, the date component of both the start and end time should be equal. Hours can be different for all offers and bids. Only Resource-specific offers are not allowed to overlap. DAM Requirements document will be updated :Change 6 from "Submission of all DAM Offers and Bids shall..." "Each DAM Offer and Bid shall..." See document Explanation of Market Submission Items.doc.
136 | GP&L (R.Hoeinghaus) | p. 29, Sec. 3.1.2, PD2 |  | Accepted | J.Gilbertson
42 | Reliant (M.Wagner) | p. 29, Sec. 3.1.2, PD2 | 6. Submissions of all DAM Offers and Bids shall have the same start date and end date. [Reliant: but the hours can be different, right?] | Clarification Provided | J.Gilbertson | Yes. See document Explanation of Market Submission Items.doc.
141 | REP Segment (J. Reynolds) | p. 28, Sec. 3.1.2, PD2 | 3.2.1 -- PD 1: Requirement # 6 - "Submission of all DAM offers and bids shall have the same start date and end date" -- Does this mean the Operating day in question?? | Clarification Provided | J.Gilbertson | No, it can be any day in the future.
6 | TXU | p. 28, Sec. 3.1.2, PD2 | 9. Overlapping offers for Three-Part Supply Offers shall not be allowed. Any offer that is submitted for a period of time where an existing Three-Part Supply Offer exists shall be rejected in full. Overlapping Offers for combined AS Offers shall also be rejected in full. TXU: Why not overwrite previous offers? | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
43 | Reliant (M.Wagner) | p. 29, Sec. 3.1.2, PD2 |  | Clarification Provided* | J.Gilbertson | See document Explanation of Market Submission Items.doc. DAM Requirement document will be updated: Revise 1c to state "c. If the data is already present, then the information from the new submission is used to update the data in the operational database, except for AS Offers from resources and Three-Part Supply Offers. "
44 | Reliant (M.Wagner) | p. 30, Sec. 3.1.23, PD3 | Subsequently, the data shall be re-validated (Phase 2) on every scheduling day for D+1 for credit checks, facilities/participant access rights, validity and other pertinent validations necessary before the DAM market closes. This shall occur at the validation time (nominally at 7:00 am on the scheduling day). Success or failure messages shall be sent to QSE after phase 2 validation has completed. [Reliant: Not clear what this secondary validation is for… Also, ERCOT should not rely on QSEs getting data for the DAM in at 0700 since the deadline isn’t until 1000 AM.] | Clarification Provided | J.Gilbertson | QSE may submit ahead of time for which MMS does not have the data such as the latest credit limit, registration data to validate against. By 0700, the data is available for validating QSE input. Data submitted after 0700 runs through all the necessary validations including credit checks as validation data is now available.
45 | Reliant (M.Wagner) | p. 30, Sec. 3.1.23, PD3 | QSE submitted data shall be validated and stored in the operational database upon receipt. The QSE shall be informed of the results of validation. [Reliant: presumably a pass signal is straight forward, but will a rejection include the reason for the validation failure? It should.] | Clarification Provided | J.Gilbertson | Yes. Error messages will be included to indicate the nature of the error.
46 | Reliant (M.Wagner) | p. 31, Sec. 3.1.23, PD3 | The successfully validated and processed data is indicated to QSE by information messages, whereas failures are indicated by error messages. [Reliant: will error messages include the reason for the validation failure?] | Clarification Provided | J.Gilbertson | Yes. Error messages will be included to indicate the nature of the error.
149 | ERCOT | p.31,Sec.3.1.3,PD3 | Some of the Requirements steps indicate that a step may be rejected, but do not provide what happens if rejected. | Response |  | Moved to IDA Punch List. More clarity required on the comment. If this is referring to validation, PD3 describes in general what happens when submissions are rejected (QSE is informed of the rejection and the reason for it).
47 | Reliant (M.Wagner) | p. 31, Sec. 3.2.1, ST1 | 5. Manual input of the RMR Offers by the ERCOT operator shall not be subject to validations against the RMR contracts. [Reliant: Don’t understand this—why would the operator be allowed to enter data that is outside of the contract—or to force the unit to operate outside of known parameters or limitations? How will such entries that are not subject to contract validations be tracked and reported to the market?] | Clarification Provided | J.Gilbertson | The software functionality to be able to modify the automatically generated offer is included because the automatically created offer may not account for costs such as emissions related costs. Tracking and reporting of deviations from the automatically created RMR offer will be enforced.
7 | TXU | p. 31, Sec. 3.2.2, ST2 | b. Energy offers (both low and high limits) TXU: High and low limits on Offers? | Clarification Provided* | J.Gilbertson | High/Low limits apply for Combined Cycle just like any other Resource. This does not need to be explicitly stated here and can be deleted. DAM Requirements document will be updated: Change to "Energy Offer Curve" and will state "Min-Energy Offer" for consistency
8 | TXU | p. 31, Sec. 3.2.2, ST2 | e. Reserve bids TXU: What is this? | Clarification Provided* | J.Gilbertson | Change to "AS Offers."
48 | Reliant (M.Wagner) | p. 32, Sec. 3.2.2, ST2 | e. Reserve bids [Reliant: what is a reserve bid? Bids are to buy something, right?] | Clarification Provided* | J.Gilbertson | Change to "AS Offers."
9 | TXU | p. 32, Sec. 3.3.1, VA1 | c. Trade ID TXU: New Requirement? There is nothing in the existing ERCOT Market for exchanging TradeIDs. Doesn’t seem to be a plausible expectation. | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
10 | TXU | p. 32, Sec. 3.3.1, VA1 | i. Time of submission Capacity Trades submitted after the Adjustment Period for the applicable hours of the Operating Day shall be rejected. TXU: Why? Treat like Energy Trades? | Clarification Provided | J.Gilbertson | 6.4.1(1) states that a QSE may submit and update Capacity Trades during the Adjustment Period.
11 | TXU | p. 32, Sec. 3.3.1, VA1 | e. The QSE who is the other party to the trade shall be notified of the trade and can view and confirm it by setting a flag against the trade. If the other party attempts to submit the same trade afresh, it shall be rejected. TXU: Submitting same trade should serve as the confirmation. Should not have separate confirmation message. Both counterparties should be able to submit the SAME data. Should not be dependant on who submitted first. | Clarification Provided | J.Gilbertson | The requirements follow the Nodal Protocols (4.4.1.1, 4.4.2.1, 4.4.7.3.1): 1. The trade is reported by "a QSE" 2. Must be confirmed by both QSEs 3. The QSE that reports the trade is "deemed to have confirmed it …" Also please see document Explanation of Market Submission Items.doc.
49 | Reliant (M.Wagner) | p. 34, Sec. 3.3.1, VA1 | e. The QSE who is the other party to the trade shall be notified of the trade and can view and confirm it by setting a flag against the trade. If the other party attempts to submit the same trade afresh, it shall be rejected. [Reliant: so does a trade have to be validated by both parties before it can be updated? Can the original submitter remove the trade before it has been validated by the counterparty? (Protocols provide for this.) How will ERCOT identify the trade as the “same trade?”] | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
12 | TXU | p. 33, Sec. 3.3.1, VA1 |  | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
50 | Reliant (M.Wagner) | p. 34, Sec. 3.3.1, VA1 | 4. A given trade is unique for the ordered n-tuple {Trade ID, Buying QSE, Selling QSE and Date/Interval}. For example, QSE-A as buyer and QSE-B as seller can have one unique trade for Capacity for a given Date/Interval and Trade ID [Reliant: so will ERCOT publish specifications for assigning Trade IDs? Why aren’t we relying on time stamps? If all QSEs need to have Trade IDs with each counterparty, how will ERCOT ensure that Trade IDs are unique across the universe of Trades coming in? Will ERCOT assign the Trade ID?]. | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
13 | TXU | p. 34, Sec. 3.3.2, VA2 2.d | a. Trade ID TXU: New Requirement? There is nothing in the existing ERCOT Market for exchanging TradeIDs. Doesn’t seem to be a plausible expectation. | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
142 | REP Segment (J. Reynolds) | p. 34, Sec. 3.3.2, VA2 | 3.3.2 - VA2- Requirement 2 j. "Energy trades submitted after 1430 of the day following..." - Should this be day preceding?? | Clarification Provided | J.Gilbertson | No, Section 4.4.2(3) states “An Energy Trade may be submitted for any Settlement Interval within an Operating Day before 1430 of the following day.” Since Energy Trades only affect the Settlement process that takes place after Real Time, this is not an issue.
14 | TXU | p. 34, Sec. 3.3.2, VA2 3.d | d. QSE not submitting trade must report confirmation. The QSE who is the other party to the trade shall be notified of the trade and can view and confirm it by setting a flag against the trade. If the other party attempts to submit the same trade afresh, it shall be rejected. TXU: Submitting same trade should serve as the confirmation. Should not have separate confirmation message. Both counterparties should be able to submit the SAME data. Should not be dependant on who submitted first. | Clarification Provided | J.Gilbertson | The requirements follow the Nodal Protocols (4.4.1.1, 4.4.2.1, 4.4.7.3.1): 1. The trade is reported by "a QSE" 2. Must be confirmed by both QSEs 3. The QSE that reports the trade is "deemed to have confirmed it …" Also please see document Explanation of Market Submission Items.doc.
15 | TXU | p. 34, Sec. 3.3.2, VA2 |  | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
51 | Reliant (M.Wagner) | p. 36, Sec. 3.3.3, VA3 | 7. The submitted NERC Tags by the QSE shall be subject to validation for well-formed NERC Tags and against the OATI E-Tags supplied interface data. The manual confirming process is not in MMS. However, the confirmed DC tie schedule should save back to MMS for being used by RUC. | Accepted | J.Gilbertson
114 | LCRA (S.Siddiqi) | p. 38, Sec. 3.3.4, VA4 | Self-Schedules, as well as other potential inputs into the DAM, [not used in DAM] shall be validated by the MMS against the Protocol specified criteria and reported to the QSE. This shall provide QSEs with immediate feedback to allow as much time as possible to make the decision to either correct their report and resubmit, or not submit the report. | Accepted | J.Gilbertson
148 | ERCOT | p. 36, Sec 3.3.4, VA4 | What are self-schedules used for in the Day-Ahead Market? | Clarification Provided |  | They are not used. They are in the DAM Requirements document because they can be submitted in the Day-Ahead (and later), and because all of the other QSE submission and validation requirements are in this document.
115 | LCRA (S.Siddiqi) | p. 39, Sec. 3.3.5, VA5 | CRR Offers, as well as other potential inputs into the DAM, shall be validated by the MMS against the Protocol specified criteria and reported to the CRR Account Holder [do these need to be in QSE accounts since if they don’t clear in the DAM, they’re settled in RT?]. This shall provide the CRR Account Holder with immediate feedback to have as much time as possible to make the decision to either correct their offer and resubmit, or not submit the offer. | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc.
52 | Reliant (M.Wagner) | p. 39, Sec. 3.3.5, VA5 2.g | Minimum Reservation Price ($/MWh): Defaults to $2000/MWh [Reliant: Note that Protocols 4.4.5(3) stipulates Min Res price for NOIE CRRs only.] | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc.
53 | Reliant (M.Wagner) | p. 39, Sec. 3.3.5, VA5 2.i | i. Offer of multiple CRRs All CRRs must be of the same type. [Reliant: with the changes to CRRs embodied in NPRRs that the CRR team has put forth, CRRs have changed to “time of use blocks” which means that for a single offer, the “same type” qualifier means ---same “hedge type” (option, obligation, FGR) and same “time of use block.”] All CRRs must have the same source and sink Settlement Points. A block CRR Offer must have the same number of CRRs offered in each hour. [Reliant: note that hourly granularity for CRRs has been removed through NPRRs. CRRs are not defined by “time of use blocks.”] A block CRR Offer must have contiguous hours for the CRRs offered. [Reliant: note that with comments above, this requirement becomes ‘inherent’ by the definition of the CRR time of use block.] | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc.
54 | Reliant (M.Wagner) | p. 39, Sec. 3.3.5, VA5 | 3. Before 7:00 am, any CRR offers submitted shall go through validations (excluding CRR ownership validation and total quantity). Since the CRR auction data is not available to the MMS system, the additional validations shall be done by a background process when the data is available (before 7:00 am) [Reliant: not quite sure the timing works here—if DAM bid submission closes at 11—this seems to indicate that CRR offers are due by 7 AM---not sure that this time constraint is in Protocols.] | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc.
55 | Reliant (M.Wagner) | p. 39, Sec. 3.3.5, VA5 | 4. At 7:00 am, a background process shall run on the MMS system to validate the submitted CRR offers against the CRR auction ownership data (CRR ownership and total quantity). | Clarification Provided* | J.Gilbertson | See CRR Related Issues in DAM.doc. DAM Requirements document will be updated: Change "auction" to "ownership"
56 | Reliant (M.Wagner) | p. 39, Sec. 3.3.5, VA5 | 5. Any CRR offers submitted by the CRR account holder after the background process completes (time to be determined), shall be subject to additional validations, such as whether this CRR offer owner is the real owner and whether the sum of offers of the same CRR ID is greater than total quantity of CRR owned by CRR Account Holder for that CRR ID. [Reliant: not sure that the timing will work. We need to have a ‘hard deadline’ for submission of CRR offers in DAM---but we need a Protocol change to require this in a timeframe different from the timing of the DAM processes in current nodal Protocols.] | Clarification Provided* | J.Gilbertson | See CRR Related Issues in DAM.doc.
57 | Reliant (M.Wagner) | p. 39, Sec. 3.3.5, VA65 | Input: CRR auction owner of record data from CRR system CRR Offer from CRR Account Holders who are NOIEs and this is submitted via the MMS QSE interface. [Reliant: what about other CRR offers? Protocols 4.4.5 allows any CRR holder to Offer a CRR for sale in the DAM.] | 1st change Accepted 2nd comment: Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc. DAM Requirements document will be updated: Change "auction" to "owner of record"
16 | TXU (R.Spangler) | p. 39, Sec. 3.3.5, VA5 | 3.3.5 VA5 – Validation of CRR Offers TXU: The only CRRs that may be sold in the DAM are those that are eligible for settlement in Real Time and that are not subject to the Refund Option. It is not clear that the above checks would be sufficient to invalidate the offer of a CRR that does not meet this criteria. | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc.
157 | ERCOT | p. 39, Sec. 3.3.6, VA6 | Section 3.3.6, VA6: Validation of PTP Obligation Bids” Protocol 7.1 (3) requires that QSEs buying PTP Obligations be CRR holders. Shall a corresponding validation be added? | Accepted |  | Additional validation rules will be added for PTP obligation bid submission. The QSE submitted PTP Obligation Bids should be an CRR Account Holder. [Protocol 7.1.(2)]
58 | Reliant (M.Wagner) | p. 41, Sec. 3.3.6, VA6 | 1. Validation shall take place when PTP Obligation bids are reported submitted to ERCOT. | Accepted | J.Gilbertson
59 | Reliant (M.Wagner) | p. 41, Sec. 3.3.6, VA6 | d. Bid ID (used for overlapping submissions) [Reliant: what is an overlapping submission?] | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
60 | Reliant (M.Wagner) | p. 42, Sec. 3.3.7, VA7 | f. Quantity of self-arrangement provided by Load Resources Rejected: If RRS is more than limiting percentage of AS Obligation [Reliant: what does this mean? Is the “limiting percentage” the ERCOT systemwide defined amount of Responsive that can come from Load Resources? And if so, how is this apportioned/enforced on a QSE by QSE basis?] | Clarification Provided | J.Gilbertson | This percentage not only system-wide but is also applied on a QSE basis as per Section 3.16(7) [revised by NPRR002]
61 | Reliant (M.Wagner) | p. 42, Sec. 3.3.7, VA7 | g. Quantity of total self-arrangement by type Curtail to the total AS Obligation if more self-arrangement is more than total AS Obligation. [Reliant: does this mean that ERCOT will curtail a QSEs self arranged amount? Or would ERCOT reject a QSEs statement of self supply if it exceeds the QSE’s obligation?] | Clarification Provided* | J.Gilbertson | Section 4.4.7.1(1) [revised by NPR006] states that a QSE can self-arrange all but cannot exceed its AS Obligation. ERCOT will not reject but will curtail to the AS Obligation amount any submission where the self-arrangement is more than the QSE AS Obligation. DAM Requirements document to be updated: Typo fix: Curtail to the total AS Obligation if more self-arrangement is more than total AS Obligation
62 | Reliant (M.Wagner) | p. 43, Sec. 3.3.7, VA7 | 4. This submission shall trigger the credit checking process. [Reliant: Per Protocols Section 16.11.4.5 and 4.4.10, ERCOT calculates the credit requirement for each QSE as set forth from the protocol citations below. How does the DAM account for the credit limit? Does the DAM then employ a specific credit constraint for each QSE? Are a QSE’s bids be screened by the credit requirement? | Clarification Provided | J.Gilbertson | MMS will calculate the credit exposure as specified in Section 4.4.10. The credit limit to compare the exposure against - will be provided by CMM on a QSE basis. Each offer and bid is screened by the credit requirement.
63 | Reliant (M.Wagner) | p. 44, Sec. 3.3.7, VA7 | [Reliant: If ERCOT intends to reject QSE bids on the basis of credit, a credit limit failure error must be generated for each QSE ---with the dollar value that is allowable—when a QSE’s bids exceed the credit limit. Recommend that this occur as part of bid validation.] | Clarification Provided* | J.Gilbertson | Agreed. This will be added to the credit requirement CR1.
64 | Reliant (M.Wagner) | p. 44, Sec. 3.3.8, VA8 | AS offers shall be categorized in to three groups: [Reliant: what is the purpose of breaking the AS up into groups? This makes it look like procurement of NSRS and Reg down are separate processes. Does ERCOT envision procurement of these as separate processes?] | Clarification Provided | J.Gilbertson | See document Ancillary Service Offer Modeling.doc.
65 | Reliant (M.Wagner) | p. 45, Sec. 3.3.8, VA8 | The System shall not validate Resource specific Ancillary Service Offers against the associated Resource’s COP. [Reliant: What is the purpose for this statement? Does ERCOT intend for to use the COP as envisioned in Protocols 4.4.7.2.1(1)(e) despite the fact that it might not be used for validation?] | Clarification Provided | J.Gilbertson | COP Resource Status will not be used to determine whether a Resource could be awarded any type of AS. This does not conflict with 4.4.7.2.1(1)(d) or (e). Although (d) and (e) are worded differently, their effect is the same. Linking to a Three-Part Offer and linking to a EOC mean the same thing in the DAM. AS awards will always be within the stated limits.
66 | Reliant (M.Wagner) | p. 45, Sec. 3.3.8, VA8 | Up to 5 sets of capacity offers: Rejected if more than 5 sets [Reliant: What is the limit of capacity offers for combined cycle units? Is each configuration limited to 5 sets of capacity offers?] | Clarification Provided | J.Gilbertson | Yes. Each configuration is treated as if it is a separate Resource. Each Resource has up to 5 sets of capacity offers. See document Ancillary Service Offer Modeling.doc.
67 | Reliant (M.Wagner) | p. 45, Sec. 3.3.8, VA8 | k. Multi-Hour Block Indicator: AS Offer shall be rejected if indicator is Multi-Hour Block for Generation Resource. Default is not a “Multi-Hour Block”. [Reliant: what is this limit for? Do you mean that an AS offer has to be hour by hour (and that an entity cannot offer AS only if it is taken for a block of hours), but that a Resource can offer AS for more than one hour?] | Clarification Provided | J.Gilbertson | This allows for submissions that include repetition of the same data submitted over multiple hours. See document Explanation of Market Submission Items.doc.
68 | Reliant (M.Wagner) | p. 46, Sec. 3.3.8, VA8 | n. Overlapping AS Offers for the particular AS Type shall be rejected in full. [Reliant: What does this mean? Since AS offers are Resource specific, does this mean offers for the same MW of capacity from the same Resource? And if so, how would this be enforced since Protocols allow for the same capacity to be offered for more than one service as part of DAM? See 4.4.7.2.1(1)(c)] | Clarification Provided | J.Gilbertson | Please see response to item 137 - AS Offers, and also see document Explanation of Market Submission Items.doc.
17 | TXU | p. 44, Sec. 3.3.8, VA8 | n. Overlapping AS Offers for the particular AS Type shall be rejected in full.TXU: Why? | Clarification Provided | J.Gilbertson | Please see response to item 137 - AS Offers, and also see document Explanation of Market Submission Items.doc.
137 | GP&L (R.Hoeinghaus) | p. 43, Sec. 3.3.8, VA8 |  | Clarification Provided | J.Gilbertson | Agreed. In this requirement sentence, one “AS Offer” refers to up to 5 sets of capacity offers, each capacity containing a price for each type of AS, which may be effective for more than one contiguous hour. Overlap refers to a new offer for a Resource for which an “AS Offer” (as defined here) already exists. See document Ancillary Service Offer Modeling.doc.
69 | Reliant (M.Wagner) | p. 46, Sec. 3.3.8, VA8 | - Reliant: If ERCOT intends to reject QSE bids on the basis of credit, a credit limit failure error must be generated for each QSE ---with the dollar value that is allowable—when a QSE’s bids exceed the credit limit. Recommend that this occur as part of bid validation.] | Clarification Provided* | J.Gilbertson | Agreed. This will be added to the credit requirement CR1.
70 | Reliant (M.Wagner) | p. 47, Sec. 3.3.9, VA9 | 1. The first validation check shall take place when an AS Trade is reported submitted to ERCOT. | Accepted | J.Gilbertson
18 | TXU | p. 46, Sec. 3.3.9, VA9 2.e | e. Trade ID TXU: New Requirement? There is nothing in the existing ERCOT Market for exchanging TradeIDs. Doesn’t seem to be a plausible expectation. | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
151 | ERCOT | p. 41, Sec. 3.3.8, VA8 | 3.3.8 Does not seem to contemplate Responsive Reserve. If Responsive Reserve is suppose to be captured somewhere else – it does not appear in the document. | Rejected |  | 3.3.8 does mention Responsive Reserves as part of the On-line AS group. We are not aware of any specific missing validation requirements.
71 | Reliant (M.Wagner) | p. 47, Sec. 3.3.9, VA9 2.e | e. Trade ID [Reliant: would ERCOT assign this ID? If not, how would ERCOT validate it?] | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
19 | TXU | p. 46, Sec. 3.3.9, VA9 |  | Clarification Provided | J.Gilbertson | The requirements follow the Nodal Protocols (4.4.1.1, 4.4.2.1, 4.4.7.3.1): 1. The trade is reported by "a QSE" 2. Must be confirmed by both QSEs 3. The QSE that reports the trade is "deemed to have confirmed it …" Also please see document Explanation of Market Submission Items.doc.
72 | Reliant (M.Wagner) | p. 47, Sec. 3.3.9, VA9 |  | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
20 | TXU | p. 46, Sec. 3.3.9, VA9 |  | Clarification Provided | J.Gilbertson | 6.4.1(4) states that a QSE may submit and update AS Trades during the Adjustment Period.
73 | Reliant (M.Wagner) | p. 49, Sec. 3.3.10, VA10 | f. Start Date equals End Date [Reliant: don’t understand this validation—could you please explain it a bit?] | Clarification Provided* | J.Gilbertson | Since there is date information included in the start time and end time, the date component of both the start and end time should be equal. Hours can be different for all offers and bids. Only Resource-specific offers are not allowed to overlap. DAM Requirements document will be updated: Change 6 from "Submission of all DAM Offers and Bids shall..." "Each DAM Offer and Bid shall..." See document Explanation of Market Submission Items.doc.
21 | TXU (R.Spangler) | p. 48, Sec. 3.3.10, VA10 | j. Offer Curve Price ($/MWh) and Quantity (MW) pairs – limit of 10 TXU: While the Protocols are not clear on the following, we believe that if the first Price, Quantity pair (P,Q) is not at a quantity = LSL or LASL for the Resource then the energy offer curve curve should be extended to cover the quantity range from LSL or LASL to the Q in the first offered (P,Q) at Price P from this pair. The extension does not change the 10 pair limit. The reference to LASL is included here to cover the situation in which the Resource is providing Reg Down. A similar calculation based on the next highest offered pair may be needed if the Resource offered Reg Dn for co-optimization and was struck. Rejected if any price is not within range of -$250/MWh to $1,000/MWh TXU: not needed if the following check is performed. Rejected if any price is not within the range of the resource-specific price floors and caps | Clarification Provided | J.Gilbertson | This extension behavior is not specified in the Protocols, and this extension rule is also not consistent with extension of the curve in Real-Time. Requirement CE4 states that the awarded amount will not be lower than the first quantity point. Price limit: This is true if Resource-Specific floors and caps exist and their values are limited to the -250 to 1000 range. However, the Protocols do not specify any resource-specific floors or caps, only that the software have the ability to enter them [4.4.9.3.1(2)] | Q1: This extension behavior is not specified in the Protocols, and this extension rule is also not consistent with extension of the curve in Real-Time. Requirement CE4 states that the awarded amount will not be lower than the first quantity point. Q2: Price limit: Protocol did not specify how to check the price range if Resource-specific floors or caps exist. ERCOT assumes that both ranges will be respected. However, if the prority is for resource-specific range (if exists) over the general one , Validation rules of DAM requirement for offer curve need be revised. [Protocol 4.4.9.3.1(2)]
22 | TXU | p. 48, Sec. 3.3.10, VA10 | l. Overlapping Three-Part Supply Offers shall be rejected in full. TXU: Submissions should overwrite pre-existing offers | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
74 | Reliant (M.Wagner) | p. 49, Sec. 3.3.10, VA10 | l. Overlapping Three-Part Supply Offers shall be rejected in full. [Reliant: could you explain this a little bit more, please?] | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
23 | TXU | p. 50, Sec. 3.3.11, VA11 | j. Time of submission: Submissions for the Operating Day after the specified DAM market deadline shall be applicable for the next DAM day TXU: Constrained by Expiration Date | Accepted | J.Gilbertson
75 | Reliant (M.Wagner) | p. 51, Sec. 3.3.11, VA11 | - Registration Data (QSE information, Settlement Points information) | Accepted | J.Gilbertson | Delete "s" in "Points"
143 | REP Segment (J. Reynolds) | p. 47, Sec. 3.3.12, VA12 | 3.3.12- VA 12 Requirement 2 f. " Last Hour: Rejected if earlier than first hour" - Should this be "earlier or same as first hour" --?? | Clarification Provided | J.Gilbertson | No, a bid where first hour = last hour is a valid one hour bid.
24 | TXU (R.Spangler) | p. 51, Sec. 3.3.12, VA12 | j. Curve Price ($/MWh) and Quantity (MW) pairs – limit of 10 Rejected if pairs are not entirely monotonically non-increasing TXU: Insert “If the first price-quantity pair is greater than zero, the first price-quantity pair price will be extended to cover the range between zero and the first price-quantity pair quantity. This does not affect the 10 pair limit.” Note, this is a copy from Requirement CE4, item 8i. We believe that this is worth noting here along with the caveat that this does not affect the 10 pair limit. | Accepted | J.Gilbertson | Confirmed this is in requirement CE4 and we can add this to VA12 for clarification. | Confirmed this is in requirement CE4 and we will add this to VA12 for clarification.
25 | TXU | p. 55, Sec. 3.3.14, VA14 | 5. A QSE representing a Resource that has a Resource Status of ONTEST must self-commit the Resource and must submit an Output Schedule for the Resource. TXU: What happens first? How is this enforced? Should COP be rejected? Or Offers removed? Or should a message be issued notifying the QSE of the inconsistency? | Clarification Provided | J.Gilbertson | COP is used as a reference for all validation. Hence if the QSE want to update the data then it needs to update COP first. For example: QSE has submitted an Energy Offer Curve and wants to change the status to ONTEST and submit and Output Schedule. When the QSE changes the COP entry, COP validation will give a warning message that the Resource has an Energy Offer Curve and it is required to have an Output Schedule if the status is ONTEST [refer FR29 in Requirement Specification for Overall MMS System and Other Process]. QSE will then withdraw the Energy Offer Curve and submit an Output Schedule.
26 | TXU | p. 55, Sec. 3.3.14, VA14 | 7. A QSE representing a Resource that has an Energy Offer Curve valid for an hour of the COP, cannot designate a Resource Status of ONTEST, ONOS or ONDSR for that hour for that Resource. TXU: What happens first? How is this enforced? Should COP be rejected? Or Offers removed? Or should a message be issued notifying the QSE of the inconsistency? | Clarification Provided | J.Gilbertson | COP is used as a reference for all validation. Hence if the QSE want to update the data then it needs to update COP first. For example: QSE has submitted an Energy Offer Curve and wants to change the status to ONTEST and submit and Output Schedule. When the QSE changes the COP entry, COP validation will give a warning message that the Resource has an Energy Offer Curve and it is required to have an Output Schedule if the status is ONTEST [refer FR29 in Requirement Specification for Overall MMS System and Other Process]. QSE will then withdraw the Energy Offer Curve and submit an Output Schedule.
76 | Reliant (M.Wagner) | p. 55, Sec. 3.3.14, VA14 | 8. If the COP is modified in the Adjustment period for AS, HSL/LSL and/or status changes, the COP change shall be alarmedmust trigger(flag) an alarm condition for to the ERCOT Operator. Refer to section AE2 for further details. | Accepted | J.Gilbertson
116 | LCRA (G.Graham) | p. 53, Sec. 3.3.14, VA14 | Can a Resource with a status of ONOS or ONOSREG still provide NSRS? Since they cannot have an energy offer curve along with their ONOS or ONOSREG COP, what value is used for dispatch basis? | Clarification Provided | J.Gilbertson | Resources with Output Schedule can provide Non-Spin. When Non-Spin is deployed by Operator, the Output Schedule for non-DSRs will be increased by the Non-Spin responsibility of the Resource (Limited by ramp rate) since the process submitted for TAC approval says that Non-Spin deployment from Generation Resource will be done “All or None”. [Refer FR74 in Requirement Specification for SCED and Real-Time MMS Process]. ERCOT will send a signal to QSE to indicate deployment of Non-Spin. For DSRs providing Non-Spin, on deployment of Non-Spin, the DSR’s QSE shall adjust its Resource Output Schedule to reflect the amount of deployment. Please refer to “Whitepaper - Non-Spin deployment Notification and Availability” submitted to TPTF for more information. (This doesn't concern DAM) | This issue is related to Real-Time. Please refer to Real-Time document.
117 | LCRA (G.Graham) | p. 53, Sec. 3.3.14, VA1514 |  | Clarification Provided | J.Gilbertson | Both options are acceptable. We plan on determining the most appropriate method during the detailed design process.
27 | TXU (R.Spangler) | p. 57, Sec. 3.4.1, CR1 | 1. ERCOTMMS-DAM (TXU: It is not clear from this discussion whether it is CMM or MMS that is performing the calculations described below; however, logically it appears to be an MMS function) calculates credit exposure for bids and offers in the DAM as follows: | Clarification Provided | J.Gilbertson | MMS will calculate the exposure. CMM will calculate the limit and provide to MMS.
77 | Reliant (M.Wagner) | p. 56, Sec. 3.4.1, CR1 1.h |  | Clarification Provided* | J.Gilbertson | If the credit limit is sent on Friday evening, and not again until after the DAM is run on Monday, MMS must use that value for the DAMs that are executed on Saturday, Sunday, and Monday (Operating Days Sunday, Monday, Tuesday) DAM Requirements document will be updated: Simpler wording that credit exposure will be cumulative until new credit limit is received. Delete all of h and change i (new h) to say: "If no new credit limit is received from the Credit system, the credit check validation shall look at each QSE’s DAM activities cumulatively until it receives a new credit limit for that QSE from the Credit system."
28 | TXU (R.Spangler) | p. 57, Sec. 3.4.1, CR1 1.i | i. If athe weekday is a Monday, or it is a holiday (including Saturday and Sunday), the credit check validation shall look at each QSE’s DAM activities cumulatively until it receives a new credit limit for that QSE from the Credit system. TXU: Based on the CMM Business Requirements the foregoing will occur every weekend for the Saturday, Sunday and Monday DAMs. | Clarification Provided* | J.Gilbertson | If the credit limit is sent on Friday evening, and not again until after the DAM is run on Monday, MMS must use that value for the DAMs that are executed on Saturday, Sunday, and Monday (Operating Days Sunday, Monday, Tuesday) DAM Requirement document will be updated:Simpler wording that credit exposure will be cumulative until new credit limit is received. Delete all of h and change i (new h) to say: "If no new credit limit is received from the Credit system, the credit check validation shall look at each QSE’s DAM activities cumulatively until it receives a new credit limit for that QSE from the Credit system."
78 | Reliant (M.Wagner) | p. 57, Sec. 3.4.1, CR1 Outputs | - If QSE’s credit exposure for DAM bids and Offers is more than the QSE’s Credit limit for DAM: - Reject all Bids and Offers of that QSE - Notify that QSEs violated their credit limit - [Reliant: Notify QSEs of the credit limit value that created violation.] | Accepted | J.Gilbertson | Agreed. This will be added to the credit requirement CR1.
79 | Reliant (M.Wagner) | p. 57, Sec. 3.5.1, SC1 | 4. In the AS Insufficiency Alert sent out to QSEs, the MMS shall inform the market the available quantity of that type AS and the total of associated linked offers. [Reliant: Is the notification here about what is available or what is needed—and associated MW?] | Clarification Provided | J.Gilbertson | The notification is about what is available. The DAM Clearing Engine will be used to perform the AS sufficiency check in a study mode. The cleared quantities of each AS from the study mode is also available for inclusion in the AS Insufficiency Alert. If the market feels the report should contain the amount needed, this should be added as a new requirement. However, because Resources may bid the same quantity for several AS types (both before and after the AS Insufficiency Check is run), it is still not guaranteed that the entire AS Plan will be cleared even if all the uncleared amounts as specified in the Alert are offered.
118 | LCRA (G.Graham) | p. 57, Sec. 3.5.2, SC2 |  | Accepted | J.Gilbertson
80 | Reliant (M.Wagner) | p. 59, Sec. 3.5.3, SC3 | Additional AS Offers can be requested by ERCOT prior to executing the DAM when ERCOT believes there willshall be insufficient AS, as determined by the AS Insufficiency Check (SC1). The additional offers are subject to additional validation criteria, to prevent the price on existing AS Offers from being increased. The MMS shall receive and validate these offers. | Accepted | J.Gilbertson
81 | Reliant (M.Wagner) | p. 59, Sec. 3.5.3, SC3 |  | Accepted | J.Gilbertson | (e) was intended to cover 4.5.2(1)(b)(i)(A) but is inaccurate. Change to say "e. New AS Offers shall be rejected if the lowest priced quantity of the previously submitted offers is are not resubmitted. " | (e) was intended to cover 4.5.2(1)(b)(i)(A) but is inaccurate. The language will be refined.
82 | Reliant (M.Wagner) | p. 60, Sec. 3.5.3, SC3 | e. New AS Offers shall be rejected if the previously submitted offers are not resubmitted. [Reliant: why? Where is the Protocol citation for this criterion?] | Accepted | J.Gilbertson | (e) was intended to cover 4.5.2(1)(b)(i)(A) but is inaccurate. Change to say "e. New AS Offers shall be rejected if the lowest priced quantity of the previously submitted offers is are not resubmitted. " | (e) was intended to cover 4.5.2(1)(b)(i)(A) but is inaccurate. The language will be refined.
158 | ERCOT | p. 55, Sec. 3.6.1, CF1 | To deternime the deration factor of each oversold element, the total of the positive flows resulted from all outstanding CRRs prior to the DAM execution needs to be calculated in addition to the oversold quantity. | Response |  | Moved to IDA Punch List. Current requirement does not cover the calculation for positive flows from all outstanding CRRs, However, MMS can provide all information to calculated this flow.
83 | Reliant (M.Wagner) | p. 61, Sec. 3.6.1, CF1 |  | Accepted | J.Gilbertson
84 | Reliant (M.Wagner) | p. 61, Sec. 3.6.1, CF1 | CRR owners can be assigned obtain CRRs through CRR auctions, PCRR allocations; McCamey Area Flowgate Rights allocations, or Bilateral contractstransactions. | Accepted | J.Gilbertson
119 | LCRA (S.Siddiqi) | p. 59, Sec. 3.6.1, CF1 | CRR owners Owners can be assigned CRRs through CRR auctions, PCRR allocations; McCamey Area Flowgate Rights allocations, or Bilateral contracts. | Accepted | J.Gilbertson
85 | Reliant (M.Wagner) | p. 61, Sec. 3.6.1, CF1 | 1. The SFT shall model the effect of all assigned CRRs on the Day-Ahead Updated Network Model topology. Day-Ahead Updated Network Model shall be built based on the Normal Ratings of network elements, with Dynamic Ratings based on the expected temperatures for each hour of the next day, and including information from the Outage scheduler system on known outages. | Accepted | J.Gilbertson | New language is OK; however Dynamic Ratings are computed by EMS; MMS will not use weather data to compute Dynamic Ratings, but will use the Dynamic Ratings provided by EMS
86 | Reliant (M.Wagner) | p. 61, Sec. 3.6.1, CF1 | 2. Assigned CRRs that have a source and/or sink at Load Zones or Hubs shall be allocated to electrical buses based on Load Distribution Factor as determined by the State Estimator hourly distribution for the seven days before the Operating Day. [Reliant: may need to discuss exactly what this means at TPTF.] and Hub Distribution Factors, as defined in Protocols 3,5,2, respectively. Protocols 4.5.1 states: |  | J.Gilbertson | Reliant wants to discuss at TPTF.
87 | Reliant (M.Wagner) | p. 62, Sec. 3.6.1, CF1 |  | Clarification Provided | J.Gilbertson | If Network Topology processor determines that a Nodal “Electrical Bus” is not in an energized electrical island, then this “Electrical Bus” is a dead Electrical Bus” The treatment of load buses that are "dead" will be further clarified during detailed design.
88 | Reliant (M.Wagner) | p. 62, Sec. 3.6.1, CF1 | Despite the fact that this is an “auction” reference, the way the FGRs are modeled in the system for DA analysis and the auction should be the same.] | Accepted | J.Gilbertson
120 | LCRA (S.Siddiqi) | p. 59, Sec. 3.6.1, CF1 | The SFT shall also consider the Contingency List, RAP/SPS and Generic constraints. For base case, the SFT shall use non-linear DC Power Flow for PTP obligations and incremental DC Power Flow for PTP options. For Contingency cases, the SFT shall use incremental DC Power Flow. What are non-linear DC Power Flow and incremental DC Power Flow? | Clarification Provided | J.Gilbertson | The non-linear DC Power Flow is a derivative of the Decoupled Power Flow. It solves iteratively only the real power part of the Power Flow problem by assuming a constant, flat voltage profile across the entire network. It has proven to be a very reliable tool and it is extensively used in other ISOs/RTOs across the US and elsewhere. The incremental power flow is a non-iterative solution of the real power problem. It solves the following system of equations DP = [B’] DA Where [B’] is the real matrix from the Decoupled Power Flow and DP and DA are the vectors of bus injection changes and bus angle changes
89 | Reliant (M.Wagner) | p. 62, Sec. 3.6.1, CF1 | 8. With the CRR obligations imposed on the network, if the power flow (nonlinear DC) fails to converge, the process shall stop to allow ERCOT Operators to remedy the possible data problems. [Reliant: what would they change? Would there be a log of this and would the log be provided to Market Participants?] The CRR options shall be solved via incremental model.[Reliant: what is an incremental model?] As such, there is no convergence issue. [Reliant: unclear about how the test is “simultaneous feasibility” when there is a sequential evaluation by type of CRR. Could we please discuss this at TPTF? The process set forth here seems to indicate that CRR options are evaluated sequentially—meaning that the first ones evaluated might not be ‘derated’ but that later ones, merely by virtue of the order in which they were evaluated might suffer deration. The ‘simultaneous feasibility’ goal is to look at all of the CRRs at the same time and to derate based on their impact on the binding constraint. Sequential evaluation will not provide the information required for deration.] | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc. Also see Comment #120
121 | LCRA (S.Siddiqi) | p. 60, Sec. 3.6.1, CF1 | With the CRR obligations imposed on the network, if the power flow (nonlinear DC) fails to converge [could it fail to converge if PTP Obligations are oversold?], the process shall stop to allow ERCOT Operators to remedy the possible data problems. The CRR options shall be solved via incremental model. As such, there is no convergence issue. | Clarification Provided | J.Gilbertson | Theoretically yes, but the oversold amount would have to be very large. Experience from other jurisdictions has shown that the Non-linear DC Power Flow is extremely robust and its failure normally indicates a serious network modeling problem. The program automatically outputs the divergent buses together with their connections and injections for operator’s review
90 | Reliant (M.Wagner) | p. 63, Sec. 3.6.1, CF1 |  | 1st change Accepted 2nd Change Rejected | J.Gilbertson | Dynamic Ratings will be computed by EMS. MMS does not require weather data. First line is accepted and second line is rejected.
91 | Reliant (M.Wagner) | p. 64, Sec. 3.6.1, CF1 |  | 1st comment Rejected 2nd comment: Clarification Provided | J.Gilbertson | 1st comment is not in Nodal Protocols 2nd comment: May or may not be physical transmission element limit. For Generic constraint it is the Generic constraint limit.
122 | LCRA (S.Siddiqi) | p. 61, Sec. 3.6.1, CF1 |  | Clarification Provided* | J.Gilbertson | Modify to post monitored elements and contingency IDs. Note that MPs can find the contingency elements based on the contingency ID and contingency lists. It will be too many data to publish the contingency elements.
92 | Reliant (M.Wagner) | p. 65, Sec. 3.7.1, DC1 |  | Accepted | J.Gilbertson | Agree with distribution factor statement. EMS will calculate Dynamic Ratings.
93 | Reliant (M.Wagner) | p. 66, Sec. 3.7.1, DC1 |  | Clarification Provided | J.Gilbertson | No. See CRR Related Issues in DAM.doc.
29 | TXU | p. 65, Sec. 3.8.1, CE1 | 2. The MMS shall provide an option to allow ERCOT to change this distribution. TXU: Change of the distribution factors should be posted | Accepted | J.Gilbertson | We will add the modified distribution factors as output to the requirement.
94 | Reliant (M.Wagner) | p. 66, Sec. 3.8.1, CE1 | 6. For offers, bids, and sources and sinks of CRRs at bus and the bus is dead, if the disconnected load is defined with a load rollover scheme, the disconnected load shall be rolled over accordingly. If not, the load shall be dropped. If the target bus of the load rollover is a dead bus, then the fraction of the load rollover to this bus shall be dropped. [Reliant: see comments above on this issue.] | Clarification Provided | J.Gilbertson | If Network Topology processor determines that a Nodal “Electrical Bus” is not in an energized electrical island, then this “Electrical Bus” is a dead Electrical Bus” The treatment of load buses that are "dead" will be further clarified during detailed design.
123 | LCRA (S.Siddiqi) | p. 64, Sec. 3.8.2, CE2 |  | Clarification Provided | J.Gilbertson | Agreed on assumptions. DAM will recognize Resource Status OUT and EMR, and Resources specified as outages in the Outage Scheduler as unavailable. DAM will recognize ONEMR status as On-line. All other Resource Status codes will be ignored by DAM for commitment decisions. So, if unit is planned out at 2000 and COP and /or OS shows this, DAM will recognize it; Agreed on assumptions. DAM will recognize Resource Status OUT and EMR, and Resources specified as outages in the Outage Scheduler as unavailable. DAM will recognize ONEMR status as On-line. All other Resource Status codes will be ignored by DAM for commitment decisions. So, if unit is planned out at 2000 and COP and /or OS shows this, DAM will recognize it | Agreed on assumptions. All Resource Status codes for the next operating Day will be ignored by DAM for commitment decisions. So, if unit is planned out at 2000 for next Operating Day in COP, DAM will not recognize it;
30 | TXU | p. 66, Sec. 3.8.2, CE2 | 1. DAM shall use the historical commitment data, the On-line and Off-line status for the current Operating hour from EMS and the COP status for remaining hours of the current Operating Day to project the initial commitment status at the beginning of the next Operating Day. TXU: What is the COP used for? | Clarification Provided | J.Gilbertson | Resource's commitment status in COP between current time and DAM study start time is used to determine the unit's initial status in the DAM. For example assume current time is 10:00 AM, if a unit's current status is "ON" (as shown in EMS) and the unit has commitment status "ON" from HE12 to HE19 and "OFF" from HE20 in COPS, then unit's initial commitment status is "OFF" for 5 hours (HE20 to HE24) for DAM study
95 | Reliant (M.Wagner) | p. 68, Sec. 3.8.2, CE2 |  |  | J.Gilbertson | No question
96 | Reliant (M.Wagner) | p. 68, Sec. 3.8.3, CE3 |  | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc.
124 | LCRA (S.Siddiqi) | p. 65, Sec. 3.8.3, CE3 3.a. | - Branch Group constraints - protect the ERCOT Transmission Grid against transient instability, dynamic stability or voltage collapse. Can we use same terminology as CRR docs? Are these Non-thermal constraints? Then what are Generic constraints? Aren’t Generic constraints a subset of these constraints? | Clarification Provided* | J.Gilbertson | Branch Group constraints are a type of generic constraints. DAM Requirements documents will be updated accordingly.
97 | Reliant (M.Wagner) | p. 69, Sec. 3.8.3, CE3 4.a |  | Accepted | J.Gilbertson | No comment on highlighted area. Accepted word addition.
98 | Reliant (M.Wagner) | p. 69, Sec. 3.8.3, CE3 4.d |  | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc.
31 | TXU | p. 68, Sec. 3.8.4, CE4 |  | Clarification Provided* | J.Gilbertson | Revised language. 2. The Day-Ahead Locational Marginal Price (LMP) for each Electrical Bus for each hour of the Operating Day is the Shadow Price for that Electrical Bus for the hour as determined by the DAM Algorithm. Block offers shall not set the LMP.
125 | LCRA (S.Siddiqi) | p. 68, Sec. 3.8.4, CE4 8.f | f. For any offer, except Three-Part Supply Offers, if First Hour and Last Hour are different, the offer shall be treated as a multi-hour block offer which means the cleared quantity shall be the same for all the hours in the block, Does this mean QSEs have to submit one offer for each hour? Is it better to have a block offer flag? | Clarification Provided | J.Gilbertson | See document Explanation of Market Submission Items.doc.
99 | Reliant (M.Wagner) | p. 73, Sec. 3.8.4, CE4 8.f, 8.g | f. For any offer, except Three-Part Supply Offers, if First Hour and Last Hour are different, the offer shall be treated as a multi-hour block offer which means the cleared quantity shall be the same for all the hours in the block, g. For a Three-Part Supply Offer, there is not a multi-hour offer even if the First Hour and the Last Hour are different for the Three-Part Supply offer. [Reliant: not clear what this means.] | Clarification Provided* | J.Gilbertson | ERCOT will change the requirement to read: "f. For any offer/bid, except Three-Part Supply Offers, DAM Energy-Only Offers with offer curves, and DAM Energy Bids with bid curves, if the First Hour and Last Hour are different, the offer/bid shall be treated as a multi-hour block offer/bid which means the cleared quantity shall be the same for all the hours in the block. g. For a Three-Part Supply Offer, DAM Energy-Only Offers with offer curves, and DAM Energy Bids with bid curves, the award may be a different quantity for each hour (i.e. there is not a multi-hour offer) even if the First Hour and the Last Hour are different for the Three-Part Supply offer/bid." Also See document Explanation of Market Submission Items.doc.
126 | LCRA (S.Siddiqi) | p. 68, Sec. 3.8.4, CE4 8.h | h. For a Three-Part Supply Offer, if the first price-quantity pair is greater than LSL, the Resource will not be awarded a quantity less than the quantity of the first price-quantity pair. What does this mean for Min Energy offer? Does this mean Min Energy MW is equal to first price-quantity quantity? This may be a problem since Min Energy Offer is capped based on LSL. | Clarification Provided | J.Gilbertson | No, Minimum-Energy MW is still equal to LSL.
32 | TXU | p. 70, Sec. 3.8.4, CE4 8.h | h. For a Three-Part Supply Offer, if the first price-quantity pair is greater than LSL, the Resource will not be awarded a quantity less than the quantity of the first price-quantity pair.TXU: Is this true? Isn’t the curve adjusted? | Clarification Provided | J.Gilbertson | This extension behavior is not specified in the Protocols, and this extension rule is also not consistent with extension of the curve in Real-Time. Requirement CE4 states that the awarded amount will not be lower than the first quantity point. Price limit: This is true if Resource-Specific floors and caps exist and their values are limited to the -250 to 1000 range. However, the Protocols do not specify any resource-specific floors or caps, only that the software have the ability to enter them [4.4.9.3.1(2)] | This extension behavior is not specified in the Protocols, and this extension rule is also not consistent with extension of the curve in Real-Time. Requirement CE4 states that the awarded amount will not be lower than the first quantity point.
100 | Reliant (M.Wagner) | p. 73, Sec. 3.8.4, CE4 8.r |  | Clarification Provided | J.Gilbertson | Resource's commitment status in COP between current time and DAM study start time is used to determine the unit's initial status in the DAM. For example assume current time is 10:00 AM, if a unit's current status is "ON" (as shown in EMS) and the unit has commitment status "ON" from HE12 to HE19 and "OFF" from HE20 in COPS, then unit's initial commitment status is "OFF" for 5 hours (HE20 to HE24) for DAM study
127 | LCRA (S.Siddiqi) | p. 69, Sec. 3.8.4, CE4 9.e | e. Resource output constraints (Resource Maximum and minimum constraints.): Are the use of inclusive and exclusive consistent with our discussion on them? | Clarification Provided | J.Gilbertson | See document Ancillary Service Offer Modeling.doc.
128 | LCRA (S.Siddiqi) | p. 70, Sec. 3.8.4, CE4 9.e. | - If only AS is offered, then the dispatch of On-line reserves shall require that the resource be considered On-line with an energy dispatch of 0 MW. If Off-line Non-Spin is dispatched then the resource shall be considered Off-Line. The commitment schedule shall obey the minimum run time and minimum down time constraints.When only AS is offered, it may be awarded in any hour independent of any other hour. It’s the QSE’s responsibility to commit the unit to meet these awards. The QSE always has the option of linking AS offers to 3-part offers. | Rejected | J.Gilbertson | This requirement exists so that minimum up and down time requirements make sense when units bid only AS for some hours during the day and bid energy for other hours.
129 | LCRA (S.Siddiqi) | p. 71, Sec. 3.8.4, CE4 11.e | e. Fixed Block AS Offers: Fixed Block Ancillary Service Offers for a Load Resource – blocks shall not be cleared unless the entire quantity block can be awarded and the resulting MCPC is greater than the block offer price and, for linked AS Offers, all of the awarded AS shall be assigned to a single service. | Rejected | J.Gilbertson | See document Pricing Issues with Fixed Quantity Block Offers and Bids in DAM.doc.
101 | Reliant (M.Wagner) | p. 76, Sec. 3.8.4, CE4 11.h | h. Offers of PTP Options declared to settle in RT – PTP Options shall be less than or equal to the Limits determined by the CRR Option Derating. [Reliant: So will ERCOT automatically enforce this condition? If so will QSEs holding PTP Options to settle in RT be informed? How? If the QSEs are to limit their offers to this amount (which, given the timing of the processes, doesn’t seem possible before the DAM scheduling deadline) this should be stated.] | Clarification Provided | J.Gilbertson | See CRR Related Issues in DAM.doc.
102 | Reliant (M.Wagner) | p. 76, Sec. 3.8.4, CE4 11.l | l. The DAM shall not consider any Self-Schedule energy. [Reliant: if the QSEs employing self schedules do not submit 3-part offers or energy only offers, will ERCOT just ignore all of these Resources? Do we need an NPRR to ask for Self Schedules at the same time that DAM offers and bids are due?] | Clarification Provided | J.Gilbertson | The DAM is to match bids and offers and so does not consider self-scheduling resources.
33 | TXU | p. 74, Sec. 3.8.6, CE6 | 1. DAM shall apply penalty factors to violations of the power balance and security constraints to the NCUC objective function in addition to the offer-based cost. The penalty factors shall be configurable by the authorized ERCOT Operators. TXU: Penalty factors and changes thereto shall be posted to the MIS. | Accepted | J.Gilbertson | We will add penalty factors to CE6 output section.
103 | Reliant (M.Wagner) | p. 79, Sec. 3.8.8, CE8 |  | Accepted | J.Gilbertson
130 | LCRA (S.Siddiqi) | p. 76, Sec. 3.8.9, CE9 |  | Clarification Provided* | J.Gilbertson | Modify to post monitored elements and contingency IDs. Note that MPs can find the contingency elements based on the contingency ID and contingency lists. It will be too many data to publish the contingency elements.
104 | Reliant (M.Wagner) | p. 85, Sec. 3.9.3, AE3 |  | Clarification Provided | J.Gilbertson | No, HASL and LASL are not part of COP. HASL and LASL can be determined from COP (AS schedule and HSL/LSL limits). The COP monitor will alarm on a change to the AS schedule which accomplishes the same thing.
138 | GP&L (R.Hoeinghaus) | p. 77, Sec. 3.9.3, AE3 |  | Clarification Provided | J.Gilbertson | No, ERCOT understands this protocol to mean that QSE will update their COP for the remainder of the day(s) when there is a Resource capability change.
105 | Reliant (M.Wagner) | p. 85, Sec. 3.9.3, AE3 |  | Accepted | J.Gilbertson
106 | Reliant (M.Wagner) | p. 86, Sec. 3.9.4, AE4 |  | Clarification Provided* | J.Gilbertson | Yes. DAM Requirements document will be changed accordingly.
139 | GP&L (R.Hoeinghaus) | p. 78, Sec. 3.9.4, AE4 |  | Clarification Provided | J.Gilbertson | The DEF retrieves the savecase of HRUC. It doesn't model DSR in the RUC. | The DEF retrieves the savecase of HRUC. DSR resource is treated as a normal On-Line resource in the RUC. DEF models DSR resource in the same manner as RUC.
107 | Reliant (M.Wagner) | p. 77, Sec. 3.9.4, AE4 | 7. Following convergence of the NCUC and NSM iteration, any infeasibility shall be reported. A suggestion plan shall be prepared giving the resources that can be used to relieve the transmission constraints based on the shift factors calculated by NSM. [Reliant: This would be provided to the ERCOT Operator, right?] | Clarification Provided | J.Gilbertson | Yes, it will be provided to the ERCOT operator.
108 | Reliant (M.Wagner) | p. 77, Sec. 3.9.4, AE4 |  | Accepted | J.Gilbertson | Yes, but the Deliverability Function could conceivably be run even without changes to COP. More than likely there will be multiple changes to COP when this function is run.
152 | ERCOT | p. 78, Sec 3.10, SASM | The document does not seem to provide any functional requirements for Failure to Provide, and Replaced Amounts. | Response |  | Moved to IDA Punch List. As more clarity required for resolution. Seems to be an interface/integration issue. We suppose that this comment is about SASM. If the SASM is opened for the Failure to Provide by a QSE or Undeliverable by a QSE . The reason and QSE information will be past to settlement. It is not clear about the meaning of "Replaced Amounts".
140 | GP&L (R.Hoeinghaus) | p. 81, Sec. 3.10.2, SA2 |  | Clarification Provided* | J.Gilbertson | Req 1b - This is a direct Protocol quote [6.4.8.2.1(1)(c). Requirements c and d in SA2 are based on 6.4.8.2.1(1)(a) and (b). The words “for SASM” are misleading and have been replaced by “in the Adjustment Period.” As revised, there is no conflict within 6.4.8.2.1, however a conflict still exists with the timeline in 6.4.8.2. The validation rules apply for AS offers in the Adjustment Period, but once ERCOT issues a notice, Offers submitted after the notice are not considered for that SASM. DAM Requirement document will be updated: Change (c) and (d) to read: "AS Offers resubmitted for SASM in the Adjustment Period shall be..."
109 | Reliant (M.Wagner) | p. 93, Sec. 4.1.1 |  |  | J.Gilbertson | No question
131 | LCRA (S.Siddiqi) | p. 106, Appendix 1 Subject to: 13 |  | Accepted | J.Gilbertson
132 | LCRA (S.Siddiqi) | p. 113, Appendix 1 |  | Accepted | J.Gilbertson | [ABB/MA] AS MCPC at interval is SPDRS,t, SPURS,t, SPRRS,t, SPNSRS,t for Regulation Down, Regulation Up, Responsive Reserve, and Non-Spin Reserve, respectively where SPDRS,t, SPURS,t, SPRRS,t, SPNSRS,t are the shadow prices of the respective AS requirement constraints.
133 | LCRA (S.Siddiqi) | p. 122, Appendix 4 2. CRR quantity constraint |  | Accepted | J.Gilbertson
134 | LCRA (S.Siddiqi) | p. 122, Appendix 4 2. CRR quantity constraint |  | Accepted | J.Gilbertson