## MIS_MP Comments
Document Name: TN MIS_67E030_01 Requirements
# | Issuing Entity | Name | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason
1 | Power & Gas Consulting | J. Reynolds | Sec. 1.2.1 | The text states: "TML content and functionality will not be migrated and will be provided as a separate application with no links to or from MIS Portal…" Comment: Why are there no links from TML and MIS? I am concerned about confusion among Users in going backand forth... | Accepted | MIS Team | We agree. We have re-examined this approach, and now are in agreement that links should exist from each of the portals that are part of the ERCOT web presence. Additionally, we feel that the MIS will actually become the NEW TML, and therefore provide a total solution to avoid confusion.
2 | MIS Team | P. Harris | Sec 1.2.1 | Added the text in bullet 4: "Content from ERCOT.com will not be migrated to the MIS portal, but will be accessible through MIS portal. | Accepted |  | Determination to secure all data on MIS through digital Certificate was made by the ERCOT business owners, but in order to comply with protocols will also make public data accessible in public area as described.
3 | MIS Team | P. Harris | Sec 1.2.2 | Deleted bullet 1 :Public access without authentication for public content | Accepted |  | Determination to secure all data on MIS through digital Certificate was made by the ERCOT business owners, but in order to comply with protocols will also make public data accessible in public area as described.
| IDA | G. Macomber | Sec. 1.2.3 | – what about them saving the url for those that launch in a new window? | Accepted | P Harris | Modified the words to include "as opposed to being accessed through ERCOT.com. Some applications may be linked thru a URL that is linked from the Market Participant client computer.
| IDA | G. Macomber | Sec. 1.2.3 | – information from ERCOT.com can be accessed thru the portal and ERCOT.com will have a link to ERCOT.com, but this reads like ERCOT.com will appear within MIS | Rejected |  | the words say "ERCOT.com can be accessed directly or through the MIS portal.
| IDA | G. Macomber | Sec. 1.2.3 | · TML will be provided as a separate entry point to be accessed directly, not from the MIS portal. – contradicts resolution spreadsheet, MIS will have a link to TML and TML will have a link to MIS, right? | Rejected |  | resolution spreadsheet? No, I don't expect to have or include a link to TML from MIS. TML will continue to be accessed through ERCOT.com.
| IDA | G. Macomber | Sec. 1.2.4 | Appplication launch pad that launches applications | Accepted | P Harris
4 | MIS Team | P. Harris | Sec 1.3 | changed the delivery dates in the schedule due to late signing of SOW | Accepted |  | moved delivery dates for all deliverables out 1 week due to late signing of SOW for Phase 2
| IDA | G. Macomber | Sec. 1.3 | Prototype 1: What functionality will be paper prototyping? | Rejected |  | this is not the document for details of deliverables; this information exists multiple other places.
| IDA | G. Macomber | Sec. 1.3 | prototype 2: at one time didn't this delivery include a click-thru prototype, when will that be delivered? | Accepted |  | yes, this click-thru prototype is part of Prototype 2. Again, this is detail not appropriate to the CSD.
5 | Power & Gas Consulting | J. Reynolds | Sec. 2.1.2.1 | I think it is unclear on the types of users. We had said that persons who are not Market participants (consultants, etc) could access items like transmission data -- after they went through an authentication process. I do not see that type listed. | Accepted | MIS Team | have added this clarification
| IDA | G. Macomber | 2.1.2.1 | Types of users (is this a subsection?) | Rejected | P Harris | no. Supporting data
| IDA | G. Macomber | 2.1.2.1 | I thought we'd agreed that you needed a digitial certificate to access MIS | Accepted | P Harris | yes
| IDA | G. Macomber | 2.1.2.1 | Basic Templates: The MIS portal will only be available to individuals with digital certificates | Accepted | P Harris
| IDA | G. Macomber | 2.2.4 | Security classifications: Is this something for all portlets or only static ones. |  | P Harris | Each portlet means all portlets. Security classifications will be associated with each portlet.
| IDA | G. Macomber | 2.3 | Notification: added ' a subset of the Market Participants' | Accepted | P Harris | good catch
6 | Reliant | M. Moran |  | Where are My Pages stored | Response | MIS Team | the personalization parameters (those selected by the user during MyPage configuration) are stored in a database and used to build the page when requested. No data resides on the client or cache.
7 | MIS Team | P. Harris |  | Added for clarity: In order to gain access to the MIS portal, users must be authenticated. Public data that does not require a digital certificate will be accessible to unauthenticated users through ERCOT.com. In order to avoid necessity for Market Participants to navigate back to ERCOT.com to access public data, that public data required by protocol will also be accessible through the MIS. |  | MIS Team
8 | MIS Team | P. Harris |  | Deleted as correction: Public data that does not require a digital certificate will be accessible to unauthenticated users through ERCOT.com. In order to avoid necessity for Market Participants to navigate back to ERCOT.com to access public data, that public data required by protocol will also be accessible through the MIS. Replaced with: The MIS portal will only be available to Market Participants, who will be able to launch applications, submit market data, and personalize their home pages. |  | MIS Team
9 | MIS Team | P. Harris |  | Delted: USA template modifications do not apply to Public users.
10 | Reliant | M. Moran |  | If we can download data, what is the format? | Response | MIS Team | various. XML, .xlsl, .pdf, csv, HTML. In the case where an extract is being scheduled, the format can be specified.
11 | Reliant | M. Moran |  | I would want a web service or API for any data I can see on the MIS. If there is not one for something I want, I'll have to go back to scraping (I can scraape anthing) | Accepted | MIS Team | that's not very nice!
12 | MIS Team | M. Moran |  | Google for search - excellent choice | Accepted | MIS Team | Thanks!
13 | MIS Team | M. Moran |  | For notificiations and/or other pushed/dynamic data, AJAX is another excellent choice. | Accepted | MIS Team | Great! Score TWO for the MIS team!
14 | MIS Team | M. Moran |  | I don't see how graphical data would be displayed, applets are proabably a good choice. | Accepted | MIS Team | We will use a tool (yet to be determined) to graphically display that data identified for dashports. Applets will also be used where necessary
15 | MIS Team | M. Moran |  | Do we subscribe to pushed/dynamic data? | Accepted | MIS Team | Yes. All data will be available via a subscribable web service through the messaging system
16 | MIS Team | M. Moran |  | I see a lot of potential for the mypages. It goes way beyond being a portal user display/tool. | Accepted | MIS Team | well…..yes, they are conceived so that you can display only that data that you want to see most often
17 | MIS Team | M. Moran |  | I would like to see the inner workings of mypages, from what the user sees in a browser all the way down to the web services that make the data available, published and open. Companies like PCI and Structure could have portal/display/data/whatever access built into their products. | Rejected (for now) |  | When we get further along you are welcome to review all the documentation that ERCOT determines can be shared. Understand there will be security issues in making this backend processing/design available and the project team hasn't developed it yet, but I will ensure that your request is made known to ERCOT web portal support management.
18 |  | M. Moran |  | Companies like PCI and Structure could have portal/display/data/whatever access built into their products. And I could develop some really cool stuff, building it into our scheduling web site. | Accepted |  | right on!
| IDA | G. Macomber | 2.5.1 | . –FR 107 seems to be quite dynamic data, requested refresh rate of every 10 seconds (! May raise some performance questions, are the implications of that refresh rate covered in the conceptual design?). | Agreed, BUT |  | no, not covered here.
| IDA | G. Macomber | 2.7 | add 'or to a specific subroup of MPs | Accepted |  | added
| MIS Team | P. Harris | Sec. 2.7.2 | deleted: . Users without valid credentials are permitted to view public content, |  |  | Only users with credentials (valid digital certificate) will be permitted to access the MIS portal
| IDA | G. Macomber | 2.7.3 | doesn't EIS/EDW also use the information in selecting what to pass back? | Rejected |  | probably, but don't see why that would be noted here…
13 | MIS Team | C. Otten | iii | TOC 1.2.2, Global Change: "System functional capabilities" to "System Functional Capabilities." | Accepted | MIS Team
| IDA | G. Macomber | 3.5 | no additional (TIBCO) license are anticipated. | Accepted | P. Harris | hooray!
| IDA | G. Macomber | 4.8.1 | paper prototypes: include information architecture as an example of core system concepts | Accepted | P. Harris | IF you mean demonstrating how the information is laid out or how it is presented, yes.
| IDA | G. Macomber | 5.3 | – revisit to include items from Application list that are not applications. | Rejected | P. Harris | I'm not sure what this means but the table is intneded to represen the inventory of content and requirements, since this section refers to DATA access traceability.
14 | MIS Team | C. Otten | 6 | Under 1.1., Capitalize "System" in "Market Information System" | Accepted
15 | MIS Team | C. Otten | 6 | Under 1.1, Change: "is to provide a single point of access for Market Participants, PUCT, and ERCOT staff to Nodal market information, and to ERCOT market-facing applications." to "is to provide a single point of access for Market Participants, PUCT, and ERCOT staff to Nodal market information, as well as ERCOT market-facing applications." | Accepted | MIS Team
16 | MIS Team | C. Otten | 6 | Under 1.1., Add periods to the 3 bullet points. | Accepted | MIS Team
17 | MIS Team | C. Otten | 6 | Under 1.2, Global Change: Add a comma after TIBCO Portal Builder, version 5.2 and before all "version x" fragments. | Accepted | MIS Team
18 | MIS Team | C. Otten | 6 | Under 1.2.1, Remove the period at the bullet introduction and add a colon. | Accepted | MIS Team
19 | MIS Team | C. Otten | 6 | Under 1.2.1, Define SSO, Add a comma after SSO: • Site Minder Policy Server will be available to provide authentication, SSO, and access control information. | Accepted | MIS Team
20 | MIS Team | C. Otten | 6 | Under 1.2.1, Add a hyphen between HTML and based "HTML-based" | Accepted | MIS Team
21 | MIS Team | C. Otten | 6 | Under 1.2.1; Remove extra period "• MIR will provide a secure content management solution that provides authorization by DUNS#. ." | Accepted | MIS Team
22 | MIS Team | C. Otten | 6 | Under 1.2.1, Global Change: Capitalize "Integration Layer" | Accepted | MIS Team
23 | MIS Team | C. Otten | 6 | Under 1.2.1, Has ODS's been defined previously in the document? If not, should define here. "• Interfaces within the Integration Layer will be provided when it is not feasible to get application data from application interfaces. The Integration Layer may access application ODS’s directly." | Accepted | MIS Team
24 | MIS Team | C. Otten | 7 | Under 1.2.2, Remove comma after "MyPage" and capitalize "User": • Configuration of MyPage at Market Participant and User levels" | Accepted | MIS Team
25 | MIS Team | C. Otten | 7 | Under 1.2.2., Remove "the" in front of Market Participants "• MyPage administration capabilities by the Market Participants;" | Accepted | MIS Team
26 | MIS Team | C. Otten | 7 | Under 1.2.2., Global Change: capitalize "Static Content" | Accepted | MIS Team
27 | MIS Team | C. Otten | 7 | Under 1.2.2., Add "and" at the end of the second to last bullet "• Capability of showing data in a graphical dashboard style; and" ; and add a period after "search" (last bullet) | Accepted | MIS Team
28 | MIS Team | C. Otten | 7 | Under 1.2.3., Need to define TML | Accepted | MIS Team
29 | MIS Team | C. Otten | 7 | Under 1.2.3., Add hyphens to "system to system":• Integration Layer web services will provide the system-to-system communication between Market Participant and ERCOT. | Accepted | MIS Team
30 | MIS Team | C. Otten | 7 | Under 1.2.3., Need to define Uis | Accepted | MIS Team
31 | MIS Team | C. Otten | 7 | Under 1.2.3., Change sentence structure: • TML will be provided as a separate entry point to be accessed directly [and will] not be [accessed] from MIS portal. | Accepted | MIS Team
32 | MIS Team | C. Otten | 8 | Under 1.2.4., Change that to which, "• Application Launch Pad which [that] provides service links that launch applications in a separate browser; | Accepted | MIS Team
33 | MIS Team | C. Otten | 8 | Under 1.2.4., Add a semicolon after "Portal" "• Search component that provides the ability to search MIS portal ; and | Accepted | MIS Team
34 | MIS Team | C. Otten | 8 | Under 1.2.4., Remove "and" and add a comma after "policies" and "authentication": "Directory Server: This is the store that the Site Minder Policy Server will use to store access policies , [and] user authentication , and authorization information. | Accepted | MIS Team
35 | MIS Team | C. Otten | 9 | Under 1.2.4., Change : "ERCOT.com: This is a web site that is classified as public and has static HTML content as well as public documents that are in content management system." to "ERCOT.com This is a web site that is classified as public. It has static HTML content as well as public documents that are in the Collage Content Management System." | Accepted | MIS Team
36 | MIS Team | C. Otten | 9 | Under 1.2.4., Capitalize "Team" | Accepted | MIS Team
37 | MIS Team | C. Otten | 9 | Under 1.2.4., Add "of" before "the applications": "Nodal Application Web UIs: These are the web-based user interfaces of all of the applications that MIS portal will be launching based on user permissions." | Accepted | MIS Team
38 | MIS Team | C. Otten | 9 | Under 1.2.4., Add a comma after "maintain" and "template:: "TIBCO Portal Builder: This is the portal software that will be used to create, maintain, and administer the MIS portal’s portlets, pages, templates, and other entities. MIS portal will use version 5.2." | Accepted | MIS Team
39 | MIS Team | C. Otten | 9 | Under 1.2.4., Capitalize "TIBCO administrative module" : "TIBCO Administrator: This is the TIBCO Administrative Module " | Accepted | MIS Team
40 | MIS Team | C. Otten | 9 | Under 1.2.4., Remove comma after "ERCOT.com" : "1. ERCOT.com Interaction: There will be links to access ERCOT.com from the MIS portal. Specific pages and documents in ERCOT.com will also be packaged as portlets in the MIS portal so that they can be used in creating user personalized MyPages. When interacting with ERCOT.com, the security context will be passed through the HTTP headers. | Accepted | MIS Team
41 | MIS Team | C. Otten | 9 | Under 1.2.4., Global Change: Capitalize "nodal application web" : "2. Interaction with Nodal Application Web UIs: The Nodal Application Web UIs will be launched using the" | Accepted | MIS Team
42 | MIS Team | C. Otten | 9 | Under 1.2.4., Add a hyphen between "AJAX" and "type": "3. Integration Layer XML/HTTP: There are several applications that provide an XML/HTTP interface that will be used by the MIS portal to create application portlets. Security context is expected to be provided through the HTTP headers by these applications. These interfaces will be analyzed in the detail design to see if they can be re-factored to an AJAX-type implementation to support performance considerations." | Accepted | MIS Team
43 | MIS Team | C. Otten | 9 | Under 1.2.4., Remove the comma after "designed": "4. Integration Layer Common Services: The Integration Layer is expected to provide common services interfaces for delivering notifications to the MIS portal. These interfaces will be used to create the notification functionality in MIS portal. The interface type (Web services, XML/HTTP etc.) has not been defined yet by the integration team. Once these have been defined, they will be used during the detailed design to define how the notification portlets will interact with the common services. Detail on how the security context will be passed to the integration layer will also be designed [,] as notifications need to be delivered based on roles as well as Market Participant identity." | Accepted | MIS Team
44 | MIS Team | C. Otten | 10 | Under 1.2.5, Define DMZ. | Accepted | MIS Team
45 | MIS Team | C. Otten | 10 | Under 1.2.5., Add a semicolon after "Agent": "• Complete proxy engine with a fully integrated Site Minder Agent[;] and" | Accepted | MIS Team
46 | MIS Team | C. Otten | 10 | Under 1.2.5., Change sentence from: "The above approach is proposed as based on best practices and Site Minder recommendation. " to "The approach proposed above is based on best practices and Site Minder recommendation." | Accepted | MIS Team
47 | MIS Team | C. Otten | 10 | Under 1.2.5., Global Change: Capitalize "nodal application teams" | Accepted | MIS Team
48 | MIS Team | C. Otten | 10 | Under 1.2.5., Change sentence from: "During detailed design, this configuration will be evaluated with the other teams and ERCOT Corporate Security for feasibility, and it is subject to change." to "During detailed design this configuration will be evaluated with the other teams and ERCOT Corporate Security for feasibility. It is subject to change." | Accepted | MIS Team
49 | MIS Team | C. Otten | 11 | 1.2.6., Add hyphen between "AJAX" and "based": "AJAX-based" | Accepted | MIS Team
50 | MIS Team | C. Otten | 11 | 1.2.6., Add punctuation to the bullet list as follows: "• It is based on the Object-Oriented paradigm[.] • It is Open Source, so no additional cost or licenses [.] • It improves developer productivity by[:] o Providing wizards to automatically build AJAX functionality from web services[;] o Hid[ing] the scripting complexity[;] o Provid[ing] full development and debugging environment[;] o Integrat[ing] with TIBCO Portal Builder by provi[ding](?) easy conversion of AJAX applications into portlets[.] | Accepted | MIS Team
51 | MIS Team | C. Otten | 11 | Under 1.2.6., Add commas after "considered" and "rejected": "We considered[,] but rejected[,] other options such as hand coding JavaScript & Ruby on rails. | Accepted | MIS Team
52 | MIS Team | C. Otten | 11 | Under 1.3., Rewrite the following due to bad grammar: "The software will be developed offsite, with stubbed integration points created with test data to support unit testing." | Accepted | MIS Team
53 | MIS Team | C. Otten | 11 | Under 1.3., Global Change: Capitalize "builder" in "Portal builder Data Store ": "Portal Builder Data Store" | Accepted | MIS Team
54 | MIS Team | C. Otten | 13 | Under 2.1.1., Change "Personalization is not a required feature in the protocols but it is a clear expectation expressed in the RFP and a Wish List compiled by the TPTF subgroup." to "Personalization is not a required feature in the protocols but it is a clear expectation expressed in the RFP and noted on the Wish List compiled by the TPTF subgroup. | Accepted | MIS Team
55 | MIS Team | C. Otten | 13 | Under 2.1.2., Change "Personalization will allow a user to create one or more customized pages, name them, and place on them portlets available to the user. It will also allow the user to indicate preferences for viewing notices." to "Personalization will allow a user to create one or more customized pages, to name them, and to place on them portlets available to the user. It will also allow the user to indicate preferences for viewing notices. " | Accepted | MIS Team
56 | MIS Team | C. Otten | 15 | Global Change: capitalize the "t" in Team where appropriate. | Accepted | MIS Team
57 | MIS Team | C. Otten | 15 | Global Change: capitalize the "s" in "system" : "MIS System" | Accepted | MIS Team
58 | MIS Team | C. Otten | 15 | Under Types of Users, Add comma after "teams" : "The MIS portal will serve many types of organizations, teams[,] and users – all within a strictly enforced content and application security context." | Accepted | MIS Team
59 | MIS Team | C. Otten | 16 | Under USA Template Modifications, Add a colon at the end of "portal" : "Market Participant USAs may use the following capabilities to further define what their users can and cannot see and do within the MIS portal [:]" | Accepted | MIS Team
The subsequent grammatical changes in the CSD are of the same nature as the above. Details can be provided upon request.
| MIS | P. Harris | App 5.1 | Added: RDBMS, DR, SSO, TML, UI