## Slide 1: Market Coordination Team Update Retail Market Subcommittee January 10, 2007 Susan Munson Retail Market Liaison

## Slide 2: Project Schedule
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 3: Risks / Issues
Issue | Mitigation | Owner
PR50121_07 RBP – Stabilization necessary for successful implementation | Schedule management Milestone completion | ERCOT
ERCOT February Retail Release | Schedule and resource management Milestone completion | ERCOT
PUCT Mandate of 07/01/2007 poses tight timeline | Schedule and resource management Milestone completion | All
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 4
PR40038_01 Status
Status:
  On target for schedule, budget, and scope
Project Phases:
  Initiation – Completed
  Planning – Target completion date 01/05/2007 (Original = 12/9/2006)
  Execution – Mandated completion date July 1, 2007; Go-Live 06/24/2007
  Closing – Target completion is post go-live
Recent Activity:
  ERCOT Conceptual Design Reviews Completed for TIBCO, Paperfree/NAESB, Siebel
  TML Requirements Review Completed
  Complete Exception Handling Requirements (ETS, Reprocessing, ODS, other Tools)
  Began Review of Detail Designs
  Scheduled to Gate to Execution on 01/19/2007
  Started monthly MCT progress reporting to RMS
Next Steps for ERCOT:
  Finalize Core Detail Designs (TIBCO, Paperfree/NAESB, Siebel, TML)
  Complete Test Plans, Scripting, and Data Prep
  Set Up Test Environment
Next Steps for MCT:
  Continue to monitor Market issues and progress
  Begin Market weekly status calls
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 5: Texas SET 3.0 Progress Reporting: What will be reported?
All Market Participants will be required to provide their progress on Design, Development, and Internal Testing of Texas SET V3.0 and identify any risks that may delay Flight 0407 or Implementation of Version 3.0
Progress will be reported as % complete
Non-response will default to previous month’s status
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 6: January Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 7: January Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 8: January Status Reporting - CRs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 9: January Status Reporting – ERCOT and TDSPs
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 10: CRs Not Reporting Progress for January
ACCENT ENERGY TEXAS LP
ACN ENERGY INC (LSE)
ALLIANCE POWER COMPANY LLC
AMBRIDGE ENERGY
AMPRO ENERGY INC (LSE)
ANP POWER DIRECT COMPANY (LSE)
BRIDGEPOINT POWER AND LIGHT LLC (LSE)
CONSOLIDATED EDISON SOLUTIONS INC
CURRENT POWER AND LIGHT LLC
DTE ENERGY TRADING INC
DYNOWATT LP
ENERGY WEST DBA FIRE FLY POWERED BY FRANKLIN POWER (LSE)
ENTERGY SOLUTIONS LTD
FIRE FLY ELECTRICITY LLC (LSE)
HUDSON ENERGY SERVICES LLC (LSE)
MS RETAIL DEVELOPMENT CORP
MUTUAL ENERGY SWEPCO LP (LSE)
NM ENERGY OF TEXAS LLC DBA FIVE POINT POWER
NUECES ELECTRIC COOPERATIVE INC RETAIL DIVISION (NEC RD)
NV POWER LP
PEGASUS ALLIANCE CORPORATION DBA ONPAC ENERGY (LSE)
TEXAS COMMERCIAL ENERGY (LSE)

## Slide 11: Customer Billing Contact Information File
Reminder – All CRs (new and currently certified) must send a test Customer Billing Contact Information File in Flight 0407
  This is a test file - not a production file
  Will be performed through a market test script
  All CRs will receive back a response file from ERCOT
Customer Billing Contact Information File Initial Load
  Purpose: Ensure ERCOT has a file from each CR soon after go-live and prior to the first mandatory production file transmission in October, 2007
  Production files will be sent to ERCOT by CRs following Texas SET 3.0 implementation (last 2 weeks of July, 2007)
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 12
Meeting Dates and Locations 2007
  January 24 – ERCOT Met Center
  February 21 – ERCOT Met Center
  March 28 – ERCOT Met Center
(Note: all meetings are held in conjunction with TX SET meetings)
Future Meetings/Market Communications
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 13: ERCOT Contacts
ERCOT Project Manager ERCOT SR. Business Analyst
Hope Parrish Jennifer Frederick
hparrish@ercot.com jfrederick@ercot.com
512-248-6522 (w) 512-248-6733 (w)
512-771-9582 (c) 512-413-0815 (c)
ERCOT Market Liaison
Susan Munson
smunson@ercot.com
512-248-3881 (w)
512-826-0564 (c)
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO

## Slide 14: Questions?
Project: PR40038_01 Current Phase: Planning
2007 PPL Source: Market/PUCT Priority: 0-Carryover Rank: 1 Budget: $3-$5 MM Program Area: RO