## Slide 1: PR50121_07 Retail Business Processes (RBP) Project Update
A Sub-project of the Service Oriented Architecture (SOA) Initiative

## Slide 2: Background
Objectives
Goal is to replace current SeeBeyond Retail Components with TIBCO EAI components to deliver a technology and framework improved scalability, reliability, stability & maintainability. RBP is one of 8 SOA Subprojects to replace SeeBeyond.
Drivers
Minimize or reduce operating failures produced from current SeeBeyond Application and Architecture.
Reduce maintenance costs associated with up-keep of SeeBeyond Application and Architecture.
PR50121_07 RBP PPL Source: ERCOT Priority: 1.0 Rank: .08 Budget: $1-3M Program Area: RO

## Slide 3: Project Status
Project Phases
Initiation – Completed 08/01/2005
Planning – Complete 05/08/2006
Execution
  Go-Live – Complete 12/10/2006 (within schedule and budget)
  Stabilization effort – Target Completion 02/09/2007
Closing – Target to complete February 2007
Recent Activities As of 12/29/2006
Completed migration to Production as scheduled
Began Stabilization Efforts
  Implemented several configuration and code adjustments to improve performance
  Begin Stabilization status meetings
Next Steps
Continue Delta Siebel Data Conversion every weekend until Complete (target end of January 2007)
Continue TIBCO monitoring, enhancements, and training with onsite TIBCO consultant
Compile Overall Project Lessons Learned
PR50121_07 RBP PPL Source: ERCOT Priority: 1.0 Rank: .08 Budget: $1-3M Program Area: RO

## Slide 4: Testing Report
PR50121_07 RBP PPL Source: ERCOT Priority: 1.0 Rank: .08 Budget: $1-3M Program Area: RO
Testing
A total of 1140 scripts were executed for UAT, Load, and Regression
RBP Total: 44-Environment, 24-Configuration, 98-Code, 23-Invalid

## Slide 5: Stabilization Update
Post-Production Issues:
64 Problem Tickets relating to RBP have been logged for investigation as of 01/03/2007
  43-Closed
  1-Duplicate
  2-Invalid
  2-Test for February Release
  14-Open
  2-Business Analysis/Verification (pending close)
**All open items are currently low volume and have a workaround thru normal Exception Management handling performed by Retail Customer Choice.
Project Team will continue to log, track, and document all issues related to Post-Production

## Slide 6: Questions / Contact
Adam D. Martinez
Mgr, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Hope Parrish
PM, Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com