## Slide 1: Texas Nodal Market Trials and Data Verification ROS Meeting By Steve Grendel, ERCOT Thursday, 01/11/2007

## Slide 2: Agenda
Market Trials Objectives
EDS Phases, Timeline & Definitions
Progress to Date
Data & Telemetry Verification

## Slide 3: Objective of market trials
The objective of market trials is to confirm through a series of structured and unstructured tests that:
“stable and accurate operations of the SCADA, Network Security Analysis, Transmission Constraint Management, SCED, LFC, DAM, RUC, and real time settlement system can be declared”
as outlined in the Nodal Transition Plan.

## Slide 4: Market Trials Phases
EDS 1 – Data and Telemetry
EDS 2 – State Estimator, Network Security Analysis
EDS 3 – Real Time Market Operations
EDS 4 – Day Ahead Market Operations

## Slide 5: EDS - Market Trials Timeline
EDS 3
Jul 08
Dec 08
Sep 08
Aug 08
Mar 08
Feb 08
Jan 08
May 08
Jun 08
Dec 07
Oct 08
Nov 08
Apr 08
Cycle 1 LMP w Controls
ACE
DR Testing
Compliance
1 hr EECP
Comment Period
ACE – 2 weeks (5.4.8 (2)
Compare existing with new ACE results
LMP Market Readiness Criteria MET
12/01/08 Realtime Markets GO LIVE
`
12/08/08 Forward Markets GO LIVE
Zonal Markets Shutdown GO/NO GO
Nov 07
Market Operations Sandbox & ERCOT UAT
Market Trials Start
Resource Registration
All QSEs – Real Time Parallel Operations
AS Qualification
3/31/08 Single Entry Model GO LIVE
Reasonable LMPs
24x7 support
All available MPs
Reasonableness criteria met
6 months
Oct 07
EDS 4
Feedback
168 hour test complete
168 Hour Test – 4 weeks to complete; 4 week feedback-fix
168 hour trial
Go-Live & Transition
Jul 07
Sep 07
Aug 07
May 07
Jun 07
ICCP / Telemetry Validation
SE Validation
SCED testing cycles, voluntary per QSE scripted for 30 days
Thereafter all QSEs participate in real time parallel operations
EDS 2
EDS 1
Market Operations Sandbox & ERCOT UAT
EDS 4 - Day Ahead Operations
Limited 24x7 support
Full 24x7 support
Market Operations Functional Testing

## Slide 6: EDS Market Trials Definition Schedule
Request comments on Market Trials Approach by 12/13/06
Return for approval on January 25th
Begin EDS detailed planning providing opportunities for comments as follows:
  Review Transition Plan Traceability Matrix TBD
  EDS 1 to 4 Detailed Plan – Drafts for comment TBD
  EDS 1 Detailed Plan – Final Signoff TBD
  EDS 2 Detailed Plan – Final Signoff TBD
  EDS 3 Detailed Plan – Final Signoff 3/30/2007
  EDS 3 Market Trials Handbook – Final Signoff 6/29/2007
  EDS 4 Detailed Plan – Final Signoff 9/28/2007
  EDS 4 Market Trials Handbook – Final Signoff 12/31/2007

## Slide 7: EDS Detailed Planning
Example
EDS | Description | Transition Plan Requirement | Operations / SoSA | Market Trials tasks | MP Interventions | Notes
1 | Telemetry & ICCP Validation | 5.4.1(2) ERCOT shall develop procedures for setup and data implementation requirements applicable to TSP’s and QSE’s. ERCOT shall with the assistance of TSP’s and QSE’s: (a) Verify that all data and telemetry requirements Specified in the nodal Protocols Section 3.10, Network Operations Modeling and Telemetry, Have been met and that all Data submittals are complete and represent an accurate model of the ERCOT System; | - S.UC1.OP6: Update QSE Provider Information (EMS Operation) - S.UC1.OP7: Use Revised Data (EMS Operation) - S.UC1.OP8: Use Telemetry Data (EMS Operation) - S.UC2.OP1: Update RT Generation/Transmission Data (EMS Operation) - S.UC2.OP2: Update Transmission Ratings (EMS Operation) ICCP information TO the field (external): - S.UC2.OP4: Send Base Points - M.UC12.OP1: Clear RT Market (I know Base Points are communicated to QSE’s via ICCP, will need to check which other ones do) | All telemetry (SCADA/ICCP) points checked out (programmatically or manually) 100 % Status Report at the end of this activity must indicate that 100 % of all points have been tested and verified Require Professional Engineers Seal from Entities to assure accuracy of data. Can be required from QSE’s/TSP’s due to issues of public safety and public interest Alarm Functionality Revalidated SCADA/ICCP enhancement to detect Forced Outage of equipment Real Time Weather Telemetry revalidated Dynamic Rating telemetry Validate all Transmission Element Limits and Constraints Check TSP’s calculation Transmission Element Ratings that are likely to be active in SCED Telemetry Criteria Developed (protocol 3.10.7.4) Define and implement business processes to repair errors. | 12-31-06 – Preliminary MP Interface Specs 3-30-07 – Final Interface Specs | This is a joint ERCOT and Market Participant task. Will require a EDS type functionality from TSP/QSE QSE/TSP personnel can SIMULATE analog/digital changes on their EDS and ERCOT EDS will be able to accomplish point-to-point check out with ERCOT operators Explore programmatic way to validate – this approach can be used later for periodic verification.
2 | Network Model Validation SE Solution |  |  |  |  | 
3 | Real-time Market Operations |  |  |  |  | 
4 | Day ahead Market Operations |  |  |  |  | 
Define Transition Plan Traceability Matrix

## Slide 8: Data and Telemetry Verification
Transition Plan Detail:
  5.4.1(2a) ERCOT shall develop procedures for setup and data implementation requirements applicable to TSPs and QSEs. ERCOT shall with the assistance of TSPs and QSEs: Verify that all data and telemetry requirements specified in the nodal Protocols Section 3.10, Network Operations Modeling and Telemetry, have been met and that all data submittals are complete and represent an accurate model of the ERCOT System
Why?
  Reasonable and accurate LMPs require accurate telemetry and model data.
  ERCOT needs to demonstrate the continual accuracy of both the telemetry and network model data
How can this be achieved?
  Demonstrate compliance with Telemetry Criteria
  Demonstrate compliance with SE Criteria
  Verify end to end communication and mapping of SCADA data
Are there other approaches?

## Slide 9: NMT – Network Operations Modeling & Telemetry – Project
Model Data Issues Progress by MP – as of 12/22/2006
Note 1: Blank indicates MPs that ERCOT has not contacted to date
Note 2: NMT inherited ~400 legacy model issues

## Slide 10: SCADA Telemetry Schematic
Transducer (kWh)
RTU
Analog
Status
Accumulator
Equipment Statuses
Scaling
TSP & QSE EMS
SCADA
ICCP
ICCP
ERCOT
SCADA
Phone Lines
ICCP Link
One-line Displays
Mapping to network model
ERCOT Quality codes
PT
CT
QSE/TSP data accuracy assurance points
ERCOT data accuracy assurance points
A
C
B
D
E
F
G
H
I
K
M
L
Segment | Certification Requirement | Notes
A to H | To be certified by MPs | 
H to I | To be certified by TBD (3rd Party ?) | 
I to N | To be certified by ERCOT | 
J
Quality codes posted by TSP
N
ERCOT EDS scope
Draft appropriate attestation so that accuracy and mapping from A to H can be verified by MPs without unnecessary verification rework.
Draft appropriate attestation so that accuracy and mapping from I to N can be verified by ERCOT within unnecessary verification rework

## Slide 11
Questions?