## Slide 1: PMO Update to PRS
Troy Anderson
Program Management Office
January 18, 2007

## Slide 2
PMO Update
Agenda
  Recent Project Developments
  NPRR Review Status
  2006 Project Estimate Performance
  CBA Review Team

## Slide 3
PMO Update
Recent Project Developments
  Wholesale Go-Live Projects
    EPS Meter Data (PRR283)
      Extract of RID-level EPS Meter Data and SCADA data via the ERCOT Portal (TML)
    Removal of Price Admin. for Zonal Congestion (SCR747)
    Modification of Distribution Loss Calculations (PR-60068)
      Calculation of Losses for Settlement (PRR565)
        Requires ERCOT to use actual load for calculating the Settlement Interval Loss Factors (SILF)
      Distribution Loss Factor Calculations (PRR668)
        Uses new TDSP supplied coefficient in the SILF equation
      PRR668 functionality was implemented in the code and was meant to go live on Jan 1, 2007. However, certain TDSPs have not yet supplied the required SILF coefficients. Therefore, the calculations are being held back through effective dating until the required data is received.

## Slide 4
PMO Update
NPRR Review Status
  Currently synchronizing all Nodal projects to the November 2006 Nodal Protocols
  Most Nodal projects are caught up through November
    EMS / MMS have recently started a process to review all NPRRs sequentially to reassess cross-impacts
    They plan to be caught up in February
  Project impacts will be communicated as the process continues
  Changes to previously reported estimates will be taken through the stakeholder process for approval

## Slide 5
PMO Update
2006 Project Estimate Performance
  55 Projects Completed in 2006
    15 projects exceeded their baseline budgets
    40 projects were less than their baseline budgets
  8 Market Projects Completed in 2006
    4 “<$100k” estimates that completed for <$100k
    1 “$1M-$3M” estimate that completed for $2.635M
    1 “<$100k” estimate but was combined with another project
    2 projects that were approved prior to our current Impact Analysis process

## Slide 6
PMO Update
CBA Review Board (CRB)
  Market Participants
    Manny Munoz
    Hal Hughes
    Any other volunteers?
  ERCOT Participants
    PMO
      Troy Anderson, Pat Moast, Elizabeth Mansour
    Other ERCOT Teams
      One participant per CART
Meeting Schedule
  Monthly teleconference
    January (to be scheduled the week of 1/22)
    February (tentatively set for 2/15)

## Slide 7
PMO Update
February 2007 Report Items
  Recent Project Developments
  NPRR Review Status