## DISPUTES
| Document Name: | Response_to_Comments_Qualification_Approach_v0.6
| Issuing Entity | Name | Page Number | Description | Accepted / Rejected | Reviewer | Reason
1 | Garland Power & Light | Ronnie Hoeinghaus | p.3 | How does ERCOT propose to coordinate training with the Market Implementation as it appears there will not be adequate time to train the MP’s in the time that the courses become available and the required EDS activities? Also, when is the Product Training (EMS, MMS, NMMS, CRR, CMM) and Application Support Training (EMS, MMS, NMMS, CRR, CMM, OS, MIS, EDW, MP Registration) going to be available for the required ERCOT training sessions – do not see them on the schedule yet and again the question, will there be adequate time for training to support the timeline? | Accepted | Ted Hailu | Comment is about coordination of EDS phases and training ( Concept training and produict training). Will be addressed during Readiness Approach and/or Training discussions at TPTF.
2 | Garland Power & Light | Ronnie Hoeinghaus | p.3, p.5 | In the EDS Market Trials Approach document, it says that the ERCOT team & the Market Participants will work together to finalize a set of measurable entrance & exit criteria for readiness criteria. In this document, it sounds like ERCOT is going to do it alone (“ERCOT will define…”. Believe it should be a joint effort (as the EDS Market Trials Approach document states) for this effort. | Accepted | Ted Hailu | ERCOT will work with Market Participants to define readiness criteria
3 | Garland Power & Light | Ronnie Hoeinghaus | p.6 | Believe should add qualification based on market participation level explanation that is on the bottom of slide 4 of the ERCOT Qualification Approach overview presented to TPTF on December 4th | Accepted | Ted Hailu | Added expanation of QSE qualification by level
4 | Garland Power & Light | Ronnie Hoeinghaus | p.6 | Believe should add the qualification table located on slide 8 of the ERCOT Qualification Approach overview presented to TPTF on December 4th | Accepted | Ted Hailu | Added table detailing QSE qualification by level to document
5 | Garland Power & Light | Ronnie Hoeinghaus | p.7 | Does this also include entities that qualify for PCRR’s? | Accepted | Ted Hailu | Yes. NOIEs eligible for PCRR allocation will also need to qulaify as CRR Account Holders.
6 | Garland Power & Light | Ronnie Hoeinghaus | p.9 | Balancing not in Nodal | Rejected | Ted Hailu | The list of Ancillary Services mentioned in the document is for the current market which includes balancing energy
7 | Garland Power & Light | Ronnie Hoeinghaus | p.9 | It would seem that there should be some type of test for receiving & responding to a Base Point - above list has checks for providing for ancillary services but what if a unit is not going to provide ancillary services? | Accepted | Ted Hailu | Added a statement that ERCOT will test the ability to receive and respond to base points being sent from ERCOT even for units not providing Ancillary Services
8 | Garland Power & Light | Ronnie Hoeinghaus | p.11 | According to the EMS SCADA document, you are expecting to monitor 200,000 analogs, 160,000 status points and expect to send 7,900 points for Nodal. Please explain the methodology and expected time to accomplish a point by point checkout of the Nodal points & how it fits into the Nodal timeline. | Accepted | Ted Hailu | The approach to the point-by-point telemetry checkout will be discussed as part of the EDS-1 and 2 dicussions with TPTF
9 | Garland Power & Light | Ronnie Hoeinghaus | p.13 | Did you mean Section 8.1.2.1? | Accepted | Ted Hailu | Yes. Protocol reference corrected
10 | Garland Power & Light | Ronnie Hoeinghaus | p.14 | this assumes that all resources will be on line at this particular testing time – for whatever reason, 1 or more units may not be available at this time frame thus requiring more than one qualification test) | Accepted | Ted Hailu | ERCOT will work with each QSE to accommodate units that may not be available for testing at the scheduled time for testing of units for each QSE
11 | Garland Power & Light | Ronnie Hoeinghaus | p.14 | Has ERCOT projected the amount of time required to qualify all Resources providing A/S to make sure it is in line with Market Go-Live timeline? | Accepted | Ted Hailu | This is a recognized critical path item. Work is still in progress to assure that AS qualification for most units is completed in time to support the market trials. AS qualifications will continue until the qualification freeze period.
12 | Garland Power & Light | Ronnie Hoeinghaus | p.15 | All QSEs planning to participate in the nodal market at the go-live date will need to complete qualification activities, and they must be completed prior to the beginning of this period. ERCOT shall allow a reasonable timeline for all QSE’s that wish to provide Ancillary Services to complete qualification tests prior to a go-live date implementation. | Accepted | Ted Hailu | This is a recognized critical path item. Work is still in progress to assure that AS qualification for most units is completed in time to support the market trials. AS qualifications will continue until the qualification freeze period.
13 | Garland Power & Light | Ronnie Hoeinghaus | p.15 | The table below does not match the Qualification Timeline table or chart presented to TPTF on December 4th, 2006 in the ERCOT Qualification Approach Overview – which is correct? Believe the chart on page 17 of the overview presentation should be added to this document once the dates are reconciled as mentioned above. | Accepted | Ted Hailu | Dates on table reconciled
14 | Brazos | Tony Kroskey | various | Various edits (Grammar, re-wording etc…) | Accepted | Ted Hailu | Made suggested changes