## Eligibility
| Document Name: | TN.COMS.63C01.ELIGIBILITY.CSD.A.doc
# | Issuing Entity | Name | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason
1 | GP&L | Hoeinghaus | 4 | Day-Ahead make Whole Energy Flag (DAMWENEFLAG) —The hourly flag that indicates Day-Ahead Make-Whole Payment energy eligibility for the Resource represented by the QSE, for the hour. 0 = Resource is not eligible for energy costs in the Day-Ahead Make-Whole payment 1 = Resource is eligible for energy costs in the Day-Ahead Make-Whole payment GP&L Comment: This definition for this flag is duplicated on page 6 – believe the one on page 6 should be deleted. | Accepted | J. Jackson | The duplicate comment has been removed from the Eligibility Process CSD.
2 | GP&L | Hoeinghaus | 6 | Day-Ahead make Whole Energy Flag (DAMWENEFLAG)—The hourly flag that indicates Day-Ahead Make-Whole Payment energy eligibility for the Resource represented by the QSE, for the hour. 0 = Resource is not eligible for energy costs in the Day-Ahead Make-Whole payment 1 = Resource is eligible for energy costs in the Day-Ahead Make-Whole payment GP&L Comment: This definition for this flag is duplicated from page 4 – believe this one on this page should be deleted. | Accepted | J. Jackson | The duplicate comment has been removed from the Eligibility Process CSD.
3 | Reliant | Wagner | 4 | Day-Ahead make Whole Energy Flag (DAMWENEFLAG) —The hourly flag that indicates Day-Ahead Make-Whole Payment energy eligibility for the Resource represented by the QSE, for the hour. 0 = Resource is not eligible for energy costs in the Day-Ahead Make-Whole payment 1 = Resource is eligible for energy costs in the Day-Ahead Make-Whole payment | Response-Clarification | J. Jackson | The bolded area was highlighed in Reliant's Comments. No specific comment was provided; additional clarification is needed to reply.
4 | Reliant | Wagner | 8 | A10) This Conceptual System Design will not cover every requirement for Eligibility. Specific requirements, such as the requirements defining public and private Bill Determinants, cannot be addressed technically through the configuration of charge types. The design documentation and solution for the Market Data Transparency Requirements will specifically address the definition of public and private Bill Determinants. | Response-Clarification | J. Jackson | The bolded area was highlighed in Reliant's Comments. No specific comment was provided; additional clarification is needed to reply.
5 | Reliant | Wagner | 8 | A12) All database requirements will be addressed in the Detailed Design documents for the Settlements System. | Accepted | J. Jackson | Accepted change of wording--"shall" changed to "will."
6 | Reliant | Wagner | 9 | A13) The Current Operating Plan (COP) is hourly data and thus STATUSSNAP must be an hourly interval data cut. | Accepted | J. Jackson | Accepted change of wording--"shall" changed to "must."
7 | Reliant | Wagner | 9 | A15) During the detailed design process, IT may modify the process flow logic documented here, if it does not materially change the original requirements and if it provides a more efficient process flow. | Accepted | J. Jackson | Accepted change of wording--"detail" changed to "detailed."
8 | Reliant | Wagner | 15 | A QSE Clawback Interval is determined if any QSE-Committed Interval is part of a contiguous block that includes at least one RUC-Committed Hour, unless it is QSE-committed before the first RUC instruction or is part of a contiguous block of QSE-Committed Intervals, any of which were committed prior to the RUC-committed hour. QSE-committed hours include both DAM commitments and QSE self-commitments. | Accepted | J. Jackson | Accepted change--added "is" to sentence.
9 | Reliant | Wagner | 16 | 3.3.4. Processing [Reliant: nice flow chart!] | Accepted | J. Jackson | Thank you!
10 | Reliant | Wagner | 32 | 4.5. Back up and Recovery Requirements The same server configuration should be deployed both in the primary as well as in an offsite disaster recovery data center. Data from the primary and disaster recovery systems must be synchronized in order to support continued operation in the recovery center in case of a disaster scenario. In the event of a failover during processing, the system needs to be brought back up to complete the processing within the required time window. For the Zonal System, there is a specified time window (about 4 hours) during which the system needs to be brought back up. The Nodal System will use similar metrics unless it is specified otherwise. [Reliant: who will make this decision and when will it be made?] | Accepted | S. Mijar | Added the following comment to the document: "The Settlements Business and IT groups will make the relevant decisions during the Integration Test phase."
11 | Reliant | Wagner | 32 | Usability Requirements The Settlements system shall comply with ERCOT Texas Nodal standards for usability requirements. For all User Interfaces, there will be an Usability Evaluation conducted by the Usability Group. [Reliant: What is the Usability Group?] | Accepted | S. Mijar | Added the following comment to the document: "There is a Usability Group within ERCOT that is responsible for reviewing all User Interfaces for Nodal Projects. If necessary, this group will conduct a Usability Evaluation for the Settlements System."
12 | Reliant | Wagner | 34 | 4.13. Disaster Recovery • This is not a 7x24 application. Business Requirements state that the data must be backed up on a daily basis and recoverable within the time stipulated necessary for running the application. • Still to be determined is how much data loss is acceptable in the event of a disaster. [Reliant: don’t recall seeing this statement in the other documents…] | Accepted | S. Mijar | Made this change to the document by deleting comment.
13 | Reliant | Wagner | 17 | (Footnote) 4. The process in the Eligibility Requirements that sets all hours of the Operating Day in the SUFLAG equal to zero (0) outside of the RUC De-commitment hours was removed because it would overwrite flags set in the Startup Initiator. This will necessitate and change to the Eligibility Requirements. [Reliant: is the requirements document being updated to reflect this change?] In addition, the Requirements and Protocols may also require a change for Resources that shutdown and startup multiple times in an Operating Day when the Resource is De-committed by RUC [PR 5.7.3 (2)]. To alleviate this issue determination for RUC-De-committed intervals should be altered so that only hours after a RUC De-commitment will be noted as ineligible for startup (SUFLAG = 0). [Reliant: this could use more explanation…] | Response-Moved to IDA punchlist | J. Jackson | After determining a period of time that was eligible for the RUC Decommitment Payment, the text within the requirements states “Indicate all remaining Operating Hours within the Operating Day as ineligible for RUC Decommitment Payment (SUFLAG = 0).” The change/correction to the Eligibility Requirements is to clarify that only those hours after the RUCD should be marked with SUFLAG = 0, and make clear that the hours prior to the RUCD should not be affected. Upon approval of this CSD, the requirements will be updated to reflect this clarification.
14 | Reliant | Wagner | 17 | (Footnote) 4. The process in the Eligibility Requirements that sets all hours of the Operating Day in the SUFLAG equal to zero (0) outside of the RUC De-commitment hours was removed because it would overwrite flags set in the Startup Initiator. This will necessitate and change to the Eligibility Requirements. [Reliant: is the requirements document being updated to reflect this change?] In addition, the Requirements and Protocols may also require a change for Resources that shutdown and startup multiple times in an Operating Day when the Resource is De-committed by RUC [PR 5.7.3 (2)]. To alleviate this issue determination for RUC-De-committed intervals should be altered so that only hours after a RUC De-commitment will be noted as ineligible for startup (SUFLAG = 0). [Reliant: this could use more explanation…] | Response-Moved to IDA punchlist | J. Jackson | Business will submit an NPRR to address this issue. The NPRR will address the use of the “later of” logic in 5.7.3 (2). Currently the Protocols state that “the hours used in the calculation are the hours beginning with the first decommitted hour until the later of: (a) The hour ERCOT determines that the Resource may again be at LSL; and (b) The end of the last hour of the Operating Day.” According to this logic, the settlement process would always use all hours from the start of the RUC decommitment through the end of the Operating Day in the RUC Decommitment Payment calculation, even if the Resource could be back at LSL prior to the end of the Operating Day. This appears to result in a payment during Operating Hours when the Resource could be online. The hours between the hour at which the Resource could be back at LSL and the end of the Operating Day would be included in the RUC Decommitment Payment to the Resource and therefore there would be uplift in those hours, even though the Resource could be online. Also, the current logic doesn’t seem to accommodate a scenario where a Resource receives multiple RUC decommitments within an Operating Day. The CSD was written in such a way that if the Resource was able to be back at LSL prior to the end of the Operating Day, the hours that are eligible for the RUC Decommitment Payment are those from the start of the RUC Decommitment through the hour at which the Resource may be back at LSL… NOT the end of the Operating Day (i.e, the CSD is written according the logic that will be proposed in the NPRR.)
15 | LCRA | Jill T | 4 | Day-Ahead make Whole Energy Flag (DAMWENEFLAG) —The hourly flag that indicates Day-Ahead Make-Whole Payment energy eligibility for the Resource represented by the QSE, for the hour. 0 = Resource is not eligible for energy costs in the Day-Ahead Make-Whole payment 1 = Resource is eligible for energy costs in the Day-Ahead Make-Whole payment | Accepted | J. Jackson | Accepted change case.
16 | LCRA | Jill T | 6 | Day-Ahead make Whole Energy Flag (DAMWENEFLAG) —The hourly flag that indicates Day-Ahead Make-Whole Payment energy eligibility for the Resource represented by the QSE, for the hour. 0 = Resource is not eligible for energy costs in the Day-Ahead Make-Whole payment 1 = Resource is eligible for energy costs in the Day-Ahead Make-Whole payment | Accepted | J. Jackson | This is duplicate entry and has been deleted based on other comments.
17 | LCRA | Jill T | 23 | 3.7.1. Introduction This process will determine if a RUC committed resource, identified as the Startup Initiator, is eligible for startup compensation by applying tests to determine if the Resource was offline prior to the commitment and if the Resource was online during the commitment. | Rejected | J. Jackson | The original sentence was, "This process will determine if a RUC commitment identified as the Startup Initiator …" Although a Resource is the entity evaluated for startup compensation, from a technical perspective, this process looks at independent commitments, which were previously identified as the initiator of a startup, to determine make whole eligibility. If a Resource is committed in the RUC multiple times, the earliest commitment (via snapshot) is the startup initiator and thus continues through the startup process to determine RUC Startup Eligibility. No change is necessary.
18 | LCRA | Jill T | 30 | 3.10.4. Processing (Business Defined Errors) In this process flow, there is not a line to answer “no” to the question/decision “Is the Resource RUC de-committed?” | Accepted | J. Jackson | The process flow has been updated.
19 | LCRA | Jill T | 33 | Usability Requirements The Settlements system shall comply with ERCOT Texas Nodal standards for usability requirements. For all User Interfaces, there will be a [LCRA: changed "an" to "a"] Usability Evaluation conducted by the Usability Group. | Accepted | S. Mijar | Made this change to the document.
20 | LCRA | Jill T | 35 | 4.12. Availability and Fail-over • It is expected that there will be monitoring in place to track the progress of the Settlements Batch process, and checks to signal errors if any. • If there are errors in the batch process activity, there will be pre-defined measures in place to due course of action. (this phrase is unclear “due course of action”) These measures might include restarting the batch process activity. | Accepted | S. Mijar | This section in the document has been fixed.
21 | LCRA | Jill T | 17 | (Footnote) 4. The process in the Eligibility Requirements that sets all hours of the Operating Day in the SUFLAG equal to zero (0) outside of the RUC De-commitment hours was removed because it would overwrite flags set in the Startup Initiator. This will necessitate a [LCRA: changed "and" to "a"] change to the Eligibility Requirements. In addition, the Requirements and Protocols may also require a change for Resources that shutdown and startup multiple times in an Operating Day when the Resource is De-committed by RUC [PR 5.7.3 (2)]. To alleviate this issue determination for RUC-De-committed intervals should be altered so that only hours after a RUC De-commitment will be noted as ineligible for startup (SUFLAG = 0). | Accepted | J. Jackson | Accepted change--changed "and" to "a".
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42