## <Registration>_Pre-No COP Vote
| Document Name: | COMS_CSD_Registration_System_v0.92.A
Sr # | Issuing Entity | Name | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason
1 | LCRA | Jill T | 4 | Existing registration materials from MPs in the zonal market can be transferred into the Nodal registration systems | Response | Amol/Art/Bill | Existing Registration information will be maintained. ERCOT is not building an entirely new Registration system for Nodal, but rather augmenting the existing one to accommodate Nodal. All Registered MPs will continue to be Registered. The additional fields necessary for Nodal operation will be filled by an additional Registration data request at some point in the future.
2 | LCRA | Jill T | 6 | Capture elements comprising each split unit configuration from QSEs | Accepted | Amol/Art/Bill | Protocol request.
3 | LCRA | Jill T | 23 | This last sentence needs to be reworded. | Accepted | Amol/Art/Bill | The system will set the status as Active as long as the Certification Begin Date is greater than System Date. The system will provide notice to Client Services and additional groups, to be determined in detail design.
4 | LCRA | Jill T | 23 | to | Accepted | Amol/Art/Bill | Grammatical Error
5 | LCRA | Jill T | 24 | no ????? This sentence is incomplete. | Accepted | Amol/Art/Bill | Registration forms will be accepted electronically as a Service Request module. Notification email will be sent to respective Account Manager
6 | LCRA | Jill T | 27,30,31,33,35,37 | the | Accepted | Amol/Art/Bill | Grammatical Error
7 | LCRA | Jill T | 29 | into | Accepted | Amol/Art/Bill | Grammatical Error
10 | LCRA | Jill T | 33 | and | Accepted | Amol/Art/Bill | Grammatical Error
13 | RELIANT | MW | 1 | Will existing Registration data be saved? Will Market Participants just modify or add to existing data in the ‘new’ registration system? Or will MPs have to enter all data again into the new system? If data is ported from old system is there a validation process? | Response | Amol/Art/Bill | Existing Registration information will be maintained. ERCOT is not building an entirely new Registration system for Nodal, but rather augmenting the existing one to accommodate Nodal. All Registered MPs will continue to be Registered. The additional fields necessary for Nodal operation will be filled by an additional Registration data request at some point in the future.
14 | RELIANT | MW | 1 | Do entities that are QSEs already get to skip any steps in Registration | Response | Amol/Art/Bill | Existing Registration information will be maintained. ERCOT is not building an entirely new Registration system for Nodal, but rather augmenting the existing one to accommodate Nodal. All Registered MPs will continue to be Registered. The additional fields necessary for Nodal operation will be filled by an additional Registration data request at some point in the future.
15 | RELIANT | MW | 1 | Can forms be submitted electronically | Response | Amol/Art/Bill | yes. ERCOT is working on the strategy for Accepting forms electronically. Depending upon the form type ERCOT will decide the digital signature policy. Say: wet signatures, scan copies and digital certificates
16 | RELIANT | MW | 4 | Reliant: if this assumes existing data will be ported over, what check out steps will be instituted to ensure the data are correct? | Response | Amol/Art/Bill | Existing Registration information will be maintained. ERCOT is not building an entirely new Registration system for Nodal, but rather augmenting the existing one to accommodate Nodal. All Registered MPs will continue to be Registered. The additional fields necessary for Nodal operation will be filled by an additional Registration data request at some point in the future.
17 | RELIANT | MW | 5 | Reliant: CRR Account Holder seems like it should also connect with the CRR box | Rejected | Amol/Art/Bill | No information from CRR account holder is going to CRR system directly. This will pass through MP registration i.e from Siebel to CRR. The link is already present. We are working on Single entry point for Registration data
18 | RELIANT | MW | 5 | Reliant: in the table below, why isn’t LodeStar populating the MMS to the degree possible rather than having the data show up twice. Why are rows 1 and 2 the same except for ‘external system’? What does NRT mean? Resource Parameters may require validation prior to nodal, so does putting them under ‘existing’ capture the need for validation? What is RSS (Resource Registration System)? Please define all acronyms prior to use | Accepted | Amol/Art/Bill | NRT: Near Real Time Resource parameters are going to store in Lodestar as well as MMS 30 % of the attributes will be stored under MMS & 70 % of the attributes will be stored under Lodestar RSS: is the project name for datawarehouse or storage project. Resource paramters will be verified by respective department at ERCOT before entering into Lodestar or MMS
19 | RELIANT | MW | 6 | Verifiable Cost template: Reliant: when will the template be developed? Will this be reviewed by TPTF?] | Response | Amol/Art/Bill | Registration System following parameters for verifiable Costs.  Maintenance costs  Startup fuel costs  Operation costs  Chemical costs  Water costs  Emission credits Business is working on the template during detail design Wholesale Market Sub-committee is working on the template during detail design Yes this will be reviewd by TPTF.
20 | RELIANT | MW | 6 | Reliant: what does this mean? There are specific criteria related to use of the Oklaunion exemption in the protocols and not every QSE qualifies for the exemption. So applicants should be validated against Protocol 4.4.4.3] | Accepted | Amol/Art/Bill | o Applications from QSEs requesting an Oklaunion exemption must be accepted and will be validated against Protocol Section 4.4.4.3.
21 | RELIANT | MW | 6 | Reliant: validation of signature is a manual process. How will this validation be captured in the registration system? Is a validation flag planned for manual approval of signed agreements?] | Response | Amol/Art/Bill | Forms will be accepted by Registration system electronically. ( Wet Signature / Scanned copies or using digital certificate). Original signed documents will be sent by courier later. Once both parties done with the sigining procedure the documents will be kept at ERCOT. Documents submitted will be scanned documents with a signature. The name of the person signing is validated against the Authorized Representative(s) registered for the Entity. If it is valid, the document data is entered. If not the document is rejected and sent back for clarification and or re-submission.
22 | RELIANT | MW | 6 | Reliant: is this information also stored in the Financial transfer system and or Credit monitoring? If yes to any, why is data storage duplicated? | Response | Amol/Art/Bill | We want to make single entry point for Registration data. Then once the data is validated by single source it will flow down to various systems if required. This information is required by CMM as well as CRR
23 | RELIANT | MW | 7 | [Reliant: don’t understand this. Does this mean that the Registration system needs to have point in time change control so that when a QSE relationship with an LSE changes the sytem can keep track of it and feed it to LodeStar? Otherwise, why would the registration system “notify a QSE” and how would this work?] | Response | Amol/Art/Bill | <All partnerships have begin and end dates. The notification to the QSE is required by protocol (16.3.3(3)) and done manually by Wholsale Client Services.>
24 | RELIANT | MW | 7 | [Reliant: Note that a CRR Account Holder is not required to have a parent QSE.] | Accepted | Amol/Art/Bill | <Reliant is correct, there is no "Parent" for a CRR Account Holder.> Maintain the relationship between the CRR Account Holders and any Financial Counterparty, if it exists.
25 | RELIANT | MW | 7 | [Reliant: is this information also stored in the Financial transfer system and or Credit monitoring? If yes to any, why is data storage duplicated?] | Response | Amol/Art/Bill | We want to make single entry point for Registration data. Then once the data is validated by single source it will flow down to various systems if required.
26 | RELIANT | MW | 7 | resources [Reliant: in addition to identifying WGRs, all Resource types with Generic Cost categories should be identifiable.] | Response | Art/Bill/Randy | ERCOT does not understand this question and requests Reliant to clarify.
27 | RELIANT | MW | 8 | Reliant: where does this information ‘match up’ with the metering information? For example if meter splits are based on this information, where would this happen, in LoadStar?] | Response | Art/Bill/Randy | The standard modeling of wind generation sites in Lodestar consists of one unit representing multiple turbines. On rare occasions, Market Participant requirements dictate that ERCOT sets up more than one unit at a particular generation site.
28 | RELIANT | MW | 8 | [Reliant: what does ‘start activities’ mean? Participate in nodal markets?] | Response | Art/Bill/Randy | You can apply today and have activity start date as 2 months in future. Refer the design details properly. Refer the example below in section 2.1.4
29 | RELIANT | MW | 8 | and the information provided to Planning and Operations | Accepted | Amol/Art/Bill | In complete Statement
30 | RELIANT | MW | 8 | [Reliant: why wouldn’t these be on the template referenced above under the QSE section?] |  |  | An RMR contract exists between ERCOT and the Resource Entity, not the QSE.
31 | RELIANT | MW | 8 | assist the analyst in evaluating compliance with submission deadlines. [Reliant: unless the registration system is enforcing the deadlines, the original statement is not correct.] | Accepted | Amol/Art/Bill | In complete Statement
32 | RELIANT | MW | 8 | [Reliant: TDSP registration should have the TDSP acknowledge who will be representing them as the Transmission Operator.] | Rejected | Amol/Art/Bill | Not mentioned into Nodal Protocol. Can you provide more clarification on this front?
33 | RELIANT | MW | 8 | to assist the analyst in evaluating compliance with submission deadlines. [Reliant: unless the registration system is enforcing the deadlines, the original statement is not correct.] | Accepted | Amol/Art/Bill | Grammatical Error
34 | RELIANT | MW | 9 | The Registration System must be able to designation a Counter-party’s rights as revoked Agreements as terminated. [Reliant: what does this mean?] | Accepted | Amol/Art/Bill | The Registration System must be able to designate a Counter-party’s rights as revoked and Agreements as terminated.
35 | RELIANT | MW | 9 | o The Registration System must allow for the removal of an entity’s rights to conduct activities under the protocols and will not prevent the entity from meeting it’s obligations for all costs and expenses incurred. [Reliant: this doesn’t make sense as one sentence. Further why would ERCOT try to prevent an entity from meeting its obligations?] | Response | Amol/Art/Bill | o The Registration System must allow for the removal of an entity’s rights to conduct market activities under the protocols but will not prevent the entity from meeting it’s financial obligations for all costs and expenses incurred.
36 | RELIANT | MW | 9 | o Provide a repository for relationship information between MP and whom? and maintain a history of relationship with whom? Other MPs? ERCOT? for each MP. | Accepted | Amol/Art/Bill | other MPs. o Provide a repository for relationship information between various MP entities and maintain a history of such relationships.
37 | RELIANT | MW | 9 | . [Reliant: is this an assumption for this document? If so move to assumptions, otherwise it is not relevant.] | Response | Amol/Art/Bill | Service filing forms are MP Registration / GARF / LARF / Resource Information / Resource parameters.. This is Nodal protocol requirement. The statement says that Signed agreements will be maintained for RMR service and Black start service. Those are 2 separate things. We are mentioning the strategy to store them
37a | RELIANT | MW | 9 | o Signed agreements must be maintained for entities providing RMR Service, Black Start Service and any other service required by ERCOT. [Reliant: an RMR agreement will not work for Blackstart]. | Response | Amol/Art/Bill | Each of these are separate agreements. The requirement was not meant to imply they were the same.
37b | RELIANT | MW | 9 | o The Registration System must be able to change information maintained through a Notice of Change of Information by Market Participants. [Reliant: the system also needs to keep track of the changes and the dates so that for resettlement etc, appropriate relationship information is maintained.] | Accepted | Amol/Art/Bill | The Registration System must be able to change information maintained through a Notice of Change of Information by Market Participants.The system will also maintain the history of changes.
37c | RELIANT | MW | 9 | o The Registration System must maintain the date by which the MP Entities wishes to start activities. [Reliant: What does start activities mean?] |  |  | The Registration System must maintain the date by which the MP Entities wishes to become active in the Market.
38 | RELIANT | MW | 10 | [Reliant: if there is more than one wholesale point of delivery for any given NOIE, this sentence needs to be revised to reflect that.] | Accepted | Amol/Art/Bill | A NOIE can have more than one wholesale point of delivery. o Each NOIEs wholesale point(s) of delivery must be assigned an ESI ID. The ESI ID must be assigned to an LSE.
39 | RELIANT | MW | 11 | [Reliant: the term LAAR does not exist in the Nodal Protocols. Please define acronyms before use.] | Accepted | Amol/Art/Bill | Load Resources or Load Acting as A Resource. Full form is mentioned into the document
40 | RELIANT | MW | 19 | . [Reliant: Please describe what an ‘attachment’ in Siebel means. Is this a scanned in document? Does every MP have to provide the same categories of information?] | Response | Amol/Art/Bill | The verifiable cost template will be accepted electronically as an attachment. • All the resource parameter/verifiable costs details (in template form) will be captured in Siebel as an attachment (scan document). The information will be entered in LODESTAR manually. Information related to MMS will be
41 | RELIANT | MW | 19 | . [Reliant: given MMS reliance on data from Registration, the interface needs to be dynamic or there needs to be an intermediate table from which MMS pulls that updates upon the appropriate timeframe after update in Registration.] | Response | Amol/Art/Bill | All interfaces will be addressed in Detail Design.
42 | RELIANT | MW | 19 | [Reliant: Who actually validates that the data in Registration are correct?] | Response | Amol/Art/Bill | Wholesale Client Business
43 | RELIANT | MW | 20, 23 | [Reliant: why aren’t interfaces being developed for MPs to enter the information and then once it is submitted it flags an analyst for validation? Why does the MP fill out a form and then ERCOT staff retypes it?] . [Reliant: as noted above, this seems like a process that could be streamlined.] | Response | Amol/Art/Bill | Upgrading the method of interactions with respect to receiving forms is not within the scope of the Nodal project. Whole this is a desirable upgrade, it is not being considered in this project.
44 | RELIANT | MW | 23 | Certification Begin Date can be used indicate the date by which MP Entities wish to start the activities. | Accepted | Amol/Art/Bill | Grammatical error
45 | RELIANT | MW | 23 | client rep and its (?) manager | Accepted | Amol/Art/Bill | Grammatical error
46 | RELIANT | MW | 24 | [Reliant: notification of what?] | Response | Amol/Art/Bill | Email notification for start date of MP account to Client Service and additional groups (Frequency of email notifications will be provided by business)
47 | RELIANT | MW | 24 | [Reliant: is it only trading or is all participation prohibited?] | Response | Amol/Art/Bill | All participation will be prohibited to trade into the Market for the respected MP when status is Not Qualified or In Active. Nodal protocol
48 | RELIANT | MW | 24 | . [Reliant: is it only the partner details or does it include the partner information? Care should be taken with the partner information as outside of the particular business relationship that is being dissolved by ERCOT, the partner may still be qualified to partner with other MPs. A ‘drop to POLR’ scenario would be an example of where the partners continue to do business through ERCOT.] | Response | Amol/Art/Bill | Yes. The relationship between MP and Its partner will be disabled. Partner will be Active
49 | RELIANT | MW | 24 | ) [Reliant: why should ERCOT be able to modify an MPs information without notifying the MP? Who is on the “Team?” How will MPs be notified of modified data and what such data are subject to modification by the ERCOT Team?] | Response | Amol/Art/Bill | No one on the Account Management "Team" can modify the record. Only the Registration people in Market Support can alter the MP record, and only by an NCI or other approved document.
50 | RELIANT | MW | 24 | Currently financial information is not required by any other system. [Reliant: but this information is required by the credit system under nodal.] Registration system is not going to change the current financial profile unless requested. [Reliant: please check with the credit group on this.] | Accepted | Amol/Art/Bill | Strike the line.
51 | RELIANT | MW | 24 | Reliant: whose digital signature?] | Response | Amol/Art/Bill | MP Representative's digital signature. ERCOT is working on strategy on accepting forms electronically or accepting digital signatures
52 | RELIANT | MW | 24 | [Reliant: it should also maintain an audit trail of any changes to the system | Response | Amol/Art/Bill | All the important fields decided by Wholesale client business are audit trail by the Registration System
53 | RELIANT | MW | 26 | [Reliant: This appears to be the chart that was at the beginning. It should be included only once and referenced.] | Response | Amol/Art/Bill | Good Idea. This is not a show stopper issue. Everytime user needs to scroll up the document.
54 | RELIANT | MW | 27 | [Reliant: what does this mean?] | Response | Amol/Art/Bill | Refer section 2.1.3 Billing Profile section Bank Name Account Name Account # Routing # Bill Type Bill Calc Code Contact Last name Contact First Name Bank Address Bank’s City Bank’s State Bank’s Zip Country
55 | RELIANT | MW | 27 | . [Reliant: as noted above, there is a more efficient way to accomplish this that reduces the chance for errors.] | Response | Amol/Art/Bill | Upgrading the method of interactions with respect to receiving forms is not within the scope of the Nodal project. Whole this is a desirable upgrade, it is not being considered in this project.
56 | RELIANT | MW | 27 | [Reliant: There is an NPRR sponsored by ERCOT to eliminate this. Check with the Credit Group to see if it passed or check out NPRRs.] | Response | Amol/Art/Bill | If this NPRR it will be taken care globally and not in each individual document. For Credit group separate CSD is present. The protocol change is for Zonal Market and not the Nodal market
57 | RELIANT | MW | 27 | • Siebel will provide a separate flag to identify signed agreements between QSE and ERCOT • QSE and sub QSE will be defined as separate QSEs in Siebel, each with a different ERCOT Account Id. • Siebel will maintain Ancillary Qualification Status of QSEs. • Siebel will maintain partnership information between a QSE and Sub QSE. Predefined Queries provided for grouping the information related to each partnership relation. Addition to this Siebel will provide audit trail utility to maintain the history of partnerships. Refer Partnership information from 2.1.3. • QSE can represent LSEs or Resources. [Reliant: QSEs represent these entities, not the other way around.] For such partnership start | Accepted / Response | Amol/Art/Bill | Grammatical Error. Current Zonal partnership module supports this
58 | RELIANT | MW | 28 | . [Reliant: if Registration does not generate this notification automatically, it shouldn’t be in this document.] | Response | Amol/Art/Bill | This is required in this document as per nodal protocol
59 | RELIANT | MW | 28 | Siebel will store the relationship between Resource and Resource Entities. | Accepted | Amol/Art/Bill | Grammatical Error
60 | RELIANT | MW | 28 | [Reliant: what is an example of an Operating Way?] | Accepted | Amol/Art/Randy | This will be addressed in a white paper developed by ERCOT and under review by TPTF. This paper addresses the deployment and settlement of combined cycle units and the various configurations available for these units.
61 | RELIANT | MW | 29 | . [Reliant: what corrections are envisioned?] | Response | Amol/Art/Bill | Currently Resource Entities are stored into Siebel as MP type RESOURCE. In order to inline with Nodal protocols Updates will be done in Siebel to change the Mp type to Resource Entities.
62 | RELIANT | MW | 29 | · [Reliant: all subtypes with generic cost categories should be included.] | Response | Amol/Art/Bill | ERCOT does not understand this question and requests Reliant to clarify.
63 | RELIANT | MW | 29 | · .[Reliant: define ‘start activities.’] | Response | Amol/Art/Bill | • Siebel maintains created date, certification begin date & certification end date. Certification begin date can be used as a date by which the Resource Entity wishes to begin Market activities.
64 | RELIANT | MW | 30 | Siebel will identify the resource entity as Hydroelectric All-Inclusive report. [Reliant: what does this mean?] | Accepted | Amol/Art/Bill | Hydroelectric Resource : Statement Modified
|  |  | 30 | • Team members associated with the Resource record will able to modify the record. Primary team member is assigned to each Resource record. In addition to this Siebel will provide a separate MP administration screen. Marketing admin or Siebel admin can be able to modify the Resource record. [Reliant: we do not support this construct, especially since it does not provide notification to the Market Participant that ERCOT staff has changed Registration information. Please see comments above.] |  |  | No one on the Account Management "Team" can modify the record. Only the Registration people in Market Support can alter the MP record, and only by an NCI or other approved document.
65 | RELIANT | MW | 30 | [Reliant: what does this mean—correction? Is this the process to convert existing information to the nodal system?] | Response | Amol/Art/Bill | This is a change of label. Currently Resource Entities are stored into Siebel as MP type RESOURCE. In order to inline with Nodal protocols Updates will be done in Siebel to change the Mp type to Resource Entities.
66 | RELIANT | MW | 30 | · [Reliant: Please capitalize all “resource” terms that refer to a “Resource” as defined in Protocols. Ditto for “ancillary service.”] | Accepted | Amol/Art/Bill | Grammatical Error
67 | RELIANT | MW | 30 | · .[Reliant: does this mean Block Load Transfer?] It will fill up the asset registration form. [Reliant: what does this mean, “fill up the asset registration form?] | Accepted | Amol/Art/Bill | Yes. Error from our side
68 | RELIANT | MW | 35 | [Reliant: how will Siebel remove these things?] | Accepted | Amol/Art/Bill | Current Zonal Registration system has various fields or check box like Legal, Financial, Operational etc. After introducing the Account/Contact Type as a drop down, the above check box are not required. Siebel developer will remove various check box Legal, Financial, Operational etc which are not required.
69 | RELIANT | MW | 37 | [Reliant: is there more than one per NOIE?] The ESIID must be assigned to an LSE. These details will be stored in LODESTAR. | Response | Amol/Art/Bill | A NOIE can have more than one wholesale point of delivery. Each NOIEs wholesale point(s) of delivery must be assigned an ESIID.
70 | RELIANT | MW | 38 | [Reliant: why aren’t interfaces being developed so MPs enter the information? Why does ERCOT want the liability of mis-stating Resource information?] | Response | Amol/Art/Bill | Upgrading the method of interactions with respect to receiving forms is not within the scope of the Nodal project. Whole this is a desirable upgrade, it is not being considered in this project.
71 | RELIANT | MW | 39 | [Reliant: All Resource parameters as defined in Protocols should be included here | Accepted | Amol/Art/Bill | Yes. Refer page # 9 & 10 ( section For Resource Parameters / Information). Wholesale Market Sub committee is working on that. In detail design all the attributes will be considered.
72 | TXU | H Durrwachter | 5 | TXU Comment: The above table presumes that QSEs will be making all the changes to Resource Parameters. It is possible (and quite likely) that Resource Entities will also make changes to Resource Parameters | Response | Amol/Art/Bill | <In accordance with Protocol Section 3.7, it is the QSE that submits Resource Parameters.>
73 | TXU | H Durrwachter | 5 | (Resource Parameters are not new) | Response | Amol/Art/Bill | Resource Parameters are not new. But the interface to MMS is new. The table indicates that Registration information will flow down to various systems.
74 | TXU | H Durrwachter | 6 | (TXU Comment: what about Black Start agreements?) | Response | Amol/Art/Bill | Black Start Agreement is there. Refer Requirements common to All MP entities on Page 8
75 | TXU | H Durrwachter | 7 | (Comment: registration covered in bullet above) | Accepted | Amol/Art/Bill | Valid Suggesstion
76 | TXU | H Durrwachter | 7 | (TXU Comment: what about a Resource Entity’s decision to return a unit to service? How will that be captured?) | Response | Art/Bill/Randy | mothballed units still in syatem - no action needed, retired unit that is brought back will need to be registered as a new unit
77 | TXU | H Durrwachter | 7 | (Comment: only Mothballed Units submit estimates of lead time to return to service. RMR units are already in operation (subject to the RMR contract)) | Response | Art/Bill/Randy | planning will need to anwser question on "lead times"
78 | TXU | H Durrwachter | 8 | o (Comment: shouldn’t the Registration System also capture information on the following items?  Black start contract terms, capacity, operating limitations, etc.  Probability of Mothballed Units Returning to Service (submitted by Resource Owners) | Response | Art/Bill/Randy | planning will need to anwser question on these topics
79 | TXU | H Durrwachter | 9 | o Provide the ability for the Authorized Representative of a registered Market Participant to electronically update information provided to ERCOT during the registration process. (Comment: The current process is 100% paper driven. Electronic signatures or use of digital certificates should be allowed in lieu of requiring written signatures). | Response | Amol/Art/Bill | Registration forms will be accepted electronically as a Service Request module as an attachment. Notification email will be sent to respective Account Manager. ERCOT is working on the strategy for Accepting forms electronically. Depending upon the form type ERCOT will decide the digital signature policy. Say: wet signatures, scan copies and digital certificates MPs authorized representative will able to submit the forms electronically. Due to Budget Constraint we are not going to provide any API during this phase of project
80 | TXU | H Durrwachter | 9 | The Registration System must be able to electronically change information maintained through a Notice of Change of Information by the Authorized Representative of a Market Participant. | Rejected | Amol/Art/Bill | Protocol does not mention to submit the documents electronically. Refer Response for Sr # 79
81 | TXU | H Durrwachter | 9 | Entity or QSE | Accepted | Amol/Art/Bill | valid Request
82 | TXU | H Durrwachter | 9 | o The Registration System must be able to capture Resource Parameters submitted by each QSE or each Resource Entity for each Generation Resource, Generation Resource Parameters submitted by each QSE or Resource Entity | Accepted | Amol/Art/Bill | Valid Request
83 | TXU | H Durrwachter | 11 | TXU Comment: In the above figure the box labeled “LAAR” is confusing because the Nodal Protocols do not use the term “LAAR”. The Nodal Protocols refer only Load Resources. Secondly, what is a LAAR system? It seems that the registration system will need to interface with the MMS, which is not shown but should be shown. Information about Load Resources is a subset of the information that is acquired by the Registration System and required by MMS. | Accepted | Amol/Art/Bill | LAAR changed to Load Resources. ( or Load Acting as a Resource)
84 | TXU | H Durrwachter | 34 | (Comment: Where does the Authorized Representative fit in this? Authorized Representative is not mentioned. ) | Response | Amol/Art/Bill | Authorized Representative : Account/Contact Type = 'Primary' Account / Contact Type or various contact roles: 1. Customer Services 2. Financial 3. Legal 4. Operational 5. Primary 6. USA 7. Technical 8. ERCOT 9. Expired 10. Secondary 11. Officer 12. Working 13. MT Administrator 14. IAS Primary 15. IAS Secondary 16. Incident Report

## <Registration>_Aft No COP vote
Document Name:
# | Issuing Entity | Name | Page Number | Description | Accepted / Rejected / Response | Reviewer | Reason
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42