## Qualification
| Document Name: | Response_to_Comments_Qualification_Approach_v0.6
| Issuing Entity | Name | Page Number | Description | Accepted / Rejected | Reviewer | Reason
1 | Garland Power & Light | Ronnie Hoeinghaus | p.3 | How does ERCOT propose to coordinate training with the Market Implementation as it appears there will not be adequate time to train the MP’s in the time that the courses become available and the required EDS activities? Also, when is the Product Training (EMS, MMS, NMMS, CRR, CMM) and Application Support Training (EMS, MMS, NMMS, CRR, CMM, OS, MIS, EDW, MP Registration) going to be available for the required ERCOT training sessions – do not see them on the schedule yet and again the question, will there be adequate time for training to support the timeline? | Accepted | Ted Hailu | Comment is about coordination of EDS phases and training ( Concept training and produict training). Will be addressed during Readiness Approach and/or Training discussions at TPTF.
2 | Garland Power & Light | Ronnie Hoeinghaus | p.3, p.5 | In the EDS Market Trials Approach document, it says that the ERCOT team & the Market Participants will work together to finalize a set of measurable entrance & exit criteria for readiness criteria. In this document, it sounds like ERCOT is going to do it alone (“ERCOT will define…”. Believe it should be a joint effort (as the EDS Market Trials Approach document states) for this effort. | Accepted | Ted Hailu | ERCOT will work with Market Participants to define readiness criteria
3 | Garland Power & Light | Ronnie Hoeinghaus | p.6 | Believe should add qualification based on market participation level explanation that is on the bottom of slide 4 of the ERCOT Qualification Approach overview presented to TPTF on December 4th | Accepted | Ted Hailu | Added expanation of QSE qualification by level
4 | Garland Power & Light | Ronnie Hoeinghaus | p.6 | Believe should add the qualification table located on slide 8 of the ERCOT Qualification Approach overview presented to TPTF on December 4th | Accepted | Ted Hailu | Added table detailing QSE qualification by level to document
5 | Garland Power & Light | Ronnie Hoeinghaus | p.7 | Does this also include entities that qualify for PCRR’s? | Accepted | Ted Hailu | Yes. NOIEs eligible for PCRR allocation will also need to qulaify as CRR Account Holders.
6 | Garland Power & Light | Ronnie Hoeinghaus | p.9 | Balancing not in Nodal | Rejected | Ted Hailu | The list of Ancillary Services mentioned in the document is for the current market which includes balancing energy
7 | Garland Power & Light | Ronnie Hoeinghaus | p.9 | It would seem that there should be some type of test for receiving & responding to a Base Point - above list has checks for providing for ancillary services but what if a unit is not going to provide ancillary services? | Accepted | Ted Hailu | Added a statement that ERCOT will test the ability to receive and respond to base points being sent from ERCOT even for units not providing Ancillary Services
8 | Garland Power & Light | Ronnie Hoeinghaus | p.11 | According to the EMS SCADA document, you are expecting to monitor 200,000 analogs, 160,000 status points and expect to send 7,900 points for Nodal. Please explain the methodology and expected time to accomplish a point by point checkout of the Nodal points & how it fits into the Nodal timeline. | Accepted | Ted Hailu | The approach to the point-by-point telemetry checkout will be discussed as part of the EDS-1 and 2 dicussions with TPTF
9 | Garland Power & Light | Ronnie Hoeinghaus | p.13 | Did you mean Section 8.1.2.1? | Accepted | Ted Hailu | Yes. Protocol reference corrected
10 | Garland Power & Light | Ronnie Hoeinghaus | p.14 | this assumes that all resources will be on line at this particular testing time – for whatever reason, 1 or more units may not be available at this time frame thus requiring more than one qualification test) | Accepted | Ted Hailu | ERCOT will work with each QSE to accommodate units that may not be available for testing at the scheduled time for testing of units for each QSE
11 | Garland Power & Light | Ronnie Hoeinghaus | p.14 | Has ERCOT projected the amount of time required to qualify all Resources providing A/S to make sure it is in line with Market Go-Live timeline? | Accepted | Ted Hailu | This is a recognized critical path item. Work is still in progress to assure that AS qualification for most units is completed in time to support the market trials. AS qualifications will continue until the qualification freeze period.
12 | Garland Power & Light | Ronnie Hoeinghaus | p.15 | All QSEs planning to participate in the nodal market at the go-live date will need to complete qualification activities, and they must be completed prior to the beginning of this period. ERCOT shall allow a reasonable timeline for all QSE’s that wish to provide Ancillary Services to complete qualification tests prior to a go-live date implementation. | Accepted | Ted Hailu | This is a recognized critical path item. Work is still in progress to assure that AS qualification for most units is completed in time to support the market trials. AS qualifications will continue until the qualification freeze period.
13 | Garland Power & Light | Ronnie Hoeinghaus | p.15 | The table below does not match the Qualification Timeline table or chart presented to TPTF on December 4th, 2006 in the ERCOT Qualification Approach Overview – which is correct? Believe the chart on page 17 of the overview presentation should be added to this document once the dates are reconciled as mentioned above. | Accepted | Ted Hailu | Dates on table reconciled
14 | Brazos | Tony Kroskey | various | Various edits (Grammar, re-wording etc…) | Accepted | Ted Hailu | Made suggested changes
15 | TXU PM and TXU Power | Henry Durrwachter | Item 7. | In this document, ERCOT has outlined their proposed approach to qualifying Market Participants in the transition to the nodal market design. The ERCOT Protocols require that Market Participants demonstrate to ERCOT’s reasonable satisfaction that they are capable of performing the functions required of them by the protocols. In particular, activity no. 7 describes the proposed approach for the qualification criteria and testing methods for the Ancillary Services (AS) of Responsive Reserve, Regulation Reserve, and Non-Spinning Reserve. This proposed activity includes the testing of the QSE and each resource for each ancillary service provided. TXU Portfolio Management Company LP (TXU PM) and TXU Generation Company LP (TXU Power) respectfully submit the following comments and proposal regarding the ERCOT requirements for qualification criteria for providing ancillary services in the nodal market. | Response | Hailu/Mereness | Pending review of proposal by ERCOT Operations
16 | TXU PM and TXU Power | Henry Durrwachter | Item 7. | The timeline for testing AS, January 1, 2008 through September 1, 2008, presents challenges to the Nodal Market implementation schedule. ERCOT is proposing testing each QSE’s resources simultaneously to help alleviate the timing issues associated with testing and qualifying approximately 500 different resources. One of the reasons for moving to a nodal market is to improve the efficiency of the market. Testing of each resource will necessitate operating units out of merit order for testing, introducing inefficiency and excess costs into the market. Existing market participants have been providing AS by reliably operating their Resources to maintain the reliability of the ERCOT grid. TXU PM and TXU Power recommend an approach to AS qualification and testing that would alleviate timing issues and challenges, reduce market cost and inefficiency, follow methods accepted for compliance certification by ERCOT in other areas, and support the integrity of the ERCOT market and reliability of the ERCOT grid. | Response | Hailu/Mereness | Pending review of proposal by ERCOT Operations
17 | TXU PM and TXU Power | Henry Durrwachter | Item 7. | TXU PM and TXU Power recommend that ERCOT utilize a self-certification approach (subject to audit by ERCOT) that would apply to QSE’s and resources that are currently providing AS in the existing ERCOT zonal market. While testing may indicate a resource/QSE capability at a given time under controlled circumstances, historical performance of market participants provides a truer picture of the actual capabilities of a resource and/or a QSE to provide Ancillary Services in real time under real market conditions. Each year, ERCOT utilizes self-certification of compliance subject to audit for a variety of testing and capability requirements. TXU PM&Power respectfully request ERCOT utilize the same approach for AS qualification for current market participants when transitioning to Nodal. This will reduce the burden on ERCOT to do qualification testing during nodal implementation. Specifically, TXU recommends that ERCOT Operations and MPs (through WMS) jointly develop a self-certification and audit process to be reviewed and approved by TAC in a timely manner. | Response | Hailu/Mereness | Pending review of proposal by ERCOT Operations
18 | TXU PM and TXU Power | Henry Durrwachter | p.11 | ERCOT should also include submittal and maintenance of verifiable costs for each generating resource. In addition, ERCOT should ensure that seasonal differences or values can be collected and maintained. | Rejected | Hailu/Mereness | Out of Scope of this Qualification Approach document, but addressed in CommOps Registration Requirements (http://nodal.ercot.com/docs/pd/coms/pd/regreq/09a4_CommOps_Registration_Requirements_v1.0.doc). - Reqts for Verifiable Costs as FR2 - Reqts for Seasonal Resource Parameters as FR37