| Texas Nodal Market Implementation Program - Overview |
| --- |
| Program Director | Jerry Sullivan | Reporting Period | Status at 01/22/2007 |

Confidence in delivery – RAG Status

| Dimension | This week | Trend | Commentary |
| --- | --- | --- | --- |
| Scope/baseline | A | = | Working to close NPRR backlog on all projects to November Protocol version |
| Resources | A | ( | Initiated discussions from ERCOT staff for additional personnel. Looking to ramp up committed resources from zonal for nodal projects and transition preparation |
| Costs | A | = | Second reporting cycle initiated. Tracking to budget with some variances. Working with finance to close variances |
| Timescales | R | ( | December TPTF commitments met. Working on requirement and CSD approvals with TPTF |
| Critical dependencies | R | ( | Critical path work identified major build and release sequence to support EDS trials; working to finalize integrated project schedules to confirm feasibility of build sequence and timescales for downstream projects (integration, Integration testing, and market trials) |
| Vendors | A | = | ERCOT Board of Directors postponed approval of CRR Phase II contract until January 2007. Project team to assess impact during meetings with vendor and determine recovery plan |
| Stakeholders | A | ( | Requirements and CSDs approaching approval, and initial Interface documents delivered to TPTF. Working to make MP Sandbox available mid February “Deep dive” review scheduled with ERCOT Executives, business/IT owners and Nodal leadership to improve engagement |

( - Worse, ( - Better, =  - Same

# Key Issues for escalation

# IDA

- Working to improve QA, traceability across the program

# NMMS

- Need to correct list of electrical bus names, work in progress with MPs

MER Training

- Towards the end of 2007 training will require dedicated facilities to deliver training.  We are pursuing ERCOT facilities and free MP facilities but there is a very real concern that we will not be able to meet the facility requirement.

# MER & MIS

- CEII security handling strategy has not yet been determined by Security. Need a decision by March 1st, will escalate if none.

- Identity Management is required for MIS go-live, and currently there is continued discussion within ERCOT about how/whether to fund it.

IRT

- Recent efforts on program critical path and facility needs are causing delays in our deliverable creation (related to market trials).

  - Focusing some of the market trials team back on to market trials to slow schedule slippage.

  - IRT expects ongoing maintenance of the critical path to be transitioned to the Nodal PMO by end of January.

- TPTF is focused on Requirements and Conceptual System Designs (CSDs) and has indicated participation in readiness criteria development and market trials will be delayed.

  - Slight delay has been estimated (2 weeks).  Readiness Advisor team has a lower than estimated burn rate to date so expecting no cost impact to the project.

Key achievements and expectations

| Project | Achievements this Period | Outlook for next period |
| --- | --- | --- |
| PMO | Measures signed off for Nodal balanced scorecard | Prepare for Nodal Program ‘deep-dive’ Produce draft prototype for Nodal balanced scorecard |
| IDA | Preliminary review of EMS RPP CSD Preliminary review of CRR Use Cases Review and response to TPTF comments for EMS requirements QA Operation document approved 2nd phase SoSA planned SoSA POC initiated | Publish the consolidated IDA/EA issues list Review/update of the artifacts tracking spreadsheet Review of CRR Use Cases QA Adoption Training workshop Initial End-to-End testing workshop with stakeholders End-to-End plan agreed and publicized |
| NMMS | NMMS: Develop training documentation NMT: Now 75% complete with 4,013 Network operations modeling issues. Closed out of the 5,359 identified data issues. The new query (based on the 10/30/2006 to 12/31/2006 period) results brought in 1,082 additional new pending data issues. NMT: Created development, SIR and MCD to promote measurement weight fix to iTEST. | NMMS: Prepare training classes. NMMS: Clarify and document modeling issues. NMT: Continue to internally resolve the outstanding issues prior to meeting with MPs. NMT: Conduct work on QSE issues. |
| EMS | Continued TPTF Review of EMS Requirements Comments & Responses. Completed EMS/MMS Basic Impact (Y/N) Analysis For NPRR’s Through Jan. 2007 | Continue Review of TPTF Comments & Responses of EMS Requirements Commence TPTF Review of OS Requirements Documents Continue EMS/MMS Phase 2 Baseline Planning & Budgeting Activity Commence Full Funding SOW Amendment for EMS Phase 2 Vendor Launch First OS Work Tasks to System Operations Designees |
| MMS | TPTF Approved All (Five) MMS Requirements Documents | Complete Full Funding SOW Amendment for MMS Phase 2 Vendor |
| CRR | Hired Sr. Market Analyst Reviewed System Level Use Cases with team Developed initial list of NOIE Generators Begun McCamey Area map | BOD vote on budget Draft Technical Architecture document |
| COMS | Completed second draft of development guidelines. Began interface reconciliation with CMM and EMS. Obtained TPTF approval for all but one COMS CSD Registration: Review by TPTF on 12/5 and looking for comments by 12/15. Approval is scheduled for 1/9/2007. | COMS: Conduct architectural workshops (settlements business process) Continue data model definition CMM: Complete initial draft Detail Validate Exposure Calculation Model Define Test Plan Standup CMM Sandbox system |
| MER - Training | Launch of Online testing for ERCOT Nodal 101 the Basics Delivery of ERCOT Nodal 101 the Basics in Houston. | Continue development of text for WBT ERCOT Nodal 101 Continue development of LSE 201, Transitions and Basic Training Courses |
| MER - MIS | Conceptual System Design has been approved by TPTF. Security Sign Off has been obtained for Security Audit documents Technical Architecture Document has been completed and submitted to the EA group. All Use Cases finalized Finalized MIS Punchlist. | Continued content inventory documentation UI design for notifications entry (will require a CR) Dashboards analysis, design and wireframes Site visit to StarTex Power rescheduled. Submission of final Use Cases. Compare AsisSiteMap to current Requirements |
| EDW | EDW Governance document reviewed by stakeholders. Achieved definitions of 80% of project areas and have begun process of high-level requirements gathering for those identified. | Receive feedback on EDW engagement process. Deliver MIS/EDW requirements collaboration presentation to Nodal Leadership team. |
| Infrastructure | Web Services Sandbox: Server build completed and turned over to the project team. EDS ½ Environment: Vendor reported successful test of the software targeted for these servers EA Lab: Progress made and build nearing completion | Siebel Development environment: complete build Lodestar development environment: Complete build of blade server P595 Austin Standup: IBM to complete engineering review. Credit monitoring development environment: Schedule second round of server builds |
| Enterprise Integration | Nodal Integration Flow Matrix (D2.3) MIS External REQ Specs (D4.1) NMMS-Settlement Test Data & Scripts (D6.4) Registration-CMM Interface Design Specs (D7.2) S&B-CMM Interface Requirements Specs (D8.1) EI Team and MMS/ABB meeting held to discuss working together more effectively. Initial draft of Mapping EDS/Release/Build Sequences completed. Stephen Kerr, joined as the ERCOT Project Manager this week. | Integration Roadmap w/ Phasing by EDS (D1.6) MMS-MIS Interface Build Iteration (D5.5) S&B – CMM Interface Design Specs (D8.2) |
| Integration Testing | COMS Met with CMM team to collaboratively develop test plan Received use cases from Settlements and Billing for test case writers to provide test case examples Data/E2E/Info QC-Database POC Testing POC for QC-Database Performance Testing Tools Review of Sandbox Test Script Breakdown Reviewed LMS Test Cases Organized LMS Requirements in Req Pro and QC Verified LMS Requirements and finalized scope for latest LMS test cycle Project Reviewed process for establishing duration estimates for testing Established metrics for QA Assessment process | COMS Test case writer to create separate test case documents in standard template from ROME test cases NMMS Create initial NMMS FAT Test Plan Create initial estimation for NMMS Test Tools Update QC to Req Pro Sync and Transfer Ownership from IT to Testing Review all LMS Test Scripts and submit to business for approval Review LMS Test environment for completeness and standards Project Submit request to vendors for additional resources Complete December budget summary |
| ERCOT Readiness & Transition | Transition: Continued discussions with ABB / Areva regarding training curriculum Two resources assigned to control room desk procedure development Market Trials: Continued work on program critical path Build sequence matrix (v5) and diagram (v2) reviewed with projects Posted market trials overview presentation for TPTF meeting on 1/25 (addresses market feedback) TA document for EDS 1 & 2 environments completed, infrastructure ordered Readiness Advisor: Conducted second round of discussions with Internal metric owners | Transition: Organization structure / sizing discussions with ERCOT Directors IRT Team organization review with Project Director Transition Work plan review with Project Director Training curriculum review Market Trials Continue Critical Path refinement Present response to market comments re: market trials approach Readiness Advisor Present to TPTF: Status, candidate metrics, metric sub-group scope and involvement |

Key Milestone Status

| Control Milestone | Baseline | Actual/F’cast | Comment |
| --- | --- | --- | --- |
| Requirements approval | 10/31/2006 | 1/24/2007 | Slippage to key reqts (EMS, MMS & EDW) |
| Key CSD submission | 12/31/2006 | 12/31/2006 | Planned CSDs issued on schedule |
| Key CSD approval | 2/28/2007 | 2/28/2007 | CRR, MIS and most COMS CSDs approved ahead of schedule |
| Vendor SOW BOD approval | 12/10/2006 | 1/16/2006 | CRR vendor approval delayed |
| Interface specs – draft | 12/31/2006 | 12/31/2006 | Deliverable issued to TPTF on schedule |
| Market Operations Sandbox | 1/31/2007 | 2/15/2007 | Initial functionality will be limited and depends on planned January TIBCO release |
| Interface specs – final | 3/31/2007 | 3/31/2007 |  |

Top Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| EDS trials disrupted by inability of upstream projects to deliver product in time to enable proper integration testing sequence | H | H | Establish build and release strategy for critical path Establish releases and dependencies Workshops with PM’s to agree details and ensuring commitments |
| Lack of discipline in managing ongoing changes to protocols impact budget and delivery schedule | H | H | Address backlog NPRR’s for cost and schedule impact, TPTF and Steering Board approval of changed scope Periodically synchronize projects to target versions of Protocols Establish more proactive, timely change control process |
| Delays to the integration project could impact the Nodal critical path | H | H | Identify and establish integration vendor Obtain Integration PM resource Initiate Integration activity to identify issues |