## Slide 1: NMT Network Operations Modeling & Telemetry
TAC Meeting
February 2007
By Raj Chudgar, ERCOT

## Slide 2: NMT – Network Operations Modeling & Telemetry - Project
Topics to Cover
  Network Model Data Issues
  Critical Measurements Telemetry Analysis
  Measurement Weights Modeling

## Slide 3: NMT – Network Operations Modeling & Telemetry - Project
  Network Model Data Issues

## Slide 4: NMT – Network Operations Modeling & Telemetry - Project
Model Data Issues – as of 01/26/2007
  Began with 200+ manually entered issues in Mid-August 2006
  Developed the Automated Query Process to find additional issues
    Ran First Case from September 2006 thru October 2006
      Generated 4000 new issues
      NMT Closed 78% before running next case
    Ran Second Case from November 2006 thru December 2006
      Generated 1100 new issues
      Total baseline is 5400 issues
      NMT has Closed 4100+ or 77% of new baseline
    Remaining issues
      319 Assigned to ERCOT to resolve internally
      882 Assigned to MP to email this week
    Next Case to run from January 2007 thru mid-February 2007
  Next Steps
    Begin contacting QSEs
    Document NMT processes to hand over to ERCOT Operations
    Begin wrap of NMT project to end on 3/31/2007

## Slide 5: NMT – Network Operations Modeling & Telemetry - Project
Network Model Data Issues Status – by MP

## Slide 6: NMT – Network Operations Modeling & Telemetry - Project
  Critical Measurements Telemetry Analysis

## Slide 7: NMT – Network Operations Modeling & Telemetry - Project
Critical Measurements Telemetry Analysis
  Spreadsheet Feedback
    Continuing to work with each of the Market Participants to:
      collect and document comments and feedback
      clarify questions
      perform additional analysis
  Recent emailing and MP contact in January 2007
  Next steps:
    Continue to implement modeling changes as a result of analysis
    Complete documentation of feedback by end-of-February 2007
    Publish results and schedules by end-of-March 2007

## Slide 8: NMT – Network Operations Modeling & Telemetry - Project
Critical Measurements Telemetry Analysis

## Slide 9: NMT – Network Operations Modeling & Telemetry - Project
  Measurement Weights Modeling

## Slide 10: NMT – Network Operations Modeling & Telemetry - Project
Measurement Weights Modeling
Analysis and Progress Update
Setup Tuning Environment with near real-time feeds from Production
  Measurement weights were re-defined
  Requires software change to add plausibility checks on negative load telemetries
  Changed the limits for a set of unit capability curves
Tuning Environment Results
  Bus mismatches (Mw/Mvar) after SE convergence are reduced
  The maximum difference in Mw/Mvar flows between SE and Power Flow (RTCA base case) are reduced
  The number of voltage violations on the RTCA base case are reduced
  The performance index was improved.
Implementation Plan
  Test in the ERCOT ITEST environment in February 2007 and promote to ERCOT Production in March 2007

## Slide 11: NMT – Network Operations Modeling & Telemetry - Project
Measurement Weights – Point in time –
16 Hour Study Comparison to Production

## Slide 12: NMT – Network Operations Modeling & Telemetry - Project
Measurement Weights – Point in time –
16 Hour Study Comparison to Production

## Slide 13: NMT – Network Operations Modeling & Telemetry - Project
Measurement Weights – Point in time –
16 Hour Study Comparison to Production

## Slide 14: NMT – Network Operations Modeling & Telemetry - Project
Summary
  Major Model clean-up underway
    Target to complete by 3/31/2007
  Major effort to reduce critical measurements and improve observability underway
    Target to have all justifications and schedules for new implementations by 3/31/2007
    Implementation schedule will be published end of 1Q2007
  Measurement Weights tuning recommendations to be implemented into Production March 2007
  ERCOT will continue to provide progress reports to TPTF, TAC, and ROS on a regular basis